Oxford Academy Project (Oxfordshire 2)

Information Brochure / Initial Consultation – timetable

| Item | Deadline / Date |
| --- | --- |
| Meetings with Governing bodies to discuss academy proposals. | 29th March 2007 |
| Other “Progress/pre-consultation” meetings ( prior to brochure distribution) | Staff 12 March Primary Heads 01 May 2007 |
| Initial letter and Information Brochure Production | Consideration of 1st text draft by PSG | 12th April 2007 |
|  | Draft introduction letter for Parents prepared for comment Draft introduction letter for staff/governors and other schools | 13th April 2007 25th April 2007 |
|  | Agreement on letter for parents Agreement on other letters | 25th April 2007 27th April 2007 |
|  | Letter parents by LA/School & Letters or staff/other schools | w/c 23 April 2007 w/c 30 April 2007 |
|  | Final brochure text agreed by key stakeholders | 27th April 2007 |
|  | Initial layout with illustrations drafted | 4th May 2007 |
|  | Final review of brochure by key stakeholders and final amendments | 11th May 2007 |
|  | Agree Wording layout of Consultation Meeting Flyer | 1st May 2007 |
|  | Printing and arrival (Flyer) | 14th -18 May 2007 |
|  | Agreement to open informal consultation granted | 4th June |
|  | Printing and arrival (Brochure) | w/c 28 May 2007 |
|  | Agree wording newspaper consultation advertisement | 14th May 2007 |
|  | Agree final design of newspaper consultation advertisement | 18th May 2007 |
|  | Printing of Consultation meeting Newspaper advertisement | w/c 4th June 2007 (submit on the assumption permission will be granted) |
|  | Brochure Distribution | 5th-11th June 2007 |
| Start of Informal Consultation Period (6 weeks) | 11th June 2007 |
| Public Meetings 1. Blackbird Leys Community centre 2.Rose Hill Community Centre 3. Peers School 4. Pegasus Primary School Staff and Governing Body Students Parents and community SRG | 12 June – 17.00 14 June – 17.00 18th June -16:30 -17:30 19th June -15:30 -17:30 6th - 8th June (TBC) 6th -8th June (TBC) 6th -19th June 2007 (TBC) |
| Production of Q&A newsletter for public distribution following outcome of meetings | 20th June -6th July 2007 |
| Distribution of Q&A newsletter | 9th July - 13th July 2007 |
| End of informal Consultation Period | 23 July 2007 |
| Collate responses and with LA | 24th July – 7th August 2007 |
| LA prepare and finalise report (submit papers to meeting) | 28th August 2007 |
| LA Executive meeting | 18th September 2007 |
| If LA Executive agree formal consultation, then |  |
| LA Call in period for decisions (10 working days) | 19th September – 2 October 2007 |
| Distribution of statutory public notices Parents /libraries and letter to parents, staff and Governing Body | w/c 8th October 2007 |
| Distribution of statutory public notices in the press | w/c 8th September 2007 |
| Statutory consultation period (6 weeks of term time and one week of half term) | 15th October 2007 -3 December 2007 |
| Collate papers for Executive meeting (4 weeks before Executive meeting) | 3 December - TBC |
| Executive meeting | TBC –November 2007 |
| LA call in period for decisions (10 working days) | 10 days ( |
| Publish decision to close the school | w/c 17th December 2007 |

Notes

1. School Organisation Committee (SOC) due to be abolished on 31 May with school closure decisions to be made by Council Executive instead – DfES to advise on any changes

2. Permission for the informal consultation to take place is expected on 4th June

3. Submission of papers is four weeks before a meetings –see if this can be reduced for the December meeting –the closure notice could then be finalised by the end of the year

| 4. OCC Executive meetings |
| --- |
| Papers submitted | Meetings |
| 24 May 2007 | 20 June 2007 |
| 22 June 2007 | 17 July 2007 |
| 28 August | 19 September 2007 |