ITEM CMDT2 - ANNEX1

OXFORDSHIRE COUNTY COUNCIL

E&E TRANSPORT

CABINET MEMBER FOR TRANSPORT

PROGRESS OF APPROVED SCHEMES – JANUARY 2008 UPDATE

| # TIC/CMD/ # TDC # Date | Ref | Scheme | Contact Officer | Status |  |  | Implementation Planned (P)/Actual (A) Dates with Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Red | Amber | Green |  |
| 6 December 2002 | 11/02 | Stopping Up of Highway – off Newlands Avenue, Didcot | John Boyd (01865 815082) |  | A |  | With SODC to progress. unable to advise on dates (appears SODC have been reluctant to act but Legal Services are applying pressure). |
| 25 September 2003 | 41/03 | Thornhill Park and Ride Interchange Improvements | Mike Collins (01865 815877) |  |  | G | Programmed for construction over 2006/07/08 (P). |
| 8 January 2004 | 01/04 | Kidlington Premium Bus Route | David Taylor (01865 816519) |  |  |  | Oxford Rd/Yarnton Rd Signals & Linking: Implemented Oct 2005 (A) see 28 Oct 2004 TIC. Kidlington Rbt Bus Lane: January 07 (A). |
| 17 June 2004 | 40/04 | Oxford, Headington North East, Quarry and Girdlestone Road Parking Controls | Craig Rossington (01865 810443) |  |  |  | Introduced and enforceable. Over 2005/06 and 2006/07. |
| 29 July 2004 | 48/04 | Oxford, London Road, Headington – Provision of an ‘Off Road’ Cycle Route | David Clough (01865 815743) |  |  |  | New brief now expected following implementation of A40 Headington scheme. |
| 2 March 2005 | 14/05 | Cholsey Church Railway Bridge; Transfer of Ownership from Wallingford Town Council to Oxfordshire County Council | Peter Brown (01865 815641) |  | A |  | Property Services processing transfer through MouchelParkman. MouchelParkman being chased for an update. |
| 1 September 2005 | 41/05 | Stopping Up of Highway – Milton Park Estate, Sutton Courtenay | Caren O’Sullivan (01865 815916) |  | A |  | Legal Services to process through Magistrates. Currently unable to advise on dates because contractual indemnity issues require resolution. |
| 17 November 2005 | 53/05 | Witney – Woodford Mill Cycle Track | Alex Coley (01865 810443) |  |  | G | January 2008 (P). Secretary of State has confirmed CPO without modification. |
| 22 December 2005 | 59/05 | Oxford, Merrivale Square – Proposed One-way System | John Cramer (01865 815963) |  |  |  | Implemented January 2007 (A). |
|  | 61/05 | Provision of Bus Stop Clearways – Witney Road, Eynsham1 and George Street, Oxford2 | David Taylor (01865 816519) |  |  |  | Witney Road, Eynsham 1: June 2007 (A) & . George Street, Oxford 2: April 2006 (A). |
| 2 February 2006 | 04/06 | Banbury, Orchard Way Zebra Crossing | David Clough (01865 815743) |  |  |  | Implemented April 2007 (A). |
| 16 March 2006 | 09/06 | Abingdon Town Centre Various Roads 20 mph Speed Restriction Proposals | Ralph Green (01865 815816) |  |  | G | March 2009 (P) to end of Phase 2 works. |
|  | 10/06 | Eynsham Premium Bus Route – Land Acquisition | James Wright (01865 815551) |  | A |  | Significant issues: EA object to flood relief aspect, land CPO requirements may involve Public inquiry and funding availability. Revised proposals issued to EA. |
| 27 April 2006 | 11/06 | Banbury. Merton Street/Middleton Road Signalisation and Associated Traffic Regulation Orders | David Clough (01865 815743) |  |  |  | Implemented July 2007 (A). |
|  | 13/06 | Oxford, Old Marston Village – Traffic Calming | Andrew Vidovic (01865 810437) |  |  |  | Implemented December 2006 (A). |
| 8 June 2006 | 16/06 | Bicester, Residents Parking Agency Agreement | Ralph Grant (01865 812622) |  |  |  | See Ref 16/07. |
| 20 July 2006 | 22/06 | Public Transport Development Programme | David Taylor (01865 816519) |  |  | G | Most East Oxford works implemented 2007. Hollow Way/Cowley Centre March 2008 (P). Carterton and Chipping Norton routes March 2008 (P). |
|  | 23/06 | Kidlington Premium Bus Route - Bus Lane Order | James Wright (01865 815551) |  |  |  | Implemented January 2007 (A). |
|  | 25/06 | Bicester A4095 : Proposed Speed Limits | David Deriaz (01865 815666) |  |  |  | Implemented November 2006 (A). |
|  | 26/06 | Parking Charges Oxford City Centre On-Street Parking | Craig Rossington (01865 810443) |  |  |  | Implemented January 2007 (A). |
|  | 27/06 | Oxford, The Lakes Parking Zone | Richard Kingshott (01865 815716) |  |  |  | Implemented (enforceable) January 2007 (A). |
|  | 28/06 | Oxford, Northway Parking Zone | Richard Kingshott (01865 815716) |  |  |  | Implemented (enforceable) January 2007 (A). |
|  | 30/06 | Stopping Up at Roman Way and Garsington Road, Oxford | John Boyd (01865 815082) |  |  |  | District judge made the stopping up order on 15/10/07, matter concluded. |
| 14 September 2006 | 33/06 | Disabled Persons’ Parking Places – South Oxfordshire District | Mike Ruse (01865 815978) |  |  |  | Implemented November 2006 (A). |
|  | 34/06 | Shillingford Bridge Signalisation | Gary Critchlow-Smith (01865 815817) |  |  | G | Phase 1 implemented April 2007 (A). Phase 2 December 2007 (P). |
| 6 October 2006 | 38/06 | Camera Enforcement – Oxford City Centre Bus Gates | Alex Coley (01865 810409) |  |  |  | Implemented February 2007 (A). |
|  | 39/06 | Oxford, Marston South Controlled Parking Zone | Richard Kingshott (01865 815716) |  |  |  | See Ref 14/07. |
|  | 40/06 | A361 Banbury Road, Bloxham, Ells Lane Proposed Controlled Crossing | James Wright (01865 815551) |  |  | G | Scheme now planned for completion by end of January 2008 (Developer Wimpey/Contractor M V Kelly) |
|  | 42/06 | Gorwell, Watlington – Amendments to One Way and No Waiting Traffic Order | Malcolm Bowler (01235 466119) |  |  |  | Implemented February 2007 (A). |
|  | 43/06 | Henley-on-Thames, Market Place – Proposed Traffic Regulation (Amendment) Order | Malcolm Bowler (01235 466119) |  |  |  | Implemented March 2007 (A). |
|  | 44/06 | Disabled Persons’ Parking Places – Cherwell District | Mike Ruse (01865 815978) |  |  |  | Implemented February 2007 (A). |
|  | 45/06 | Disabled Persons’ Parking Places – West Oxfordshire District | Mike Ruse (01865 815978) |  |  |  | Implemented March 2007 (A). |
| 24 November 2006 | 46/06 | Oxfordshire County Council (Banbury, Ruscote Avenue)(Prohibition of Right Turns) Order 200* | David Clough (01865 815743) |  |  |  | Implemented April 2007 (A). |
|  | 47/06 | Special Parking Areas Outside Oxford - Enforcement Arrangements | Steve Smith (01865 810435) |  | A |  | Current implementation programme Nov 08 to Mar 09 (consultation dependent). District discussions in Jan 08 to agree principles of Agency Agreements. |
|  | 48/06 | Oxford: Headley Way Cycle/Pedestrian Crossing | Ian O’Connell (01865 815755) |  |  |  | Implemented March 2007 (A). |
| 4 January 2007 | 01/07 | Implementation of Bus Stop Clearways – Various | Daniel Metcalfe (01865 815683) |  |  |  | Implemented January 2007 (A). |
|  | 02/07 | Cowley Road, Oxford – Traffic Regulation Order Amendments to Waiting and Parking | John Cramer (01865 815963) |  |  |  | Implemented April 2007 (A). |
|  | 03/07 | Oxford, A40 Elsfield Way to Jackson Road Experimental Left Turn Ban | John Cramer (01865 815963) |  |  |  | Implemented March 2007 (A). |
| 15 February 2007 | 04/07 | 50mph Speed Limit Proposals | James Wright (01865 815551) |  |  | G | Scheme now complete. Some minor signing amendments planned for completion late December 2007/early January 2008 |
|  | 05/07 | Oxford, George Street/Cornmarket Street, Oxford – Review of Traffic Signals | John Cramer (01865 815963) |  |  |  | Further report to be considered in March 2008. |
|  | 06/07 | Oxfordshire County Council (High Street, Didcot) (Bus Lane, One Way and Prohibition of Waiting) Order 2007 | Malcolm Bowler (01235 466119) |  |  |  | Implemented March 2007 (A). |
|  | 07/07 | Coopers Lane, Abingdon – Amendment to Restriction of waiting Traffic Order | Lee Turner (01235) 466120 |  |  |  | Implemented June 2007 (A). |
| 29 March 2007 | 08/07 | Summertown Shopping Area Street Environmental Proposals | Paul Fermer (01865 815764) |  |  | G | Summer 2008 (P). |
|  | 09/07 | Relocation of Premium Route Bus-Stops – Howard Street | Dan Metcalfe (01865 815683) |  |  |  | Implemented April 2007 (A). |
|  | 10/07 | Better Ways To School Highway Schemes Wheatley Primary School - Littleworth Road Proposed Zebra Crossing | David Deriaz (01865 815666) |  |  |  | Implemented August 2007 (A). |
|  | 11/07 | Proposed Waiting Restrictions - Church Road, Wheatley | Malcolm Bowler (01235 466122) |  |  |  | Implemented October 2007 (A). |
| 26 April 2007 | 13/07 | Oxford, North Summertown Controlled Parking Zone | Richard Kingshott (01865 815716) |  |  |  | Implemented and enforceable November 2007 (A). |
| 7 June 2007 | 14/07 | Oxford, Marston South Controlled Parking Zone Permit Charges | Richard Kingshott (01865 815716) |  |  |  | Implemented June 2007 (A). |
| 19 July 2007 | 15/07 | Capital Programme – Additional Developer Funded Schemes | Jacqui Cox (01865 815713) |  |  | G | Over 2007/08 and 2008/09 (P). |
|  | 16/07 | Oxfordshire County Council (Bicester Various Roads) (Parking) Order 200* | Louise Harrison (0845 310 11 11) |  |  | G | December 2007 (P). |
|  | 17/07 | Implementation of New Bus Stop on Premium Bus Route - Buckingham Road, Bicester | Stuart Timms (01865 815655) |  |  |  | Implemented November 2007 (A). |
|  | 18/07 | Headington Roundabout – Proposed Permanent Closure of the Access Gap Outside Macdonalds | Colin Baird (01865 815536) |  |  |  | Implemented August 2007 (A). |
|  | 19/07 | Oxford , Phipps Road - Proposed Relocation of Highway Gate | Andrew Vidovic (01865 810437) |  |  |  | Decision deferred pending Cowley Area Committee views. |
|  | 20/07 | Oxford , Summertown Shopping Area – Street Environment Scheme | Paul Fermer (01865 815764) |  |  | G | Summer 2008 (P). Formal consultation and land purchase still outstanding and may have an impact on programme. |
|  | 21/07 | Oxfordshire County Council (Various Roads, Goring) (Prohibition and Restriction of Waiting) (Amendment No.3) Order 2007 | Malcolm Bowler (0845 310 11 11) |  |  |  | Implemented October 2007 (A). |
|  | 22/07 | Great Haseley - Stopping Up of part of an Classified Unnumbered Highway Adjacent to A329 | Caren O’Sullivan (01865 815916) |  | A |  | Forwarded to Legal Services to progress through to Magistrates Court but issues remain in implementing planning conditions. |
| 6 September 2007 | 23/07 | Banbury - Western Corridor Proposed Parking Bays And Related Signing and Lining | David Clough (01865 815743) |  |  |  | Implemented November 2007 (A). |
|  | 24/07 | Use of Bus Lanes by Private Hire Vehicles | John Cramer (01865 815963) |  |  |  | Further report to be considered in March 2008. |
|  | 25/07 | Oxford, London Road Corridor Improvements –Progress and Consultation on Design | Mike Collins (01865 815877) |  |  | G | June 2008 (P). |
|  | 26/07 | Implementation of Bus Stop Clearways on Premium Bus Route – Barton | Stuart Timms (01865 815683) |  |  |  | Implemented November 2007 (A). |
|  | 27/07 | Disabled Persons’ Parking Places - Oxford City | Mike Ruse (01865 815978) |  |  | G | Scheme now complete. |
|  | 28/07 | Proposed 18 Tonnes Weight Restriction –Railway Bridge Foxhall Road, Didcot | Malcolm Bowler (0845 310 11 11) |  |  | G | January 2008 (P). |
|  | 29/07 | Proposed Amendments to waiting Restrictions – Church Road and High Street, Wheatley | Malcolm Bowler (0845 310 11 11) |  |  |  | Implemented October 2007 (A). |
|  | 30/07 | A415 Newbridge River Thames Crossing | Julian Hartless (01865 815097) |  |  | G | February 2012 (P). Current design stage on time. |
| 4 October 2007 | 31/07 | A415 Newbridge River Thames Crossing | Julian Hartless (01865 815097) |  |  |  | Committee noted decision and comment of E&E Scrutiny Committee. |
|  | 32/07 | Banbury Middleton Road and Waterloo Drive Parking Restrictions | David Clough (01865 815743) |  |  | G | January 2008 (P). |
|  | 33/07 | Oxfordshire County Council (Abingdon Road,Oxford) – (Traffic Management) Order 200* | Peter Egawhary (01865 815857) |  |  | G | March 2008 (P). |
|  | 34/07 | Oxford, Relocation of Bus Stop from Wentworth Road to Aldrich Road | Dean Gildea (01865 815724) |  |  |  | Implemented October 2007 (A). |
|  | 35/07 | Henley Integrated Transport Strategy - Town Centre Scheme – Traffic Regulation Orders | Mark Bostock (01865 815789) |  |  | G | April 2008 (P). |
|  | 36/07 | Proposed Extension of 30 Miles Per Hour Speed Limit- Station Road, Shiplake-on-Thames | Malcolm Bowler (0845 310 11 11) |  |  | G | December 2007 (P). |