ANNEX B

ACTION PLAN

Following the self assessment in Annex A, the following actions have been identified in order for Oxfordshire to strengthen its approach to Network Management.

These actions are listed as two tables. Firstly, short term actions in order to progress the Network Management Plan to a final draft stage for October 2008, and secondly, those actions that will be completed within the period of the second LTP (2011).

This action plan will be a live document and will be reviewed by the Network Management Board on a quarterly basis using a RAG status report on all actions.

Work needing to be completed for final draft of Network Management Plan

| Work | Lead | Work to date | Deadline |
| --- | --- | --- | --- |
| Contingency Plan Development Plan. | KMP | Programme of work produced to April 2009. Full three year programme being progressed in consultation with the area offices. | Mid October |
| List of key contacts and meetings produced as preliminary work towards communications plan. | KMP | Contact list produced in spreadsheet. Key meetings yet to be identified. | Mid October |
| Testing of Performance Indicators | PE | Good progress with Parity and Congestion. | Mid October |
| Identification of suitable public perception indicators | PE | Results now available. | Mid October |
| Identification of membership to Stakeholders Group. | PE | Workshop to be held in the wintertime. Date and attendance needs to be confirmed. | Mid October |
| Working group to be set up to consider existing road hierarchies and how these can be effectively joined up | PE | Initial meeting with working group, subsequent meetings with ICT. Project commenced identifying road use across the network. | Underway |
| Production of a Review programme for signal timings | TA | Discussions held, draft list produced. | Mid October |

Work in progress, to be completed by 2011

| Work | Lead | Work to date | Deadline |
| --- | --- | --- | --- |
| Development of UTMC in Oxford City (TIM). Includes VMS signs. | PTD | Contract awarded, at install stage. | First stage ‘switch on’ spring 09 |
| Phase two of JTMS | TS | Implementation from September 2008 to March 2009. | Spring 09 |
| Provision of Travel Information on the Web (TIM website) | CG | Initial workshops held. Waiting to see what UTMC can offer. | Start up again October 08, full system available in Spring 08 |
| Undertaken timing review of traffic signals. | SIG | Draft programme produced with list of priority sites. | Priority sites complete by Summer 2009. |
| Develop methods to monitor and report levels of congestion. This will include the use of ANPR and ITIS data. | TS | Tables and Plans produced. Base data based on ANPR and ITIS data for year 08/09 | Spring 2009 |
| Review of Signing around Oxford City, approaches, and market towns | PTD | Inventory complete, awaiting review and recommendations. | Oxford Ring Road and Approaches complete by April 2009. |
| Production of Communications Plan in line with the corporate plan and the transport services consultee list. | NC | Identification of key contacts and meetings. | March 2009 |
| All works to be recorded on electronic register. | SW | Process for notification of works agreed with D&I group. Section 58 pages on OCC intranet. | Roll out by PM and DLS, November 2008 |
| Adoption of Key Parity Measures | SW | Raised with Highways group in September 2008. OCC preferred KPMs forwarded for discussions. Meeting with Mayrise set up for Mid October. | Indicator S4 to be measured for Oxford City by October 2008. |

| Work | Lead | Work to date | Deadline |
| --- | --- | --- | --- |
| Adoption of Parking Performance Indicators | TE | New contract arrangements in place. PIs need to be confirmed | Spring 2009 |
| Develop contingency plans for strategic routes | NC | Programme drafted. Work on ring road to begin in November 2008 | All key routes completed by 2011 |
| Integrate existing processes to include skips and scaffolding, diversions, and events on the Streetworks Register. Produce and implement procedures following results of DfT consultation | AO | Area office putting a programme of work together. | Programme for October 2008, procedures in place for Spring 2009 |
| Consultation on the Highway Agencies Tactical Diversion Routes | SW | Partially complete. Change of contractor for area 3 has lead to slippage. | January 2009 |
| Review of Traffic Sensitive Streets network. | SW | Awaiting software installation. | Proposed update to Utilities for comment January 2009. |
| A review of the agreement in place with the NTCC on the shared use of VMS in emergency situations is being carried out. | CG | At discussion stage. | Spring 2009 |
| Review of the Road Hierarchy as established within the Transport Networks Review. | CG | Initial meeting with working group, subsequent meetings with ICT. Project commenced identifying road use across the network. | Autumn 2009 |
| Full notifications for all works on the highway | SW | Meetings held with teams. Senior management involvement. Performance indicator set, but needs testing and target to be set. | March 2010 |
| Work | Lead | Work to date | Deadline |
| Traffic Growth, congestion and Accidents report to be considered by the Network Management Board. | CM | Reports to be assembled in early 2009. | March 2009 |
| Produce a guide for event organisers on traffic management responsibilities | NC | Waiting to be printed and loaded onto web. | October 2008 |
| Quarterly meetings of Stakeholders Group | CG | Initial workshop planned to determine how to take this forward. | Spring 2009 |
| Development of the Central Oxfordshire Transport Strategy. | LTP | Draft Strategy being developed for November 08 | Mid 2009 |
| Review of the Oxford Transport Strategy (OTS) | OTS | Scoping review being undertaken. Formulation of strategy for consultation 2009 | 2010 |
| Strategic Transport Reviews being carried out for major towns, to be completed by Autumn 2008. | ITS | Modelling work carried out, recommendations being developed. | December 2008 |
| Development of the Access to Oxford Major Project. | A2O | Central Oxfordshire Transport Model has been produced. Business case currently being developed to be submitted 2010 | 2013 |
| Development of Air Quality Action Plans. | LTP | Chipping Norton Plan being developed to be submitted Defra. | December 2008 |
| Development of VISM model for Oxford City Centre. | OTS | Mostly complete. Testing phase. | October 2008 |
| Introduce civil enforcement of parking restrictions in the remaining four districts of Oxfordshire. | TRO | Consolidation of existing restrictions is underway with one district almost complete. | 2009 |
| Review of existing Controlled Parking Zones in Oxford. | TRO | Completed reviews in two areas. Made minor modifications in three others. | On-going |

| Work | Lead | Work to date | Deadline |
| --- | --- | --- | --- |
| Implementation of new Controlled Parking Zones. | OTS | Informal Consultation on two new zones. Formal consultation to be carried out in Spring 2009. | 2010 |
| Implementation of road classification changes arising from the Transport Network Review | LTP | A44 Signing to be completed by Spring 2008, preliminary work then to be undertaken on the A424 |  |
| List of ‘who to consult’ in transport being developed in design and implementation team (John Cramer). | D&I | Draft produced. | Spring 2009 |
| Walking\Cycling maps in towns being developed by travel plans team in partnership with local businesses. | TP | Thame produced, Kidlington being developed. Programme for remaining towns also being developed. | Kidlington by Mar 09, programme by Mar 09. |
| Travel plans team to develop Parking Management Policy for employers as part of the teams workplace travel planning work. | TP | At research stage | March 2009 |
| Travel Planning team working with Brookes University on ‘Walk it’ project designed to inform public of cost (money\time\health) of different modes in making a particular journey. | TP | Progress to be determined |  |
| Review of Freight Quality Partnership arrangements. | CM | To be considered by the Network Management Board. | December 2008 |