ANNEX 1


Oxfordshire Children and 

Young People’s Plan

2006 - 2009

1 October 2005

Children and Young People’s Plan

Contents


Page

Purpose of the Plan
1

Links to other strategic plans
1

Arrangements for co-operation between agencies
3

Engagement of children, young people and their families
3

Views of children, young people and their families
4

Performance monitoring
5

Statement of how resources will be deployed to achieve the outcomes
5

Vision for Children’s Services
6

Emerging priorities for improving outcomes for children and young people
7

The areas of the Plan
8

-
Be healthy
9

-
Stay safe
12

-
Enjoy and achieve
14

-
Make a positive contribution
17

-
Achieve economic wellbeing
20

-
Service integration
23

-
Children looked after
26

-
Children with special educational needs/disabilities
29

-
Children and young people from ethnic minorities
32

Appendix 1:
Resource Implications
35

Appendix 2:  
Targets for improving outcomes for children and 
38


young people


Purpose of the Plan

There is a statutory requirement to produce a single, strategic plan for all services for children and young people provided by the local authority and all relevant partners.  The intention is that the plan should support local authorities and their partners to agree clear targets and priorities for all their services to children and young people, to identify the action needed to achieve them and to ensure delivery.

The duty to prepare the plan is given to the County Council, alongside its duty to secure co-operation among a number of partners to improve the wellbeing of children and young people.

The plan covers services for children and young people aged 0 - 19, and those over 19 receiving services, including leaving care and those over 19 and under 25 with learning difficulties.

Links to other plans

The Government’s intention is that the Plan should be the single, strategic, overarching plan for all services for children and young people in a local area.  The ability to secure agreement to the widest possible scope for the Children and Young People’s Plan (CYPP) and the necessary links with other plans will be key.

The plan covers all local authority services, including:

· early years and childcare;

· education;

· lifelong learning;

· youth and play services;

· children’s social services, including safeguarding;

· planning and regeneration;

· housing (a district council responsibility in two tier areas);

· leisure services (a district council responsibility in two tier areas).

It also covers:

· health services for children and young people, including child and adolescent mental health;

· advice and guidance for 14-19 year olds (including Connexions);

· services to tackle the misuse of drugs and alcohol;

· youth justice services, where the Probation Service is already engaged in Multi-Agency Public Protection Arrangements (MAPPA);

· voluntary and community services.

Arrangements need to be made to capture in the plan the key elements of the following plans, to ensure the consistency which is required by regulations with the plans of other statutory partners:

· the local police authority’s Three Year Strategic Plan;

· the statutory annual Youth Justice Plan prepared by the local multi-agency Youth Offending Team;

· the Probation Area Annual Plan, based on the Business Plan of the National Probation Service for England and Wales;

· crime and disorder and misuse of drugs strategies.

School Development Plans will show how schools contribute to positive outcomes for children and young people.  Other plans which need to be consistent with the CYPP are the  LSC Local Strategic Plan for 14-19 Education, CAMHS strategy, Healthy Schools Programme and play strategies.  In addition, any planning documents on traffic, transport, culture, leisure, sports, open spaces and the wider public realm will be taken into account insofar as they affect children and young people.  

It is proposed that the CYPP will form a section of both the Oxfordshire Plan and the NHS Delivery Plan:






Oxfordshire Community Strategy


















OCC Cabinet


Public Service Board

PCT Boards


District Council Cabinets



























Children and Young People’s Joint Commissioning Board














NHS Local Delivery Plan

Children and Young People’s Plan 


Oxfordshire Plan

Operational Service Plans

Team and Unit Plans

Other strategic plans:

· Early Years Development Plan

· School Organisation Plan

· Asset Management Plan

· Safeguarding Plan

· Accessibility Strategy

· Special Educational Needs 

· Building Schools for the Future Plan

· Children’s Fund Plan

· Community Safety Plans

· Play Strategy

· Public Health Strategy

· School Travel Plans

· Connexions Plan

· Police Authority Strategic Plan
· Recreation & Cultural Strategies
· Housing/Homelessness Strategies
· Economic Regeneration Strategies
· Transforming Youth Work Plan

The plan will link to the Oxfordshire Community Strategy and work in collaboration with Local Strategic Partnerships.

Arrangements for co-operation between agencies

The Children and Young People’s Plan is being developed with the engagement of a wide range of partners.  Work on the plan is overseen by a Project Board, including the Chief Executive of the County Council and the Chief Executive of Oxford City Primary Care Trust on behalf of all Oxfordshire PCTs.  There is good collaboration from District Councils, Police, Early Years Development and Childcare Partnership, Youth Offending Team, Learning & Skills Council, Children’s Fund, Connexions and voluntary sector partners.  

The Children and Young People’s Joint Commissioning Board will be responsible for monitoring the implementation of the plan.  The Board will include the key decision-makers able to impact on improving outcomes for children and young people in Oxfordshire.

Engagement of children, young people and their families

There is real commitment to securing the involvement of children and young people and parents and carers at all levels in the development of services for children and young people in Oxfordshire. 

There is much good practice in Oxfordshire in consulting and engaging children and young people.  The Youth Service has comprehensive arrangements for engaging young people, including through the development of countywide youth fora.  District Councils have effective arrangements for seeking feedback from young people on the services they provide.  Two Sounding Boards have been established (one for children and young people and one for parents and carers) to consult and engage children and young people and parents and carers.  

It is proposed to build on existing good practice to develop a co-ordinated, cross agency approach to engaging children and young people throughout Oxfordshire.

The Plan is based on the feedback received from children and young people and parents and carers to date.  The Sounding Board approach is being maintained to secure the ongoing participation of children, young people and families in the development of the Plan.  There is a need to ensure the engagement of young people from across the age range and from the widest range of backgrounds and abilities.

Views of children, young people and their families

Feedback from Children and Young People

Feedback from children and young people was a key feature of the Best Value Review of Services for Vulnerable Children and Young People.  A Children and Young People’s Sounding Board has been established. More than 200 children and young people have been involved in providing feedback into the process. 15 children and young people have been involved in regular meetings with senior officers and members.  A detailed report has been produced of the feedback provided by children and young people.  Some of the main themes which have emerged are:

· the value of securing the participation of children and young people in finding solutions to difficulties and the need to maintain this in the future development of children’s services;

· the importance to children and young people of relationships with adults based on mutual respect and with sufficient time to listen to and understand each other;

· the need to increase access to play, leisure and youth services, including drop-in youth centres open at suitable times for young people;

· the value of a named professional who is able to develop a relationship over time with the child or young person;

· the need for early practical support for children and young people when things start to go wrong, e.g. young people to talk to with similar experiences, practical support for parents;
· the need for better information in many of different forms about support that is available.

Feedback from Parents and Carers

A Parent and Carers Sounding Board was established as part of the Best Value Review involving over 270 parents through questionnaires and face to face meetings.  A detailed report has been produced of the feedback.  Some of the main themes which have emerged are:

· health visitors, schools, GPs and family centres are key points of contact for parents;

· parents emphasise the importance of being able to develop a good relationship with professionals, based on mutual trust and respect;

· a significant number of parents said they had to get to a crisis before they received help;

· the vast majority of parents said things had got better as a result of the help they received;

· parents particularly valued the support of the voluntary sector;

· parents of disabled children highlight the need for more respite support;

· parents who had experienced parenting programmes valued them and recommended them to others.

Performance monitoring

Each section of the Plan will include the targets to be achieved in order to improve outcomes for children and young people.  This will include past and current performance against the targets.  It is proposed that The Children and Young People’s Strategic Board will be responsible for monitoring the implementation of the CYPP and progress towards the performance targets.  The County Council and partners have a commitment to develop this arrangement by April 2006.  The Board will report directly into the Public Service Board, as well as to the Cabinet of the County Council, District Councils and PCT Boards:



Public Services Board

Membership

Leader of the County Council,

Leaders of District Councils,

Health, Police












Children and Young People’s Joint Commissioning Board

Membership

County Council Lead Member for Children 

County Council Lead Member for School improvement 













District Council Lead Members for Children

PCT Chair, Police, Voluntary Sector, Children and Young People, Parents and Carers












Children and Young People’s Partnership

Membership

Wide ranging membership of services for children and young people from:  County Council, District Councils, Health, YOT







Police, Children and Young People, Parents and Carers, Voluntary Sector
















Stay Safe

Be Healthy

Enjoy and Achieve



Make a Positive Contribution

Achieve Economic Wellbeing

Statement of how resources will be deployed to achieve the outcomes

DFES guidance is clear that the Children and Young People’s Plan should include details of the resources which will be allocated to implement the Plan.  Appendix 1 provides a statement of how resources will be deployed and highlights areas where additional investment is needed.  Further work is underway with partners to look at the resource implications of the Plan across all agencies and this will be included in the final draft of the Plan in February.  

Vision for Children’s Services in Oxfordshire

Our aim is to improve outcomes for all children and young people by giving every child and young person the opportunity to achieve their potential.  

Our vision is for Oxfordshire to be a place where every child and young person receives the help they need to:

· enjoy good physical and mental health;
· be protected from harm and neglect and grow up able to look after themselves;

· achieve educational success and enjoyment and develop self-confidence and life skills for a creative and positive adulthood;

· make a positive contribution to the community and society;

· enjoy and achieve their potential and make the most of their lives.

We will achieve this by:

· ensuring that all children and young people are able to exercise the rights identified in the United Nations Convention on the Rights of the Child;

· ensuring the involvement and participation of children and young people and their parents and carers in the development of  our services, plans and decisions;

· understanding and starting from the perspective of the child or young person, and their family and empowering vulnerable children, families and the communities in which they live to find their own solutions

· ensuring that all children and young people are protected from abuse or neglect and that this is a key priority for all agencies working with children and young people;

· making sure that children and families receive support early enough if there are difficulties;

· giving parents and children and young people better information about the help that is available;

· providing services that are personalised, accessible and acceptable to children, young people and families, including a greater involvement of the voluntary sector;

· innovating on the basis of reliable evidence about what works both locally and nationally, without de-stabilising what is already working well;

· ensuring clearer accountability and improved co-ordination and integration of education, health and social care around the needs of children;

· minimising bureaucracy and maximising contact time for children and families with professionals;

· the development of a skilled, effective and well motivated workforce working as part of a multi-disciplinary team;

· effective case management by a lead professional or key worker who has the time to develop a relationship with the child or young person and family and support them through a range of services they might need;

· improved sharing of information and common assessment arrangements across agencies.

· understanding where services are likely to have the greatest impact on improving outcomes for children and young people and their families and target resources accordingly.

Emerging priorities for improving outcomes for children and young people

The following priorities for improving outcomes for children and young people have been agreed across the agencies in Oxfordshire:

1.
To improve health outcomes for children and young people, with a particular focus on:

-
promoting healthy and active lifestyles for all children and young people;

-
increasing the number of children and young people accessing sport, play, leisure, out of school, community, cultural and arts activities;


-
improving emotional and mental health and wellbeing and improving access to child and adolescent mental health services;

-
reducing the use of harmful drugs and alcohol and developing drug and alcohol treatment services;

-
reducing teenage conceptions and sexually transmitted infections.

2.
To improve the early, practical support for vulnerable families to prevent, abuse, neglect and family breakdown.
3.
To improve educational achievement and enjoyment at all key stages, but with a particular focus on:


-
the needs of young children so that action is taken to promote educational success from the earliest stage;


-
ensuring that children and young people enjoy their education and are actively encouraged to participate in decisions and activities in the school and community;


-
ensuring that all schools are successful in helping pupils to make progress in line with their potential;


-
ensuring that all pupils leave school with a good standard of education and the qualifications needed for further education, employment or training.

4.
To improve support for young people with behaviour difficulties in schools and reduce the incidence of youth offending.

5.
To increase the participation of children and young people in our services and ensure that it is well co-ordinated across the agencies.

6.
To improve life chances of children looked after, particularly through improved educational achievement, reduced involvement in offending and strengthening support to meet their needs in-county.

7.
To improve services for disabled children and young people and their families, so that more children and young people’s needs can be met in-county.
The Areas of the Plan

Strategic Action
Leads

1.
Be Healthy
Jane Bell, Head of Children’s Services, North Oxon PCT Partnership


Emma Glanville, Senior Manager (Children & Families), Oxford City PCT

Mark Andrew, Primary & Community Services Manager, South West Oxfordshire, PCT




2.
Stay Safe
John Richards, Interim Head of Social Care for Children, Social & Health Care



Sandra Bingham, Senior Education Officer (Access & Social Inclusion), Learning & Culture




3.
Enjoy and Achieve
Judith Morris, Head of School Development Service, Learning & Culture


Roy Leach, Senior Adviser (School & Service Monitoring), Learning & Culture




4.
Make a Positive Contribution
Rick Harmes, Head of Community Learning, Learning & Culture


     
Mike Simm, Head of Youth Offending Service




5.
Achieve Economic Wellbeing
Dave Waller, Unit Manager (Strategic Development & Economic Development), Environment & Economy



Amanda Powell, Childcare Development Manager, Learning & Culture




6.
Service Integration
Sarah Breton, Children’s Trust Project Manager




7.
Particular groups of children requiring a special focus





A.
Children and Young People Looked After
Noreen Collins, Operations Manager, Social & Health Care

Fran Fonseca, Service Manager (Family Placement), Social & Health Care


Sandra Bingham, Senior Education Officer (Access & Social Inclusion), Learning & Culture




B.
Children and Young People with Special Educational Needs/Disabilities
Liz Shaw, Senior Manager (Children’s Therapies), Oxford City PCT

Simon Adams, Senior Education Officer (SEN), Learning & Culture

Sharron Jenkinson, Co-ordinating Adviser (SEN/Access/ Inclusion), Learning & Culture



Sarah Ainsworth, Operations Manager, Social & Health Care




C.
Children and Young People from Ethnic Minorities
Sharon Fleming, Development Officer (Equalities & Communications), Learning & Culture

1.   Be Healthy
Strategic Analysis

Overall, people living in Oxfordshire get a good start in life compared to the rest of the country.  Public health data shows that Oxfordshire has some of the lowest incidence of adult heart disease and cancer in the country and infant mortality is lower than the national average.  There are above average levels of breastfeeding and take-up of immunisations is good.

On the measures of people living with life-limiting, long term illness, Oxfordshire ranks as the second healthiest county in the south-east.  However, there is a 15 year difference in life expectancy between the best ward and the worst.  

More than £8m is spent annually in Oxfordshire on services for children and young people who have a diagnosed mental illness. However, there are some young people with mental health difficulties who cannot access these services, or who have to wait too long to see someone. 

Teenage conception rates are below the national average.  The overall trend is upwards against a national picture of a decline, though the most recent data indicates that there was a reduction of 2% in conceptions between 2003 and 2004.  There are 19 wards in the county with an under 18 conception rate for 2000-2002 that is amongst the highest 20% in England.

Sexually transmitted infections (STIs) are on the increase and young people are particularly vulnerable. In Oxfordshire there has been a year on year increase in STIs, including HIV. 74% of chlamydia cases seen at the Harrison Clinic in Oxford in 2002 were in young women under 24. 

37% of 5 year olds in Oxfordshire have decayed, missing or filled teeth.  This is broadly in line with the regional average.

Ofsted school inspections in 2003/04 identified that arrangements for participation in sport are “good” or ‘”excellent” in 100% of secondary schools and 79% of primary schools.  This is better than national in secondary schools and in line with national in primary schools.  65% of school children have at least two hours sports a week.  45 schools have been accredited as healthy schools.

In relation to healthy lifestyles, there are three areas where health outcomes are a concern:

-
childhood obesity is on the increase across socio-economic groups;

-
levels of physical exercise are decreasing with more sedentary family life;

-
the number of young women taking up smoking is still increasing, despite a general downwards trend in the incidence of smoking.

Priorities for Improving Outcomes

· To promote healthy and active lifestyles for all children and young people.

· To increase the number of children and young people accessing sport, play, leisure, out of school, community, cultural and arts activities.

· To improve the emotional and mental health, self-esteem and self-confidence of children and young people and improve access to Child and Adolescent Mental Health Services.

· To reduce the use of harmful drugs, encourage safe drinking among young people and increase access to drug/alcohol treatment services.

· To reduce teenage conceptions  and sexually transmitted infections.

Targets

· % of school children spending a minimum of 2 hours a week on sport and PE.
· Number of accredited healthy schools.
· Number of young people accessing sport, play, leisure, out of school, community, cultural and arts activities.
· Under 18 conceptions per 1000 by 50% by 2010 (national target).
· Number of teenage mothers in education, employment or training (national target).
· Number of young people using Class A drugs (national target).
· Waiting times for CAMHS Tier 3 services.
Strategic Actions Planned to Improve Outcomes

Actions
Timescale
Lead

Implement co-ordinated, multi-agency health promotion programmes in all settings for children, young people and families, including the healthy schools programme, including a focus on:

-
healthy eating, including locally sourced school meals;

-
increasing physical activity; 

-
health education (including drugs, alcohol and smoking);

-
sex and relationships education;

-
personal, social and health education

-
health services provided on school sites.
2005-2006
Senior Adviser (Partnerships, Extended Learning)

All agencies to work together to reduce drug and alcohol misuse and provide integrated programmes of treatment, care and support for young people with substance misuse and alcohol problems.
2005-2008
Head of Community Safety





Improve access to child and adolescent mental health services by:

-
implement a preventative multi-agency strategy to promote children’s mental health and emotional wellbeing;

-
establishing a new Primary Care Child and Adolescent Mental Health Services, with a focus on early intervention and support;

-
increasing the availability of services for particular groups of young people (with conduct disorders, learning disabilities, children looked after, young carers, and parents with mental health problems);

-
implementing a training programme in emotional wellbeing across all schools and settings
2005-2008
Chair of CAMHS Steering Group

Improve support to reduce teenage pregnancy:

-
establish countywide teenage pregnancy team;

-
improve the quality of sex and relationships education;

-
target areas of high need and young people in “at risk” groups;

-
improve access to information and advice.
2005-2008
Chair of  Teenage Pregnancy Steering Group

Develop and implement a co-ordinated play and recreation strategy across Children’s Centres, childcare, recreation, youth service, diversionary activities, extended schools, etc.
2005-2008


Target resources to improve health outcomes to areas of highest need (Oxford City, Banbury, Bicester, South Abingdon and other targeted areas where outcomes are poor).
2005-2008
Directors of Public Health, PCTs

Links to Detailed Plans  (hyperlink)

· Physically healthy

· Mentally and emotionally healthy

· Sexually healthy

· Healthy lifestyles/Parents and carers promote healthy choices

· Choose not to take illegal drugs

2.   Stay Safe

Strategic Analysis

The number of children on the Child Protection Register (248 at 31 March 2005) is in line with other authorities, though there has been an increase since 2004.  Performance on all three child protection indicators is good.  Only 1% of children are on the Child Protection Register for more than two years.  Performance in relation to the number of reviews held on time (98.5%) and re-registration rates (15.6%) is approaching the top band of performance nationally.  16.5% of children on the Child Protection Register are from black and minority ethnic groups.

On 31 January 2005, there were 462 children and young people looked after in Oxfordshire.  This represents 35 per 10,000 population against a national average of 54 per 100,000.  Of the 462 children looked after, 66 were asylum seekers.  Performance is good in relation to placement stability and adoptions of children looked after.  The number of children adopted has increased from 6.2% in 2004 to 9% in 2005.  70% of care orders are processed within the recommended maximum of 40 weeks.  An average of 90% of children looked after receive all relevant health checks.

There is a lack of placement choice within the county resulting in a relatively high number of children looked after (18%) being placed in independent agency places.

Recent inspection of the fostering service and Thornbury House judged provision to be “good”, with the majority of standards being fully met.  The Adoption Inspection showed a more mixed picture, with the majority of standards being almost met.

Limited information is available on the incidence of bullying and racist incidents in schools and the community, but young people report that bullying is a concern. 

Priorities  for Improving Outcomes

· To increase the proportion of young people who say that they feel safe from bullying, crime and anti-social behaviour in and out of school.

· To improve early, practical support for vulnerable families to prevent abuse, violence, neglect and family breakdown.

· To reduce the incidence of accidents in children and young people.

Targets

· Number of families accessing support through Children’s Centres, Extended Schools and locality teams.
· Number of families accessing co-ordinated information about services.
· Number of children killed or seriously injured in road accidents (national target).
· % of children looked after in out-county placements.
· % young people who say that they have been bullied in the last 12 months.
Strategic Actions Planned to Improve Outcomes

Actions
Timescale
Lead

Increase the availability of early preventative family support for children at risk of family breakdown or significant harm through:



-
the development of Children’s Centres to co-ordinate the provision of support for new parents and the early identification and support of pre-school children in need of additional services;
2005-2010
Head of Community Learning

-
the development of extended schools;
2005-2008
Head of School Development Service

-
support for families experiencing domestic violence;
2006
Acting Head of Children’s Services, Social & Health Care

-
support for families of offenders and prisoners.
2006
Acting Head of Children’s Services, Social & Health Care

Implement the Placement Matters strategy to reduce out-county places, increase foster care and kinship placements.
2005
Acting Head of Children’s Services, Social & Health Care

Implement a co-ordinated programme in early years settings and schools to promote positive emotional health, wellbeing and relationships and tackle bullying.
2006
Head of School Development Service

Head of Children’s Services

Build upon existing good practice in Districts and YOT to consult and engage children and young people in crime reduction strategies.
2006
Head of Community Safety

Target support to Adoption Services to ensure that all standards are met.
2005
Acting Head of Children’s Services, Social & Health Care

Establish a Children’s Safeguarding Board
2006
Acting Head of Children’s Services, Social & Health Care

Support the development of Mediation Services
2006


Links to Detailed Plans  (hyperlink)

· Safe from maltreatment, neglect and sexual exploitation
· Safe from accidental injury and death
· Safe from bullying and discrimination
· Safe from crime and anti-social behaviour in and out of school
· Have security, stability and are cared for
· Parents, carers and families provide safe homes and stability
3.   Enjoy and Achieve

Strategic Analysis
Standards in the Foundation Stage in most areas of learning are broadly in line with national expectations.  Standards in primary schools are generally in line with national and similar authorities.  However, there is evidence that counties similar to Oxfordshire are improving at a faster rate.  

Attainment of 14 year olds is above the national average at L5+ and L6+.  Standards have improved significantly over the last two years.  At 16, the percentage of pupils achieving 5+ A*-C GCSEs (50.6%) in 2004 fell below the national average and is below performance in similar authorities.  The percentage of pupils achieving five GCSEs A*-G including English and mathematics is in line with national, but below that in similar authorities.  Schools have registered an improvement at A Level for the fourth successive year with performance in line with or better than national figures and significantly better than for all comprehensive (or non-selective) schools.  Value-added progress from KS2 to KS3 is above expectation.  Value-added progress between KS2 and KS4 is in line with expectations but in a significant number of secondary schools, progress is in the bottom quartile nationally.

Improving the educational achievement of vulnerable groups of children is a priority at all key stages.  There is encouraging progress in relation to the educational achievement of children looked after and some ethnic minority groups.

Feedback from teachers and young people highlights the importance of promoting children’s enjoyment and emotional health and wellbeing both in its own right and as a key way of raising self-esteem and achievement.

School attendance levels in Oxfordshire are in the top 25% of authorities at primary and secondary level.  Attendance has improved year on year for the last three years.  Unauthorised absence at secondary is in line with national.  The attendance of some vulnerable groups of children, including children looked after and young offenders, is a priority for improvement.

The percentage of schools of concern is in line with the national average.  No schools have been judged by Ofsted to have inadequate sixth forms since September 2001.
Priorities for Achieving Outcomes

There is a need for a concerted, joint agency/partnership focus on:

-
raising standards of educational achievement and enjoyment at all key stages;

-
supporting schools so that they are successful in meeting the personal development and wellbeing needs of pupils and staff.

Within this context, there is a need to ensure that there is an appropriate focus on:

-
the needs of young children so that action is taken to promote educational success from the earliest stage;

-
ensuring that children and young people enjoy their education and are actively encouraged to participate in decisions and activities in the school and community;

-
ensuring that all schools are successful in helping pupils to make progress in line with their potential;

-
ensuring that all pupils leave school with a good standard of education and the qualifications, including vocational qualifications, needed for further education, employment or training.

Targets

· % children achieving a score of 78 or above on the Foundation Stage profile.

· % of children achieving Level 4 at KS2 in English, Maths and Science.

· Number of schools with value added (KS2-KS4) in the top 50% of all schools nationally.

· % children eligible for free school meals achieving 5 GCSE A-C.

· % pupils achieving 5 GCSEs A-C and 5 GCSEs A-G or equivalent.

· % schools where overall personal development and wellbeing needs of learners is good or better.

Strategic Actions Planned to Improve Outcomes

Actions
Timescale
Lead

Target multi-agency support to children not achieving a score of 78 or above on the Foundation Stage profile
2006/07
Head of Children’s Services

Head of School Development Service

Promote the involvement of children and young people in school improvement, with a particular focus on personalised learning, emotional wellbeing and quality of relationships.
Consultation: March-June 2005.

Implementation: Sept. 2005-July 2008
Senior Adviser (Partnerships & Extended Learning)

Co-ordinating Adviser (Secondary/14-19 Strategy)

Target support to improve leadership and management and quality of teaching in schools where value-added is poor.
Analysis: April 2005.

Implementation: May 2005-July 2008
Senior Adviser (School & Service Monitoring)

Improve support for early years settings and schools in meeting the needs of vulnerable groups of children before school and at all key stages.
April 2005- July 2008
Senior Education Officer (Access & Social Inclusion)

Senior Adviser (Additional Educational Needs)





Improve and expand the range of curriculum options and vocational teaching for 14-19 year olds.
Consultation/ development: May-July 2005.

Implementation: Sept. 2005-July 2008
Co-ordinator Secondary Education and Director 14-19 Strategy 

Develop all Oxfordshire schools as extended schools, offering a range of support, e.g. childcare, study support, family learning, out of school play, recreation, culture, sport and creative learning, to improve engagement and achievement.
Launch: April 2005.

Implementation: May 2005-July 2008
Senior Adviser (Partnerships, Extended Learning)

Develop training packages for departmental self-evaluation, use of data, middle management toolkit, monitoring and evaluation of teaching and learning.
Development: April-July 2005.

Implementation: Sept. 2005-July 2008
Co-ordinator Secondary Education and Director 14-19 Strategy

Increase young people’s access to play and community youth facilities, including drop-in centres open at times suitable for young people.
2006-2007
Head of Community Learning

Children’s Fund

Successful formation of Oxfordshire Sports Partnership and local sports networks.
2005
Oxfordshire Chief Leisure Officers

Sports England SE

Implement programme of building improvements in schools
2005-2010
Head of Resources

Links to Other Plans  (hyperlink)

· Ready for school
· Attend and enjoy school
· Achieve educational standards at primary school
· Achieve personal development and enjoy recreation
· Achieve educational standards at secondary school
· Parents, carers and families support learning.
4.   Make a Positive Contribution

Strategic Analysis

Oxfordshire has a strong track record of consulting children and young people and there are many examples of good practice.  However, arrangements for consulting and engaging young people are not sufficiently well co-ordinated across the agencies.  There is scope to develop a more coherent approach.  There is no co-ordinated process for surveying the views and attitudes of children and young people.

The vast majority of young people make a positive contribution in their schools and communities.  Young people have a huge amount to offer their  communities if we can harness their energy and potential.  Standards of behaviour are generally good.  Permanent exclusions for Oxfordshire schools are low and have reduced significantly in 2004/05.  However, fixed term exclusions are increasing and there is concern from schools about the difficulties they face meeting the needs of a minority of young people with increasingly challenging behaviour.  Young people highlight concern about the problem of bullying, both in and out of school.  

Levels of youth offending are in line with national and with similar authorities.  There has been a 17.5% reduction in youth offending over the last five years.  

Priorities for Achieving Outcomes

· To increase the effective participation of children and young people in decision-making at all levels and ensure that it is well co-ordinated across the agencies.  This needs to include children of all ages, backgrounds and ability levels.

· To support schools, parents and communities in promoting positive behaviour and wellbeing of young people, thereby reducing the incidence of behaviour difficulties and bullying.

· To support the development of young people as active citizens, making a positive contribution within their communities, thereby reducing levels of young offending, particularly in areas of high need. 

Targets

· % schools where learners’ contribution to the community is good or better.
· % days lost through fixed term exclusions.
· % young people involved in offending
· % residents who think, over the last three years, the following have got better:
-
activities for teenagers;

-
facilities for young children.

· % of young people who say that they have been bullied over the last 12 months.

Strategic Actions Planned to Improve Outcomes

Actions
Timescale
Lead

Establish a coherent and co-ordinated joint agency strategy to secure the effective participation of children and young people at all levels in children’s services.  Secure school engagement in this strategy.
By September 2006
Head of Children’s Services

Establish a new integrated Youth Support Services, including provision of information, advice and guidance.
2006-2008
Head of Community Learning

Develop a regular, structured survey of young people’s views on a wide range of issues.
By September 2006
Head of Children’s Services

Develop a co-ordinated, multi-agency approach to  strengthen the capacity of, and support for, early years settings and schools to meet the needs of children and young people with behaviour difficulties.  Review access to off-site provision for pupils with behaviour difficulties.  Explore with schools the delegation of funding for behaviour support.  Improve community and multi agency support.  Increase access to sport and recreational activities.  Develop nurturing programmes.
Starting in September 2005
Head of Children’s Services

Head of School Development Service

Develop a co-ordinated multi-agency strategy to combat bullying in schools and the community.
During 2006/07
Head of School Development Service

Head of Children’s Services

Head of Community Learning

Implement a comprehensive programme of parenting support for children with behaviour difficulties, including strengthening arrangements to reinforce parental responsibility for behaviour.
2006-2009
Head of Children’s Services, 

Head of Community Safety

Head of Community Learning

Implement a multi-agency strategy to reduce levels of youth offending, including:

-
positive activities for young people at risk of offending;

-
intensive support for prolific offenders;

-
full-time education, employment or training for young offenders.
2006-2009
Head of Community Safety

Links to Detailed Plans  (hyperlink)

· Engage in decision-making and support the community and environment
· Engage in law abiding and positive behaviour in and out of school
· Develop positive relationships and choose not to bully and discriminate
· Develop self confidence and successfully deal with significant life changes and challenges
· Develop enterprising behaviour
· Parents, carers and families promote positive behaviour.
5.   Achieve Economic Wellbeing

Strategic Analysis

Unemployment rates in Oxfordshire are about half the average for England.  However, four wards (Blackbird Leys, Northfield Brook, Littlemore and Barton) have jobless rates over 10%, more than double the Oxfordshire average.

About one in ten children in Oxfordshire live in low income households.  Blackbird Leys and Northfield Brook feature in the top 10% of income deprived wards in England.  These wards have more than one in every ten people living on low income.  Three out of five districts (South, Vale and West) are in the top 10% least deprived local authorities in England.  Oxford City has a rate of child poverty 0-4 years (24%) and 5-19 (19%) that is double that for any other district and higher than the national average.

Oxfordshire has 13 areas in the top 20% most deprived in the country.  10 of these are in Oxford City and 3 are in Banbury.

Nearly 28% of people in Oxfordshire have a degree or higher degree.  This is the highest proportion of any county in England.  At the same time, 21% of the adult population does not have any qualifications at all.  In Blackbird Leys and Ruscote wards, more than 2 in 5 adults have no qualifications.

Oxfordshire has a larger than average number of childcare places available, but there is still a lack of childcare to meet the needs of particular families, e.g. shift workers or families with disabled children.  

Just 3% of the population live in “unfit” housing.  The average price of a terraced house is seven times the level of average income.  

Participation in education and work-based learning is higher than the average nationally and for the south of England.  However, the number of people not in education, employment or training and the number of 16-18 year olds in jobs with no training increased from 2003 to 2004 

Parents of some children with special educational needs have expressed concern that there is no post-16 provision for their children in Oxfordshire special schools.

Priorities for Achieving Outcomes
The priority is to tackle some of the county’s marked economic inequalities, with a particular focus on their impact on children and young people.  This will require concerted action, targeted to areas of high need and vulnerable groups of children, to:

· reduce levels of homelessness/temporary accommodation in young people and ensure that all care leavers have access to appropriate accommodation;

· reduce the number of families in temporary accommodation;

· increase access to affordable, flexible and high quality childcare;

· reduce the percentage of young people not in education, employment or training or in jobs with no training’

· produce sufficient transport to meet the needs of children and young people, particularly in rural areas;

· increase the quality of post 16 provision for young people with special educational needs.

Targets

· % children living in low income households.
· % 16-18 year olds in education, employment or training.
· % 16-18 year olds in jobs with no training.
· % registered childcare places (6 months - 16 years).
· % 19 year olds achieving L2+ in NVQ or equivalent.
· Number of care leavers with appropriate accommodation.
· Number of families in temporary accommodation.
· Number of homeless young people.
Strategic Actions  Planned to Improve Outcomes

Actions
Timescale
Lead

Implement the national strategy to increase the availability of childcare places .
2005-2010
Head of Community Learning

Develop and implement the new 14-19 strategy.  Increase training and employment opportunities to meet the needs of the local economy.
2005-2008
Co-ordinator Secondary Education

Director 14-19 Strategy in LSC 

Implement a co-ordinated strategy to raise parental aspirations about post-16 educational opportunities.
2005-2006
Head of School Development Service

Review post-16 provision for young people with special educational needs.
2005-2006
Chief Executive of Learning & Skills Council

Head of Children’s Services

Secure joint agency commitment to allocation of resources across Oxfordshire, based on indicators of need
2006-2009
Director of Children’s Services

Secure the development of appropriate accommodation for care leavers
2006-2007
Acting Head of Social  Care for Children

Develop joint agency assessment and preventative measures for young people at risk of homelessness/temporary accommodation.
2006-2007
Head of Youth Service

Links to Detailed Plans  (hyperlink)

· Engage in further education, employment or training
· Ready for employment
· Live in decent homes and sustainable communities
· Access to transport and material goods
· Live in households free from low income
· Parents, carers and families are supported to be economically active.
6.   Service Integration
Strategic Analysis

There is a need to develop coherent, integrated arrangements for the management of the wide range of services for vulnerable children and young people across Oxfordshire.  Health services for children and young people are managed from within the five Primary Health Care Trusts, with Oxford City Primary Care Trust having the lead responsibility for commissioning services for children and young people.  A wide range of services are managed on a countywide basis from Learning & Culture and Social & Health Care.  Other services for children and young people are provided by Connexions, Children’s Fund, Sure Start, Youth Offending Team etc. Over recent years, there has been an increase in the number of projects and short term initiatives, for example Sure Start, Children’s Fund, EAZ and the Excellence Cluster, Neighbourhood Renewal.

There was strong feedback from professionals and parents about the need to ensure coherent joint planning and co-ordination of service delivery.  There was feedback about the need to reduce reliance on short term projects, to mainstream learning and best practice from such projects, and to redirect resources to strengthen front line services for children and young people.  Potentially, this could increase time available for front line staff to provide the early intervention, consistency and continuity of support which children, young people and their families identify as key to effectiveness.

Currently, although there are a number of support services available, many of which are very well regarded by families, thresholds for accessing services for families with more complex difficulties can be very high. This means that families can have to reach crisis point before they receive the service they have been asking for. Each service has different targets to achieve and uses different assessments. Families and staff are frustrated by the time spent on repeat assessments and by the negative impact this has on their ability to form helpful relationships that can be sustained over time. Feedback from families is that they value these relationships very highly and that they help build resilience so that families can manage their own problems.

The Best Value Review of Children’s Services identified that services for vulnerable children and young people are not sufficiently integrated across the county to minimise service overlaps or gaps, and that local service co-ordination needs to be promoted more effectively throughout the county. 

Priorities for Achieving Outcomes
· To take forward the development of integrated services for children and young people within the new Directorate for Children, Young People and Families.

Strategic Actions Planned  to Improve Outcomes

Actions
Timescale
Lead

Implement an integrated programme of workforce development.
2005-2008
Operations Manager (HR), Social & Health Care

HR Manager (Learning & Development), Learning & Culture

Develop an integrated Children’s Information System
2005-2008
Development Officer (Information Management Systems)

Senior Education Officer (SEN)

Service Manager (Assessments), Social & Health Care

Implement a system of integrated support services:


September 2006
Head of Children’s Services, Learning & Culture

Head of Community Learning

Acting Head of Children’s Services, Social & Health Care

· locality teams, common assessment, lead professional;
September 2006
Senior Education Officer (Access & Social Inclusion)

· extended schools;
May 2005 - July 2008
Senior Adviser (Partnerships, Extended Learning)

· children’s centres.
2005-2010
Head of Community Learning

Establish a Children and Young People Commissioning Trust.
April 2006
Children and Young People’s Strategic Board Project Manager

Develop a strategy to secure greater engagement of the voluntary sector.
April 2006
Children and Young People’s Strategic Board Project Manager

Develop a strategy to implement Children’s Rights, including securing the engagement of children & young people and parents & carers.
April 2006
Children’s Fund Manager

Adviser (PSHE)





Take forward the development of joint agency information/directories about services for children and young people in Oxfordshire.
September 2006
Children and Young People’s Strategic Board Project Manager

Children’s Information Service

Develop a strategy to secure improved information sharing and joint working with District Councils
2005/06
Children and Young People’s Strategic Board Project Manager

Links to Other Plans  (hyperlink)

· Workforce Development

· Integrated Children’s ICT system

· Integrated Support Services:


-
locality teams/common assessment/lead professional


-
extended schools


-
children’s centres

· Children and Young People’s Trust

· Engaging the Voluntary Sector

· Engaging Children, Young People and Families

· Joint agency information about children’s services

· Equalities

A.   Children Looked After

Strategic Analysis

On 31 January 2005, there were 462 children and young people looked after in Oxfordshire.  This represents 35 per 10,000 population against a national average of 54 per 100,000.  Of the 462 children looked after, 66 were asylum seekers.  

An average of 90% of looked after children received all relevant health checks in 2004.  Immunisations and dental checks were up to date.  This is above the national average and shows ongoing improvement.  In 2004, 85% of looked after children participated in their review and 93% were allocated to professionally qualified social workers. Performance in both these areas exceeded both the national and comparator authority averages. 

Oxfordshire has reduced the number of children looked after and improved placement stability for this vulnerable group of children. The number of children adopted has increased from 6.2% in 2004 to 9% in 2005, and over the same period, short term stability has improved by 5% and long term stability by 9%. In relation to the national average and comparator authorities this is good performance. It is clear that the current support structures in place has had a significant effect on ensuring looked after children remain in stable placements securely attached to their carers. 

There is a lack of placement choice within the county, leading to some unnecessary out of county placements, and an overspend of the agency budget. Currently 18% of looked after children are placed in independent agency placements, many of which are out of Oxfordshire. 

The educational outcomes of looked after children are significantly lower than the average levels of attainment of their peers at all key stages.  15% of children looked after missed 25 days’ education a year.  However, there was a significant improvement in outcomes at all key stages in 2004:

· the percentage of children looked after achieving 5 GCSEs A-G increased from 23% in 2002/03 to 33% 

· the percentage of care leavers achieving 1 GCSE A-G has improved from 35% in 2002/03 to 45% in 2004/05;

· the percentage of children looked after achieving Level 2 in English improved from 17% in 2002/03 to 52% in 2003/04.

Further improvements are projected for 2005 and the challenging PSA targets are within reach.

The Leaving Care service has been built in partnership with young care leavers. A nationally recognised ‘Source Worker’ programme exists whereby Care Leavers are trained to:

· to consult with other looked after children, both individually and in ongoing groups; 

· interview for all posts within the looked after children service;

· deliver training to a range of workers, managers and councillors;

· contribute to local and national developments and conferences such as ‘Blue Print’ and Big MAC;

· raise the profile and status of looked after children. 

In 2002, the Council set up the Leaving Care Service and in 2003/04 54% of care leavers aged 19 were in employment, education and training (EET), against a national average of 55%.  In 2005, 73% are in EET, i.e. 81% of the level of their peers, which exceeds the government target of 75%. 

This steady improvement has resulted in Oxfordshire achieving the maximum rating for good performance and the Leaving Care Service being awarded a Charter Mark. An analysis of the service highlights the fact that we have provided an increasing service for care leavers from within a budget only allowing for inflationary rises. Ironically, the more successful the service becomes in establishing and maintaining contact and getting care-leavers into higher education, the more pressure the budget will be under. The other pressure on the budget is the cost of appropriate accommodation and the fact that all young people in further education aged 19 are not entitled to benefits. 

The vast majority of looked after children are law-abiding citizens who make a positive contribution to society. While few offend (30 during the years 2003/04) the numbers are higher than looked after children in other parts of the country. This was identified as a significant area for improvement three years ago resulting in the county entering into a Public Service Agreement (PSA). There have been significant reductions in the number of offences being committed by individual looked after children to the extent that present performance exceeds the PSA target.

Priorities for Achieving Outcomes
· To raise educational achievement of children looked after.

· To improve school attendance of children looked after.

· To reduce cautions and convictions of children looked after.

· To reduce the number of children looked after in out-county placements.

Strategic Actions Planned to Improve Outcomes

Actions
Timescale
Lead

Implement Placement Matters
2005-2007
Acting Head of Children’s Services, Social & Health Care

Establish joint ICT/data systems for children looked after.
2005-2007
Senior Education Officer (SEN)

Service Manager (Assessments)

Target support to improve school attendance and educational achievement, including establishing a virtual school
2005-2006
Senior Education Officer (Access & Social Inclusion)





Improve support for parents who misuse drugs and alcohol.
2005-2007
Head of Community Safety

Target support to children looked after at risk of offending.
2005-2007
Service Manager (Family Placement)

Ensure provision of health checks for all children looked after.
2005-2006
Lead Nurse for Children Looked After

Increase percentage of care orders processed within 40 weeks.
2005-2006
Service Manager (Family Placement)

Links to Detailed Plans  (hyperlink)

· Children Looked After:


-
Be healthy


-
Stay safe


-
Enjoy and achieve


-
Make a positive contribution


-
Achieve economic wellbeing

B.   Children with Special Educational Needs/Disabilities

Strategic Analysis

2.5% (2,474) of children and young people in Oxfordshire have a statement of special educational needs and 1% are in special schools.  This is lower than national, but in line with similar authorities.  1,764 children under 18 are recorded on the joint Health and Social Care database.  There is national and local evidence that a small, but increasing, number of children with severe learning difficulties and complex medical needs are surviving longer and that the incidence of diagnoses of autism is rising

Disabled children with complex mental health needs, including challenging behaviour, and those with complex health needs/chronic illness do not have adequate access to day/overnight care or to intensive inpatient/out patient support.

National research indicates that disabled children are significantly more likely to be abused than their non-disabled peers. Children with communication difficulties find it harder to explain what has happened to them and learning disabled children may also find it hard to give consistent stories. There are very few disabled children in Oxfordshire on the Child Protection Register.  Further work is needed to clarify the reasons for this and ensure that this vulnerable group is safeguarded.  Children with secure placements with their families or with local alternative carers/care facilities are most likely to be protected from abuse.  Access to respite, together with day care and play and leisure activities, is a high priority in Oxfordshire in order to ensure that parents, carers and families are able to provide safe homes and stability.

The Best Value Review identified the need to build on work piloting models of good practice in early intervention.  further work is needed to ensure that practitioners and families are clear about the nature of pathways and journeys for children, young people and families.

There is good knowledge in Oxfordshire from both national and local research about what this group of children and young people want and need in order to make a positive contribution. This has been enhanced by active representation from learning disabled children on the Children and Young People’s Sounding Board and from information gleaned through questionnaires to children, young people and families during the Best Value Review process and work completed as part of the Disability Service redesign. 

Educational achievement of children with special educational needs is below the national average at Key Stage 4.  All children in special schools currently transfer to colleges of FE if they are to continue in education. There is currently variability in the choice/ appropriateness of post 16 provision available for disabled children and young people, with some forms of disability being better catered for than others. There is a need to enhance provision and the effectiveness of transition arrangements to address this.

Priorities for Achieving Outcomes
· Improve in-county support for children with SEN/disabilities and their families so that the needs of more children can be met successfully in-county.

· Strengthen support for children with complex health needs/chronic illness/mental health difficulties.

· Target support to improve the educational achievement of children with special educational needs, to include co-ordination of resources use through the Common Assessment Framework and multi-agency team working, ensuring access to appropriate early intervention and support and extending the SEN Development Programme.

· Enhance post-16 provision available for children and young people with SEN/ disabilities.

Strategic Actions Planned  to Improve Outcomes

Actions
Timescale
Lead

Establish an integrated SEN/disability service
2006
Director of Children’s Services

Extend multi-agency, early intervention support and transition planning for young children with SEN/disabled children.
2005/06
Education Officer (Early Years)

Review specialist community children’s nursing across all Trusts to ensure most effective use of current resources and to identify shortfall and opportunities for skill mix/workforce development, to include continuing care work.
2005
Senior Manager (Children & Families), Oxford City PCT

Redesign residential support services for children with disabilities to enhance support for children and families.
2005/06
Acting Operations Manager, Social & Health Care

Enhance provision within county for disabled children with complex mental health needs.
2005/06
Head of Mental Health Redesign, Oxford City PCT

Review post 16 SEN provision for children and young people with special educational needs.
2005
Head of Children’s Services

Chief Executive of Learning & Skills Council

Take forward the development of extended special schools as an integral part of developing accessible play, leisure and childcare for disabled children, young people and their families.
2006
Senior Education Officer (SEN)





Strengthen support for children with SEN in mainstream schools, including exploring delegation of the statementing budget and implementation/ extension of the SEN Development Programme.
2006
Senior Education Officer (SEN)

Co-ordinating Adviser (Inclusion & SEN)

Implement the strategy for the development of  community special schools.
2005/06
Senior Education Officer (SEN)

Strengthen support for children with SEN in play and leisure settings.
2005-2007
Senior Education Officer (SEN)

Improve multi-agency support for children with severe and challenging behaviour.
2005/06
Head of Children’s Services

Acting Operations Manager

Co-ordinate resources through common assessment and multi-agency working, ensuring access to early intervention and support.
2006/06
Senior Education Officer (SEN)

Acting Operations Manager, Social & Health Care

Extend SEN Index funding to playgroups and non maintained nurseries
2007
Senior Education Officer (SEN)

Links to Detailed Plans  (hyperlink)

· Children with special educational needs/disabilities:


-
Be healthy


-
Stay safe


-
Enjoy and achieve


-
Make a positive contribution


-
Achieve economic wellbeing

C.  Children and Young People from Ethnic Minorities

Strategic Analysis

Nationally there are concerns regarding specific black and minority ethnic groups’ predisposition of certain conditions such as sickle cell anaemia, thalassemia, heart disease, diabetes and mental health issues. Local plans have identified the need for improved information, communication and community development, advocacy support, ethnic monitoring and greater access to services for prevention, mental health and diabetes.

Tackling racial harassment and racially motivated crime is identified as a community safety priority by Oxfordshire Race Equality Council.  Comprehensive  monitoring of  incidents of racial harassment has been established with schools.  100% of schools submit data.  In 2004-5 58% submitted nil returns.  The Ofsted inspection 2004 indicates that schools use the system well.  Annual collection of incidents of racial harassment in schools indicates that 450-625 incidents per year are reported.  Action taken is monitored.  

Further investigation is required regarding possible over-representation of ethnic minorities amongst Looked After Children and access to preventative services.  

The educational achievement of Black Caribbean, Pakistani and Bangladeshi pupils is below that of similar pupils nationally.  At age 16, ethnic minority pupils leave school with lower performance in A/AS/A2 Level and Vocational A Level.  Their subsequent participation in education (75% - 91.3%) is higher than the average for White groups (69.9%).  Unemployment rates are lower, except for mixed race groups.  School exclusions of black and minority ethnic pupils are disproportionately high compared with the pupil population.

Minority groups are under represented in the workforce.  Oxford City Primary Health Trust has highlighted a need for developing appropriate employment strategies in their Race Equality Scheme.  The County Council is the largest employer, but ethnic minority groups are under represented (4.9% of the county’s residents are from black and minority ethnic groups, but only 2.9% of employees are from black and minority ethnic groups).  

Priorities
· To raise the educational achievement of Black Caribbean, Pakistani and Bangladeshi pupils.

· To address the particular health needs of black and minority ethnic children and young people. 

· To reduce the incidence of racial harassment.

· To investigate black and minority ethnic representation within the looked after children population and increase access to preventative services.

· To ensure that equal opportunities policies are implemented in employment practices.

Strategic Actions Planned to Improve Outcomes

Actions
Timescale
Lead

Target support to raise the attainment of identified groups of ethnic minority pupils. 
2005 onwards
Head of School Development Service (SDS)

Implement strategies to reduce the number of ethnic minority pupils excluded from school.
2006 onwards
Head of Children’s Services 

Target resources to identify and reduce:

· racial harassment and racially motivated crime;

· racial harassment incidents in schools
2005 onwards
Crime and Disorder Reduction Partnerships 

Heads of SDS & Children’s Services

Complete 2nd phase of BME study re: preventative services prior to entry into care or formal child protection
 2006
Social & Health Care – Acting Head Children’s Services

Provide generic staff training on diversity issues across all agencies, and service specific training to embed good practice in service delivery .
2006 onwards
Human Resources Services in all Agencies

Implement PCT Race Equality Schemes, including PCT Plans to: 

· promote use of interpretation/translation and use of health promotion resources, information etc in appropriate languages;

· address mental health issues;
2005-2008
All PCTs

Oxford City PCT

North Oxon PCT

South Oxon PCTs

· make specific provision within the Choosing Health delivery plan;



· promote uptake of prevention services

· provide information and access to services for diabetes.



Devise and implement staff recruitment and development strategies to support local employment needs and ensure appropriate BME representation at all levels of employment across all agencies.
2006 onwards
Human Resources Services in all Agencies

Broaden the range of ethnic monitoring data collection and analysis. Use this data strategically to inform planning, resource allocation, service delivery and quality assurance.
2006 onwards
Lead Officers for Data Collection & Information Sharing in each agency

Target resources to promote BME community consultation and involvement.
2005 onwards
Consultation Officers in all agencies

Links to Detailed Plans  (hyperlink)

· Children and young people from ethnic minorities:


-
Be healthy


-
Stay safe


-
Enjoy and achieve


-
Make a positive contribution


-
Achieve economic wellbeing

Appendix 1
Children and Young People’s Plan:  Resource Implications

DfES guidance is clear that the Children and Young People’s Plan should include details of the resources which will be allocated to implement the Plan.

Further work is underway with partners to look at the resource implications of the Plan across all agencies and this will be included in the final draft of the Plan in February 2006.

In general terms, it is intended that the actions in the Plan will be implemented within existing resources.  There is much that can be achieved by realigning our services, enabling staff to work together more efficiently and effectively and shifting the balance of our resources into prevention, early intervention and direct support for children and families.

This will be achieved by:

· the establishment of a Children’s Joint Commissioning Board and a more integrated approach to planning and commissioning children’s services;

· the realignment of the Council’s Directorates to create a single Directorate for Children, Young People and Families;

· joint work across agencies to deliver the outcomes in the Local Area Agreement;

· the development of countywide, integrated services;

· the development of local multi-disciplinary teams, using a common assessment and lead professional approach;

· bringing together some of the “back office” functions into shared services;

· the management of the Connexions Service within Oxfordshire.

However, there are some areas where it is already clear that additional investment is needed:

Service Integration

ICT

The development of an integrated ICT system is a key priority in order to develop common systems for sharing information about young people, common assessment and joint directories about services.  A strategy for taking this forward over the next three years is being developed and costed as part of the CYPP process.  It is worth noting that other authorities that are facing a similar agenda are spending between £1m and £3m.  It is important that resources are available to start to implement the strategy from April 2006.  Early priorities include:

· implementing the Integrated Children’s System and electronic care record;

· implementing systems to monitor children looked after;

· implementing electronic exchange of attendance data;

· implementing on-line admissions.

Further detailed investigations will be required to determine actual financial implications.  However, experience elsewhere suggests an estimate of £500,000 is required in 2006/07.

Locality Teams

A key priority in the Plan is the development of multi-agency locality teams throughout Oxfordshire.  There is a need to appoint a senior manager to lead on the development of locality teams, lead professional roles and common assessment in the new Directorate for Children, Young People and Families.  £75,000 is required for this key post, including administration and resources.

Make a Positive Contribution

Youth Service

The Youth Service in Oxfordshire has been commended by inspectors as providing a very good service, but one which is not sustainable within existing resources.  In line with requirements in the Youth Green Paper, the Plan proposes further strengthening the services available for young people and establishing a new integrated youth support service.  The Youth Service will be integral to this development.  It is recommended that a fundamental budget review of the service takes place in 2006/07 and that, pending this review, its resources are stabilised at the current level.  This will require £250,000 per annum.

Engaging Children, Young People and Families

Additional resources are required to secure the ongoing participation of children and young people and parents and carers in the development of our services for children and young people, including in the Children’s Board and locality teams.  A total of £75,000 per year is required for the appointment of a full-time post, including administration and resources, to lead this work within the new Directorate.  The role will include:

-
leading and co-ordinating the work to engage children and young people across agencies;

-
co-ordinating feedback, for example  through school councils, youth fora, District Councils;

-
leading the work on Sounding Boards;

-
leading the work to undertake a comprehensive survey of the views and attitudes of children and young people.
Stay Safe

Children’s Social Care

There are ongoing pressures in the Children’s Social Care budget.  The forthcoming budget review process will consider how any additional funding pressures can be financed.

Children’s Centres

The Council has been allocated £4.76m revenue funding and £4.53m capital funding for the development of 25 new Children’s Centres in Oxfordshire by 2008.  This funding will also support three existing centres and all the associated management and support costs for the programme.  In order to maximise the funding available for front-line services, it is proposed that the one-off virement of £159K from existing early years funds is made permanent in 2006/07.  The Government has indicated that there will be further investment in the Children’s Centre programme in 2008-10 with a view to establishing a Children Centre in every community by 2010.

Enjoy and Achieve

Extended Schools

The Council has been allocated £1.657m (capital and revenue) in 2006/07 for the development of Extended Schools.  This will increase to £2.057m in 2007/08.

Be Healthy

CAMHS

£1m CAMHS ringfenced funding is available.  (£637,000 in Oxfordshire County Council and £455,000 combined PCT funding).  £680,000 of this has been allocated to develop the new Primary Child and Adolescent Mental Health Service.  This is within the base budget.

Teenage Pregnancy

It is intended that existing resources including Standards Funds currently supporting the teenage pregnancy strategy for the county (£175,000) and the NHS sexual health budget (£150,000) can be re-configured to deliver the services required to deliver improvements in relation to teenage pregnancy objectives.

Appendix 2

Targets for improving outcomes for children and young people

(Data being collated)

Target
Actuals
Targets


2003/04
2004/05
2005/06
2006/07
2007/08
2008/09

Be Healthy







To reduce under 18 conceptions per 1000 by 50% by 1010 (national target)







Increase the percentage of school children spending a minimum of 2 hours a week on sport and PE







To increase the percentage of children who participate in 7 hours a week or more physical activity







To increase the number of accredited healthy schools







To increase the number of teenage mothers in education, employment or training (national target)







To reduce the number of young people using Class A drugs (national target)







To increase the number of problematic drug users in treatment







To increase the number of young people accessing sport, play, leisure, arts and cultural activities







Stay Safe







Increase the number of families accessing support through Children’s Centres, Extended Schools, locality teams.







Increase the number of family group conferences







Increase the number of families accessing up to date, co-ordinated information about services







Reduce % of children looked after in out-county placements







Reduce the number of children killed or seriously injured in road accidents (national target)







% children looked after receiving health checks (national target)







% care orders processed within 40 weeks (national target)







Enjoy and Achieve







% of children achieving Early Learning Goals







% children achieving Level 2 at KS1







% children achieving Level 4 at KS2







% half days missed in secondary schools







% half days missed in primary schools







% pupils achieving 5 GCSEs A-C







% pupils achieving 5 GCSEs A-G







% 3 year olds receiving good quality early years education







Number of schools with valued added (KS2-KS4) in the top 50% of all schools nationally







% children on free school meals achieving 5 GCSEs A-C







% post 16 year olds engaged in cultural or sporting opportunities







Number of pupil visits to museums







% of schools where teaching and learning is good or better in meeting the full range of learners’ needs







% of schools where curriculum and other activities are good or better in meeting the range of needs and interests or learners







% of schools where overall personal development and wellbeing of learners is good or better







% of schools judged to be good or better in securing children’s enjoyment of education







Make a Positive Contribution







Known offending by young people 10-17 years







% permanent exclusions per 1000







% days lost through fixed term exclusions







% residents who think, over the lest three years, that the following have got better:







(a)  activities for teenagers;







(b)  facilities for young children.







% of schools where behaviour of learners is good or better.







% schools where attendance of learners is good or better







% of schools where learners’ contribution to the community is good or better







% of schools where learners’ spiritual, moral and cultural development is good or better







Achieve Economic Wellbeing







% children living in low income households







% families in temporary accommodation







Average weeks’ stay of homeless households in hostels







% social housing and vulnerable households in private sector in a decent condition







% 16-18 year olds in education, employment or training







% 19 year olds achieving Level 2 in NVQ or equivalent

 
 




% registered childcare places (6 months to 16 years)







Number of Children’s Centres







% 19 year olds achieving L2+ in NVQ or equivalent







Children Looked After







% children looked after achieving 5 GCSEs A*-G (PSA)







% children looked after achieving 1 GCSE A*-G (PSA)







% of young people leaving care age 16+ with 5+ GCSE A*-C or equivalent (PSA)







% of young people leaving care age 16+ after being looked after for 1 year or more with 1+ GCSE A*-G or GNVQ (PAF)







% children looked after who missed 25 days’ education







Special Educational Needs







Number of SEN Tribunals







% of SEN statements prepared within 18 weeks excluding exceptions (BV43a)







% of SEN statements prepared within 18 weeks including exceptions (BV43b)







Ethnic Minorities







Children from ethnic minority origin gaining five GCSEs grades A*-C to be increased - children of Black Caribbean origin







Children from ethnic minority origin gaining five GCSEs grades A*-C to be increased - children of Bangladeshi origin







Children from ethnic minority origin gaining five GCSEs grades A*-C to be increased - children of Pakistani origin







CA_OCT1805R18.doc

