CA9 - page 6

ITEM CA9

DRAFT

Proposals for Children’s Centres in Oxfordshire 2006-10

Introduction

1. The Government’s agenda for a joint approach for all key agencies working with children and families is set out in ‘Every Child Matters’ and ‘Change for Children’ which outline five key outcomes for children and young people:

· Enjoying and Achieving

· Staying Safe

· Economic Wellbeing

· Being Healthy

· Making a Positive Contribution

2. The development of Children’s Centres fits well into this agenda, supporting agencies to work together with parents from the time before the child is born, and offering the potential for parents to access the support they need, when they need it, in a local and accessible venue. Proposals for Children’s Centres will be an integral part of Oxfordshire’s developing vision and plans for Children’s Services and as a means for developing Extended Schools.

What is a Children’s Centre?

3. A Children's Centre is a centre that provides a range of integrated services for children under 5 and their families, to include: 

· Early years services

· Family support and parental outreach

· Child and family health services

· Links with Jobcentre Plus

Oxfordshire’s Vision

4. In our Children’s Centres the children’s wellbeing and needs come first. Children’s Centres should be places where children enjoy themselves and feel safe. Parents should be welcomed and included and feel that it’s “theirs”.  Staff should be well qualified and valued.

5. In developing our new Children’s Centres, we will build on existing good services, rather than starting afresh. A large number of families with young children in Oxfordshire already benefit from good quality services. Children’s Centres aim to enhance and join up services for families with young children. The development of Children’s Centres will be closely aligned with developments for locality teams and extended schools.

6. Children’s Centre services will need to meet the needs of their communities and will be developed in partnership with parents, carers and users of services and with local professionals and organisations working in the area.

7. Services and resources will vary according to the needs of the area but will build on and improve existing facilities, for example family centres and nursery schools. Children’s Centres in the 30% most disadvantaged areas will offer the following core services:

Early Years Services:

· Integrated early learning and childcare for babies and children until they are five years old. 

· Childcare suitable for working parents/carers for a minimum of 5 days a week, 48 weeks a year, 10 hours a day. 

· Support for childminders.

· Early identification of children with special needs and disabilities with inclusive services and support for their families.

· Links to local schools (extended schools and Healthy Schools) and out-of-school activities (holiday play schemes, before/after-school play and learning). 

Family support and parental outreach:

· Visits to all families in the catchment area within two months of the child’s birth 

· Information for parents/carers about the range of family support services and activities available in the area. 

· Support and advice on parenting including support at significant transition points for the family (e.g. pre birth, early days, settling into childcare). 

· Access to specialist, targeted services for those families who need them, for example, support for parents/carers of disabled children. 

· Activities which increase parents/carers' understanding of their child's development.

· Specific strategies and activities which increase the involvement of fathers.

Child and family health services:

· Antenatal advice and support for parents/carers.

· Child Health Promotion Programme.

· Information and guidance on breast feeding, hygiene, nutrition and safety.

· Promoting positive mental health and emotional wellbeing.
· Speech and language and other specialist support. 
· Support for healthy lifestyles. 
· Help in giving up smoking.

Parental involvement:

· Consultation and information sharing with parents/carers, including fathers, on what services are needed, and systems to get user feedback on services.
· Arrangements in place to ensure parents/carers have a voice e.g. parents’ forums.
Links with Jobcentre Plus:

· Centres will link with Jobcentre Plus to encourage and support parents/carers who wish to consider training and employment
8. In less disadvantaged areas there will be more flexibility to provide fewer services. 

9. Many families do not easily use centre based services. Children's Centres will provide a welcoming atmosphere that encourages families to use their centres and provide outreach for families who are not able to access the centres themselves.

10. It may not always be possible to provide all the services in one building. Some centres will be campus models with a number of services provided on the same site but in different buildings. Other Children's Centres will provide services by linking with a range of different sectors (health and family support services for example). However, the DfES have given clear guidance that children should receive their integrated care and learning in one place and should not be moved between different settings during the day. 

Progress in developing Children’s Centres in Oxfordshire so far
11. In the first phase of development from 2004-06, Oxfordshire was given funding to develop 2 Children's Centres in areas that ranked in the top 20% nationally in terms of disadvantage (using the Index of Multiple Deprivation). These are the Leys Children's Centre Project in Oxford City and the Sunshine Centre in Ruscote, Banbury. The ACE Early Excellence Centre in Chipping Norton and Rose Hill-Littlemore Sure Start were also designated as Children's Centres in that they already provided the ‘core offer’.

12. In the second phase from 2006-08, the DfES has set Oxfordshire the following targets: 

Local Authority : Oxfordshire
Total



Total number of under 5s Local Authorities (LA) need to be included in Children's Centre catchment areas by 2010   (Based on April 2003 Local Education Authority Data) 
35,835

Total number of under 5s expected to be included in Children's Centre catchment areas in wards in the top 20% areas of disadvantage by March 2006   (Based on the 1999 Index of Multiple Deprivation)
1,715

Total number of new under 5s for LA to be included in catchment areas during 2006-08
20,553

Total including children under 5 in current Children's Centre catchment areas
22,268

Number of new children’s centres to be created during April 2006 - Mar 2008
25

Total children’s centres to be developed by 2008, including current children’s centres 
29

The requirement is to develop Children's Centres first in areas that rank in the top 30% of need. 

13. Areas not reached in the second phase will be included in plans for the third phase of development from 2008-10 so that by 2010 all communities should have access to a Children's Centre. Funding for the third phase will not be announced until 2007.

Funding

14. Indicative funding allocations as follows are conditional on having development plans (by February 05) for each centre, demonstrating our ability to deliver the requirements  (buildings and core offer of services): 

Total indicative Capital funding for 2006-2008
£4,314,465

Total Revenue funding for 2006 – 2008
£4,480,780

Additional rural uplift Capital funding 2006-08
£114,000

Additional rural uplift Revenue funding 2006-08
£273,592

15. The funding is insufficient to build 25 new centres and therefore will have to be used flexibly and in conjunction with other initiatives such as extended schools.  We will also need to make maximum use of existing buildings and look for refurbishment wherever possible. 

16. Likewise with revenue funding this is insufficient to staff the core offer of children’s centre services in 28 centres (Rose Hill/Littlemore continues to get separate funding for the next 2 years). We will therefore need to add value to existing services such as family centres and nursery schools and seek additional sources of funding to ensure that the Children’s Centres deliver the best possible outcomes for children and families.

Catchment areas for Children's Centres

17. Children's Centres should be located in areas that are easily accessible by families living in the most disadvantaged communities who, traditionally, have been slow to access services. Each Children's Centre will have a defined catchment area. A centre is expected to reach an average of 800 children under 5. 

18. The catchment is likely to cover a smaller population in rural areas and some urban areas in areas with high levels of deprivation.  The Children’s Centre model will need some adaptation for rural areas and we are encouraged to focus on delivering fewer services well rather than trying to spread resources too thinly.  A mobile outreach model will be developed to help deliver services to smaller communities.

Progress of discussion and development so far

19. The proposals presented in this report have been drawn up following discussion with the following:

· Early Years Development and Childcare Partnership

· PCT (Primary Care Trust) Children’s Services leads or nominated representatives

· Voluntary Sector Partners

· Nominated officers/councillor from Oxford City and the District Councils

· Relevant officers from across the County Council

20. A consultation strategy is being drawn up so that current service providers and parents have a chance to comment on the localities suggested and other aspects of the Children's Centre strategy before formal proposals are put to the Cabinet for approval.  In order to comply with DfES requirements this initial consultation is taking place through October and November.

Mapping and needs analysis

21. In doing this exercise there was access to figures on the Child Poverty Index, Index of Multiple Deprivation (IMD), geographical maps, and maps that showed the location of schools, health centres and other key services. The ward numbers are based on projected figures for 2004. Maps available highlight the Super Output Areas (SOA) that rank most highly in terms of need (nationally) so we are able to see clearly the communities that rank most highly in terms of need. A SOA is a sub division of a ward. 

Geographical area

22. DfES guidance states that families living in SOAs in the top 30%, nationally, using the IMD must have access to Children's Centres; the principle criteria used in proposing geographical localities for the 2006-08 phase of development is, therefore, the need of the area. Beyond this, the needs of areas that have SOAs that rank in the 30-50% and areas that are known to have higher than average needs because of their particular populations have been prioritised. Areas that have family centres and nursery schools have also been prioritised for the 2006-08 development.

23. Other principles used in determining geographical boundaries of centres are -

· Accessibility. The centre should be located in an area accessible to and used by families with the greatest needs. 

· Demography (approx 800 children under 5 to a centre as stated in DfES guidance).

· Need to ensure viability and sustainability by building on existing services in family centres and nursery schools.

Location

24. Once geographical areas have been agreed, the following factors will be taken into account in making proposals for the precise location and local lead for the Children's Centre within that area - 

· Existing provision such as family centres and nursery schools where these are used by families from the identified areas of disadvantage.

· Other services that are already used by the communities in the most disadvantaged areas, for example local primary schools, health centres.

· Existing capacity in buildings used by the communities we are trying to reach.

· Opportunities created by capital developments planned in the targeted areas. 

· Developments planned as part of the extended schools programme.

25. A rural strategy is being developed to decide how to reach disadvantaged communities in more sparsely populated areas. These areas do not always show up within more general statistics and further work is being done to make sure we identify and reach areas of need.

Premises and accommodation issues

26. In most areas, Children's Centres will build on and improve existing provision rather than provide new premises. The capital funding available will not support a large number of new centres to be built. In a few cases we have centres that are already well equipped to deliver Children's Centre services and will need no alteration; an example is the East St Centre in Banbury.   However in most cases, some alterations will be needed to equip centres to be able to deliver the full range of services. The 2006-08 timescale allowed for capital development is a real challenge. 

27. It is essential that any premises are designed or altered according to the highest quality standards). A model specification for Children's Centre premises is being drawn up which will draw on guidance from the DfES and the Oxfordshire Booklet ‘A Place to Be’ (available from Oxfordshire Children’s Information Service, 0845 2262636)

Summary of key proposals for 2006-08 and 2008-10

28. More detail on the proposals below is given in the annexes including the numbers of Children's Centres and the running total of the children under 5 in the catchment areas. In the running total, the numbers include the existing centres. Our total target is therefore the following:

Total number of Children's Centres 2006-08
29

Total number of under 5s in Children's Centre catchment areas
2,268

Summary of information by District 

District
Total Under 5s
SOA in top 30% of disadv
CentresPhase 1

pre 2006
CentresPhase 2 2006-08
Children included

by 2008
Possible Centres

Phase 3 

2008–2010
 Total Centres

Oxford
   6,961 
30
2
9
7,033
0
11

The Vale of White Horse
   6,519 
3
0
4
3,340
4
8

South Oxfordshire
   7,615 
1
0
3
1,729
7
10

West Oxfordshire
   5,422 
0
1
2
3,182
3
6

Cherwell
   8,217 
6
1
6
5,742
3
10


County mobile rural outreach



1
1,242
0
0

Total
3,4734
40
4
25
22,268
17
45

Consultation and engagement of all stakeholders

29. The DfES has asked us to have made initial proposals by the end of November for the 2006-08 phase (phase 2) that include the name and address of the Children's Centre, the proposed number of children under five living in the centre’s area, the estimated capital costs, the date we plan to open the centre and a description of the centre including childcare places on site. Full centre plans need to be developed by February 2006. This is an ambitious target.

30. Informal consultations with District Councils and all relevant agencies and partners have already taken place in drawing up these proposals. Further public discussions with providers and parents will take the form of open meetings in areas where Children's Centres are planned. These will be widely advertised. Focus groups will take place to reach people who may be reluctant to attend open meetings. Online survey questionnaires will also be available for parents and organisations to complete during October and November and will be promoted to parents within our existing family centres and nursery schools.

31. The draft proposals will be an item for discussion on the agenda for the autumn County and District Councils bi-lateral meetings of leading members. 

32. The draft proposals have been presented to the County Council’s Children’s Services Scrutiny Committee at their meeting on 27 September and by the County Council’s Cabinet on 18 October. The results of consultation will be reported to the Cabinet as part of the final recommendations on the strategy in February.

33. As children’s needs and wellbeing are central to this programme it will be essential that their voices are heard – particularly at local level in designing and developing services around them. Oxfordshire has many examples of good practice in listening to the voices of young children in this way and will be working with local centre leaders and managers as well as with architects and designers to incorporate these approaches; examples of good practice in Oxfordshire are included in the booklet ‘Are you listening to me?’ (available from the Early Years and Childcare Service 01865 815630) 

Opportunities, challenges and risks

34. This programme provides a major opportunity to improve the early intervention and universal family support and childcare services we offer to families and their young children. However there are a number of challenges that present both opportunities and risks to the success of this programme:

Funding
35. The revenue provided to fund this programme is modest given the requirement to provide the core services described. 

· Proposed action: In order to make the best possible use of resources this programme will need to link with other revenue streams for example, Sure Start grant and extended schools funding. We will seek to provide the central support for children’s centre development  through reallocation of existing priorities and resources currently with the nursery grant budget so that the whole of the new children’s centre funding can be devolved directly to front line centre-based services. 

36. Health services are facing major cutbacks. This is at a time when they are trying to reconfigure some of their services to provide a greater level of service from Children's Centres and could put this at risk.
Proposed action: We will continue to work closely with colleagues in health to ensure that this remains a high profile area of service for front line health staff

Sustainability:

37. Although we are confident that central government  funding will extend beyond 2008, we will not know the level of funding until the next government spending review in 2007.  

· Proposed action: DfES advice is to plan for the long term and our experience is that similar projects such as Early Excellence Centres (the ACE Centre and East Street centres in Oxfordshire) have had continued funding.  Where possible we will add value to existing centres and schools rather than develop new services in order to ensure long term sustainability. Service agreements and contracts will be established for two years only in the first instance.

Core Offer
38. Core services will vary according to the needs of the area. We need to be clear about resources available to develop services in different areas of need. There is a risk that expectations will be raised in areas that will not be a priority for a high level of resources.

· Proposed action: during local discussion and consultations officers will present a factual picture so as not to unrealistically raise expectations. 

Workforce Development

39. A multi-skilled workforce will be needed to deliver services in Children's Centres; there are substantial workforce issues.
· Proposed actions: Officers will ensure that children’s centres receive a high priority within the early years training and development programmes.
Timescales for development

40. The February deadline for detailed proposals and the 2006-08 timescale for capital development are both of particular concern. 

· Proposed action: local consultations, audit of services and the development of formal proposals need to be conducted simultaneously in order to achieve required deadlines.  Most capital developments are likely to be improvements or extensions to existing centres.

Governance
41. Our mixed model of provision in Oxfordshire is a strength but means that governance arrangements will need to vary.

· Proposed action: we will need to be clear about what our expectations for these should be and support local Children's Centres to develop their governance and management arrangements. 

Role of Parents and Carers

42. Parents should be at the heart of this development. The challenge is to deliver services that are influenced by parents expressed needs, that also meet our requirements to the DfES to deliver core services and that maintain a consistency of service provision across the county.

Role of the Voluntary, Private and Independent  Sectors

43. The challenge is to build on quality services already provided in our communities without development that might threaten them. Some Children's Centres will develop as linked sites and we need to look carefully at what being part of a linked site would mean for partners. 

Linking with other initiatives in Oxfordshire

44. Proposals on Children's Centres localities are being developed in consultation with the proposals for locality working (arising from the Oxfordshire Best Value Review of Children’s Services), the extended schools and healthy schools initiatives and the development of more community based health and midwifery services.

Time line including next steps

45. The programme for bringing about the proposals outline in this paper, if finally approved and implemented, will be as follows:

Funding announced
April 2005

Guidance Received
July 2005

Informal Consultations with agencies and districts
July-August 2005

Draft Proposals to Scrutiny
September 2005


Draft Proposals to Cabinet
October 2005

Public Discussions with stakeholders and parents
October-November 2005

Details of planned centres on DfES web-based system
November 2005

Develop implementation plans for each new centre
Dec 2005 -February 2006

Final proposals to Cabinet for approval
February 2006

Full centre implementation plans on DfES web-based system   
February 2006

Development of phase 2 centres
April 2006-March 2008

Develop plans for centres 2008-10 (after funding announced, expected summer 2007)



County Hall, Oxford

Contact Officers:

Annie Davy, Head of Early Years and Childcare, 01865 815493

Clare Abolins, Children’s Centre Development Officer, 01235 549290

October 2005

Oxford City, Annex 1

Existing Centres

Total
Ward/SOAs
Key Service(s)
Catchment

1
Rose Hill & Iffley, Littlemore
Rose Hill-Littlemore Sure Start Children’s Centre
682

2 -4

 Leys Children’s Centre Project
Leys Children’s Centre Project
983



Total
1665



Running total of reach by 2008
1665

2006-08 Development
Total
Ward/SOAs
Key Service(s)
Catchment

5

Barton & Sandhills, Quarry & Risinghurst 72
Roundabout, Family Centre and Neighbourhood Nursery
505

6
Quarry & Risinghurst 74,73,71, Headington 35,36, Churchill, Lye Valley, 56,59
Slade Nursery School and Neighbourhood Nursery, Headington Nursery School
791

7
Cowley, Cowley Marsh, Lye Valley 57,58, Iffley Fields 46
Florence Park, Larkrise School
944

8
St Marys, St Clements, Iffley Fields 45, 47
Comper Foundation Stage School, East Oxford Primary School
823

9
Hinksey Park, Carfax, , 
Kennington and South Hinksey
Grandpont Nursery School
560

10
Wolvercote, Summertown, Jericho, North, St Margarets

1131

11
Marston, Headington Hill & Northway, Headington 34,37

614



Total
5368



Running total of reach by 2008
7033

2008-10, no further Children's Centre development. Oxford City will be covered in 2006-08 development

The Vale of White Horse, Annex 2

Existing Centres 
None

2006-2008 Development

Total
Ward/SOAs
Key Service(s)
Catchment

12
Abingdon Northcourt, 00,99, Abingdon Fitzharris, Abingdon Abbey & Barton, Marcham & Shippon

1058

13
Abingdon Caldecott, Abingdon Ock Meadow, Sutton Courtenay & Appleford, Drayton
South Abingdon & Sutton Courtenay Sure Start, Caldecott School
760

14
Faringdon & the Coxwells, Shrivenham
Faringdon Family Centre, Faringdon Primary School
945

15

Appleton & Cumnor, North Hinksey & Wytham, Osney (city)
Elms Rd Nursery School, West Oxford Primary School
577



Total
3340



Running total of reach by 2008
10373

2008-2010 Development

Total
Ward/SOAs
Key Service(s)
Catchment


Abingdon Northcourt 01, Abingdon Peachcroft, Abingdon Dunmore, Radley, Sunningwell & Wootton, Sandford

1052


Wantage Charlton, Wantage Segsbury, Hendreds, Greendown, Craven

994



Grove, Hanneys

506



Longworth, Stanford, Kingston Bagpuize with Southmoor

420



Total
2972



Running total of reach by 2010
2972

South Oxfordshire, Annex 3

Existing Centres 
None
2006-2008 Development

Total
Ward/SOAs
Key Service(s)
Catchment

16

Didcot All Saints, Harwell
Stephen Freeman Primary School, Lydalls Nursery School
496

17
Didcot Northbourne, Didcot Park, Hagbourne, Blewbury & Upton
Didcot Family Centre
851

18
Berinsfield
Berinsfield Family Centre 
382



Total
1729



Running total of reach by 2008
12102

2008-2010

Total
Ward/SOAs
Key Service(s)
Catchment


Henley North, Henley South

628


Chiltern Woods, Sonning Common, Shiplake, Goring, Woodcote

1044


Watlington, Chalgrove, Benson

896


Thame North, Thame South, Chinnor, Aston Rowant

1128


Wheatley, Great Milton, Forest Hill & Holton, Garsington

567


Crowmarsh, Brightwell, Wallingford North, Cholsey & Wallingford South

873


Didcot Ladygrove

846



Total
5982



Running total of reach by 2010
8954

West Oxfordshire, Annex 4

Existing Centre

Total
Ward/SOAs
Key Service(s)
Catchment

19

Chipping Norton, Kingham, Rollright & Enstone, Hook Norton, Chadlington & Churchill, Charlbury & Finstock, The Bartons, Ascot & Shipton, Milton under Wychwood
ACE
1378



Total
1378



Running total of reach by 2008
13480

2006-2008 Development

Total
Ward/SOAs
Key Service(s)
Catchment

20
Witney Central, Witney South, Witney East, 
Witney Families Together
845

21
Carterton North East, Carterton North West, Carterton South, 

959



Total
1804



Running total of reach by 2008
15284

2008-2010 Development

Total
Ward/SOAs
Key Service(s)
Catchment



Witney North, Witney West, Ducklington

645



Bampton & Clanfield, Burford, Leafield & Minster Lovell, Brize Norton & Shilton, Alvescot & Filkins

538


Eynsham & Cassington, Standlake, Aston & Stanton Harcourt, Freeland & Hanborough, North Leigh, Woodstock & Bladon, Stonesfield & Tackley , Hailey

1210



Total
2393



Running total of reach by 2010 
11347

Cherwell, Annex 5

Existing Centres

Total
Ward/SOAs
Key Service(s)
Catchment

22
Banbury Ruscote, Banbury Neithrop 47,48, Banbury Easington, 32,34
Sunshine Centre, Orchard Fields Community School and Neighbourhood Nursery 
857



Total
857



Running total of reach by 2008
16141

2006-2008 Development

Total
Ward/SOAs
Key Service(s)
Catchment

23
Banbury Hardwick, Banbury Neithrop 45,46, Cropredy
CHUFF Family Centre, Hanwell Fields Primary School
847

24
Banbury Grimsbury & Castle 35, part of 36 & 38, Calthorpe, Banbury Easington 30, 31 33
Britannia Rd Family Centre 
656

25
Banbury, Grimsbury & Castle, most of 36, part of 38 & 37,39 & 40
East St Early Excellence Centre, Grimsbury Family Association, St Leonard’s C of E School
590

26
Bicester West, Bicester Town, Ambrosden & Chesterton
BUFF
929

27

Bicester East, Bicester North,
BUFFERS
963

28
Kidlington South, Kidlington North, Yarnton, Gosford & Water Eaton
Kaleidoscope Family Centre
900



Total
4885



Running total of reach by 2008
21026

2008-2010 Development

Total
Ward/SOAs
Key Service(s)
Catchment



Bicester South

530



Fringford, Caversfield, Launton, Otmoor, Aston & the Heyfords, Kirtlington

1121


Bloxham & Bodicote, Wroxton, Sibford, Deddington, Adderbury

685



Total
2336



Running total of reach by 2010
13683

List of Abbreviations

BVR

Best Value Review

CC

Children’s Centre

CPI

Child Poverty Index

DfES 

Department for Education and Skills

EYDCP
Early Years Development and Childcare Partnership

IMD

Index of Multiple Deprivation

ISS

Integrated Support Services


LA

Local Authority

PCT

Primary Care Trust

PLA

Pre-school Learning Alliance

SOA

Super Output Area










� This is recorded as 0 in the final two columns as the number of children under 5 and the numbers of centres are included in the district totals listed above


� This is currently one centre but this is an area of high need and will be developed as 3 centres with one overall management structure  


� This is a smaller than average area because the area is cut off by the ring road so does not link naturally with other areas. The needs of the area justify funding as a full Children’s Centre 


� Kennington and South Hinksey are included in the City boundary although in the Vale because this community relates more to South Oxford than to areas in the Vale.





� This Children's Centre will be sited in the Vale but the catchment will include areas of the City


� New development planned for Grove will give an opportunity to collaborate with the District Council over the site for this Children's Centre.


� These areas will be included as outreach from Faringdon in the 2008-10 phase.


� Discussions are underway with the District Council over the possibility for linking Children's Centre development with the plans for new housing in West Didcot


� This is a larger than average reach. More resources will be needed in order for the ACE centre to successfully provide an outreach service to all these areas.


� When plans are developed for this area, consideration will be given to developing one Children's Centre in Witney with outreach to different settings


� This may be developed as outreach from a Carterton Children's Centre.


� Consideration will be given to developing one centrally managed Children's Centre developed in Bicester and the surrounding areas


� As above


� As above





PAGE  
CA_OCT1805R06.doc

