ANNEX B:

SUMMARY ACTION PLAN RESULTING FROM RECOMMENDATIONS OF CSCI INSPECTION OF CHILDREN’S SERVICES

|  | # RECOMMENDATIONS | # ACTION | BY WHEN | BY WHOM | # EARLY MILESTONES | # FIT WITH CYPP |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Improved consultation arrangements are needed to ensure all users of services for children with a disability feel included in the redesign of the services. | Review the overall consultation arrangements with children & parents and put in place a consultation action plan to address any gaps. | Feb 06 | Asst Head of Service (SEN, Disability, Access) with Children’s Care Partnership. | Consultation arrangements have been mapped. Parental consultation on arrangements in Jan 06. Actions in place by Feb 06. | The commitment in the plan to be service user and carers led. |
| 2. | Medium and long-term strategies need developing to ensure all Assessment Teams can undertake their work with adequate resources. | Recruit 2 additional temporary social workers. Procedures and practice reviewed and established as fit for purpose. Strengthen management/audit arrangements to ensure practice and procedures are reviewed regularly. Convert 2 temporary posts into permanent posts Recruit 2 additional permanent social workers. | Aug 05 Oct 05 Feb 06 Jun 06 Oct 06 | Asst Head of Service (Assessment, Family Support) | Achieved. Impact on timescales, practice and systems evaluated. Achieved. QA Officers to audit Assessment Teams’ thresholds for assessment and transfer. QA audits to continue 3xyearly. Recruitment to 4 permanent posts subject to acceptance of budget bid 06/07. | Ensuring children and young people are Healthy and Stay Safe. |
| 3. | Staffing problems around the Home Care service need to be resolved so that children with a disability receive a needs led service. | Put in place a Home Care Action Plan to promote stability and reduce staff turn over. Develop the University of Care to enhance the care workforce both in skills and numbers. | Oct 05 Oct 06 | Asst HoS (SEN, Disability, Access). | 50% reduction in staff turnover achieved by Nov 05. Unit manager seconded to manage the project Nov 05. | Meeting the needs of children with disabilities and their families and carers. |
| 4. | A range of fostering services need to be developed to ensure capacity and choice is increased. | Bid to modernisation fund for additional SWs (for recruitment of foster carers). Use the Placement Matters Strategy plan to strengthen in-house provision. | Dec 05 Apr 06 | Asst HoS (CLA, Leaving Care & Placements). | Bid to be evaluated by Dec 05. Improved systems underpinning foster carer availability to be in place by Jan 06. | Ensuring children and young people who are unable to live at home are Healthy, Stay Safe and able to Enjoy and Achieve. Making best use of our resources. |
| 5. | The Advocacy Service needs promoting across all services for children to ensure take up is increased. | Review and redesign the Advocacy Service and identify options for promotion and extension. | Nov 05- Apr 06 | Asst HoS (CLA. Leaving Care & Placements). | Review started 24.11.05. | The commitment in the plan to be service user and carers led. |
| 6. | Accommodation for Care Leavers needs to be improved in the short-term to ensure they have the best start in life. | Establish a Quality Housing Forum. Embed accommodation in the Local Area Agreement. Review current commissioning arrangements and develop improved approaches. | Dec 05 March 06 June 06 | Asst HoS (CLA, Leaving Care & Placements). | Forum established Nov 05. LAA submission Dec 06. Housing Worker seconded from Oxford City Council Jan 06. | Ensure Care leavers are Healthy, Stay Safe, are able to Enjoy and Achieve, Make a Positive Contribution and Achieve Economic Well-Being. |
| 7. | Unit Managers need to be relieved of the need to carry cases. | Recruit 4 additional permanent social workers: 2 in Family Support Teams, 2 in Adoption & Safeguarding (plus the 4 in Assessment Teams & those funded through the modernisation bid). | April – Oct 06 | Head of Service (Early Years & Family Support). | Subject to acceptance of budget bid for 06/07. | Managing our services and resources well. |
| 8. | The City Office reception needs to be refurnished and made more attractive. | Redecorate and re-furnish area. | Nov 05- Mar 06 | Head of Corporate Property. | Redecorated Nov 05 Replace furniture Mar 06. | Making services welcoming and accessible. |
| 9. | All assessments need to take account of cultural issues, drug and alcohol abuse and domestic violence. | Review specialist and core assessment protocols, train and support staff on implementation. Deliver domestic violence Champions’ training. | Nov 05- May 06 | Asst HoS (Assessment & Family Support). | Updated protocol for SW assessment of substance-misusing parents Nov 05. DV training Nov/Dec 05. Oxon Parent Infant Project to improve assessments of parenting capacity Jan-May 06. | Ensuring children and young people are Healthy and Stay Safe and that services meet the needs of ethnic minority communities, children and young people. |
| 10. | All Review notes need to be produced on time preferably by dedicated staff, working independently from the ‘pool’ of administrators. | Review and conference service to be strengthened and provided with additional admin support. | Apr 06 | Asst HoS (Safeguarding & QA) | Subject to acceptance of budget bid for 06/07. |  |
| 11. | All Children Looked After must have a personal education plan on file. | Virtual School (CLA) Head to oversee PEPs. Review system for monitoring, reporting and implementing PEPs. Achieve PEPs for 100% of all eligible children. | Jan 06 Feb 06 | Asst HoS (CLA, Leaving Care & Placements) | New PEP developed. Virtual Head in place Jan 06. Raise from 70% to 80% by Dec 06, then review and set timescale for 100%. | Ensuring children and young people Looked After can Enjoy and Achieve. |
| 12. | Files to be compliant with departmental procedures & actions signed off by managers at all times. The system for auditing files needs reviewing to ensure files are more consistent and compliant with departmental policies. | Review system for file auditing. Agree procedures, timescales, methods of achieving compliance with recording policy and file-auditing policy. Implement revised system. | ## Jan 06 Oct 06 | Asst HoS (Assessment & Family Support) | Review set up for Dec 05. New system to be fully operational when projected additional staff in post. | Managing our services and resources well. |
| 13. | The Council should invite parents to the Priority Panel when their children are being discussed, and parents always be given full copies of minutes of the discussion pertinent to their child. | Joint review with parents about participation in decision-making and attendance at panel. Report to be compiled with appropriate recommendations. | Apr 06 | Asst HoS (SEN, Disability, Access). | Parents receive copies of minutes already. All means by which parents take part in Panel decisions have been mapped Oct 05. | The commitment in the plan to by service user and carers led. |
| 14. | The Assessment Teams should open for client access and phone calls during lunchtime. | Lunchtime access established. | July 05 | Asst HoS (Assessment & Family Support) | Achieved. | Making services welcoming and accessible. |
| 15. | Staff should be provided with training on how to address issues of culture and heritage within their assessments. | The Equality and Diversity Action Plan addresses training and development issues. | Mar 06 | Asst HoS (Assessment & Family Support) | Good Practice Seminars in place for Mar 06. | Equipping our staff to meet the needs of all communities. |
| 16. | The collection of information needs to ensure that the outcome of new initiatives is measured and co-ordinated across the county and that more detail is available to managers on throughput and quality of work in social work teams. | Measure the Prevention and Intervention Team’s impact on throughput and quality in social work teams. Strengthen management information on throughput of cases. Review system for disseminating across teams the findings of 3xyearly practice audits by QA Officers. | March 06 Apr 06 Jun 06 | Asst HoS (Safeguarding & QA) | P&I Evaluation programme in place Nov 05. Review of web-based management information reports set up for Dec 05. Analyse outcomes of previous audits by Apr 06. | Managing our services and resources well. |
| 17. | We recommend that an action plan be developed to improve attendance by staff on training courses. | Improved attendance to be achieved through the provision of additional staff and relieving unit managers of casework. | Oct 06 | Head of Service (Early Years & Family Support) | Team plans for use of delegated training budgets to be reviewed Jan 06 Staff in post Oct 06. | Equipping our staff to meet the needs of children young people and their families and carers. |
| 18. | The combined role of decision-maker and Quality Assurance Manager should be reviewed. | Review and address as part of the re-alignment process. New arrangements to be put in place. | Nov 05 Feb 06 | Asst HoS (Safeguarding & QA) | Current arrangement reviewed by Legal Adviser Sept 05. | Managing our services and resources well. |

Hannah Farncombe, December  2005, V4

### Glossary

AHOS		Assistant Head of Service

SEN		Special Educational Needs

QA		Quality Assurance

SW		Social Worker

CLA		Children Looked After

PEP		Personal Education Plan

DV		Domestic Violence

P&I		Prevention and Intervention