ANNEX D

Oxfordshire Children’s Centre programme – Risk analysis

The children’s centre programme will offer new and expanded services to support young children and families. Providing integrated support and early intervention at local level will provide long term benefits for children and families including improved educational and economic achievement, greater well-being and life opportunities.  The success of the programme will depend on Oxfordshire’s capacity to deliver within resources and time available. There is likely to be a high level of monitoring from Government Office South East, Ofsted and the DfES.  The programme will also be monitored and contribute to assessment of the Local Authority through the APA and Joint Area Reviews.

| Identifier | Description | Impact | Probability | Counter-measures | Control monitor |
| --- | --- | --- | --- | --- | --- |
| Level of revenue resources | Revenue funding to support programme is modest in view of requirement to deliver full service model in areas of highest need | low | high | Develop graduated or ‘gateway’ model for areas outside of 30% most disadvantaged nationally and ‘graduated plus’ models for areas with only one or two population pockets in 30% most disadvantaged. Take account of existing family centre and family support resources and allocate new revenue funds accordingly. | Children’s Centre Programme Board EYFS |
| Capacity to deliver capital programme on time | Although additional capital is available, County Council resources will be stretched to deliver large programme in short timescale. | high | high | Early establishment of property group reporting to the Children’s Partnership Board. Manage as one project. Audit of existing resources – schools with surplus places to be considered as a priority where appropriate. Conversion rather than new build where appropriate. Build on OCC land where appropriate to avoid additional planning requirements and link with extended schools | Children’s Partnership Board (CYP&F Property and assets) |
| Sustainability of services in the medium and long term | Revenue funding is only guaranteed until March 2008 | high | low | Childcare Bill will make children’s centres a statutory part of Local Authority provision. Advice is to plan for long term. Minimize risk through short term service level agreements where appropriate. Capital assets are permanent and could be used to generate revenue if grant falls out. | Children’s Centre Programme Board County Council Cabinet EYFS service |
| Competing priorities and lack of engagement by schools and other agencies | Delivery of core offer of services is dependent on schools and all agencies (including health services and the voluntary sector) being prepared to refocus existing services around children’s centres, where they exist. Escalating and prohibitive costs associated with health engagement is a risk if existing community health services are not refocused" | high | medium | Children’s Health Services Leads are key members of the Children’s Centre Programme Board. Children’s Centres key mechanisms for delivery of the Children and Young People’s Plan. Refocus current service level agreements with the voluntary sector to deliver services around children’s centres where appropriate. Communication is particularly important at a time of high level of reorganization and realignment in Local Government and across the Health Trusts in Oxfordshire. | Children’s Centre Programme Board Public Services Board?, |
| Governance and management | Different models of children’s centre likely to require different governance and management arrangements. For Schools this will involve extended governance arrangements and managing income for childcare services as well as extended workforce | high | medium | Work with Governor Development Unit to provide support and training for governors and business planning support. Develop different models of governance for Local Authority managed services and those contracted to voluntary sector partner. | EYFS service, Educational Effectiveness – Governor Development |
| Workforce | The development of children’s centres will require staff to work in new ways across traditional professional and agency boundaries. It will also require the recruitment of highly skilled and qualified staff – or the intensive professional development of existing staff – especially to provide effective leadership and management | high | medium | Make children’s centre workforce development high priority in EYDCP plan and in service development programmes. Support Children’s Centre leaders through NPQICL and local mentoring pilot | Early Years Development and Childcare Partnership EYFS service |
| Planning and Delivery | Variety of new/recent initiatives in children’s services need joined up planning and delivery: Every Child Matters, realignment, Extended Schools, Children and Young People’s Plan, Children’s Trusts could lead to overload and duplication at locality level | medium | medium | Need for joined up coherent project planning. Use Local Area Agreement and Children and Young People’s Plan to develop models for better support for and local delivery of services. Pool resources where appropriate and where possible. | CYP&F Leadership Team, Children’s Partnership Board, Children’s Trust |