# Oxfordshire Minerals and Waste Development Scheme (2005 – 2008)

# May 2005

# Table 2 – Schedule of Proposed Minerals and Waste Development Documents (MWDDs) for Oxfordshire

| Document Title | Status | Brief Description | Chain of Conformity | Commence Preparation & Community Engagement | Consultation on Issues and Options | Consultation on Preferred Options and Proposals | Date for Submission to Secretary of State | Independent Examination | Adoption |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Statement of Community Involvement | Non - Development Plan Document | To set out Oxfordshire CC’s policy on community involvement in MWDDs and planning applications | Must be in conformity with regulations | March 2005 | Combined consultation stage Sept – Oct 2005 |  | Feb 2006 | June 2006 | Dec 2006 |
| Minerals and Waste Core Strategy | Development Plan Document | To set out Oxfordshire CC’s vision, objectives and overall spatial development strategy for minerals and waste matters for a period of at least 10 years | Must be in general conformity with Regional Spatial Strategy | March 2005 | Sept – Oct 2005 | May – June 2006 | Feb 2007 | Sept – Oct 2007 | July 2008 |
| Minerals Site Proposals and Policies | Development Plan Document | To make provision and identify sites for minerals development for a 10 year period and provide the framework for minerals and waste development control decisions, and replace saved plan polices and proposals | Must be in conformity with Core Strategy | March 2005 | Sept – Oct 2005 | May – June 2006 | Feb 2007 | Sept – Oct 2007 | July 2008 |
| Waste Site Proposals and Policies | Development Plan Document | To make provision and identify sites for waste management development for a 10 year period and provide the framework for minerals and waste development control decisions, and replace saved plan polices and proposals | Must be in conformity with Core Strategy | March 2005 | Sept – Oct 2005 | May – June 2006 | Feb 2007 | Sept – Oct 2007 | July 2008 |
| Proposals Map | Development Plan Document | To show spatial representation of policies and identify sites allocated for minerals and waste development | Must be in conformity with Core Strategy and Minerals and Waste Sites Proposals and Policies DPDs | March 2005 | Sept – Oct 2005 | May – June 2006 | Feb 2007 | Sept – Oct 2007 | ANNEX 1 July 2008 |
| Minerals and Waste Development Code of Practice | Supplementary Planning Document | To provide detailed guidance on operation of minerals and waste sites and on how new minerals and waste developments should be carried out | Must be in conformity with Minerals and Waste Site Proposals and Policies DPDs | March 2005 | Single consultation stage May – June 2006 |  | N/A | N/A | July 2008 |

Note:  Pre-Examination Meetings, if required, will take place a minimum of 8 weeks prior to the start of the Examination (see individual document profiles in Section 3).