ANNEX 6

Former Learning & Culture Directorate

# Action Plan to address 2005/06 budget pressures

## ISSUES

|  | January MMR £’000 | February MMR £’000 | Change £’000 | Comments |
| --- | --- | --- | --- | --- |
| LC1 – School Development |  |  |  |  |
| Strategic Management | 34 | 25 | -9 | Action identified |
| OQSA | 210 | 261 | 51 | Seeking opportunities to increase income earning |
| OSIT | 279 | 306 | 27 | Action identified and taken in part |
| Administration | 35 | 20 | -15 | Action identified and taken in part |
| Residential Centres | 41 | 29 | -12 | Action identified |
| Governor Services | 82 | 71 | -11 | Action identified |
| LC2 – Children’s Services |  |  |  |  |
| Home to School Transport | 381 | 381 | 0 | Further virement from SEN to be agreed |
| LC3 – Community Learning |  |  |  |  |
| Youth Service | 17 | 17 | 0 | Action identified and taken in part |
| Student Support | 6 | 2 | -4 | Action identified and taken in part |
| Adult Learning | 289 | 309 | 20 | Action identified and taken in part |
| LC4 – Cultural Services |  |  |  |  |
| Museums & Heritage | 9 | 9 | 0 | Action to be identified |
| Music Service | 58 | 21 | -37 | Action to be identified |
| LC5 – Resources |  |  |  |  |
| PRC | 490 | 490 | 0 | Action identified and taken in part |
| Misc Employee Expenses | 143 | 143 | 0 | Action to be identified |
| Licenses | 10 | 10 | 0 | Action to be identified |
| TOTAL PRESSURES | 2,084 | 2,094 | 10 |  |
| LC1 – School Development |  |  |  |  |
| Early Years Team | 0 | -23 | -23 | Funding from Early Years Service |
| SEN | -234 | -225 | 9 |  |
| Advisers | -445 | -477 | -22 |  |
| LC2 – Children’s Services |  |  |  |  |
| Fees to Out-County Schools | -184 | -184 | 0 | Virement to Transport to be agreed |
| Statementing | -228 | -228 | 0 | Virement to Transport to be agreed |
| Social Inclusion | 0 | 0 | 0 |  |
| LC3 – Community Learning |  |  |  |  |
| Early Years | -408 | -395 | 13 |  |
| LC5 - Resources |  |  |  |  |
| Personnel Staff Costs | -22 | -22 | 0 |  |
| Training (uncommitted) | -4 | 0 | 4 |  |
| Health & Safety (Personnel) | -92 | -92 | 0 |  |
| Joint Sports | -170 | -170 | 0 |  |
| Directorate General Expenses | -81 | -81 | 0 |  |
| Support Services | -88 | -38 | -50 |  |
| LC6 – Systems & Performance |  |  |  |  |
| Head of Service & Central Service Costs | 0 | 0 | 0 | All now treated as committed |
| TOTAL SAVINGS | -1,956 | -1,935 | 21 |  |
| Total Overspend/Underspend 2005/06 | 128 | 159 | 31 |  |
| Earmarked underspends not included above | -451 | -451 | 0 |  |
| Committed underspends not included above | -724 | -827 | -103 |  |
| Total Overspend/Underspend 2005/06 per Annex 2 | -1,047 | -1,119 | -72 |  |

Actions

| Head of Service | Budget | Action Required £k | Action Identified (per MMR) | Action Taken | Action Achieved |
| --- | --- | --- | --- | --- | --- |
| Judith Morris | Strategic Management | 25 | Proposed virement from SEN (curriculum support) |  |  |
| Judith Morris | OQSA | 261 | Seek opportunities to increase income earning but recognise budget pressure remains because of reduced capacity within team. Proposed virement of ££170k from SEN (curriculum enhancement) | Increased income targets being agreed with individuals. |  |
| Judith Morris | OSIT | 306 | Integrate OSIT and School Improvement Teams. Increase charge rate to schools and introduce paid consultancy. Virement of £240k from adviser staffing proposed. | OSIT and School Improvement Teams integrated. Consultancies introduced. School improvement funding utilised. |  |
| Judith Morris | Administration | 25 | Manage staff vacancies. Virement from adviser staffing budget proposed. | Adviser vacancy used to offset overspend. Utilisation of grant. | Vacancy savings achieved. |
| Judith Morris | Residential Centres | 29 | Review Service delivery to increase efficiency of operation. Proposed virement of £12k from SEN (curriculum support) | Review underway. |  |
| Judith Morris | Governor Services | 71 | Review balance between statutory/core and traded work. Possible virement from Clerking Service. | Review underway. £7k costs charged against Clerking Services |  |
| Gillian Tee | Home to School Transport | 381 | Virement of £370k from SEN. Virement of £100k from SEN Virement of £481k from SEN. | Requested through August MMR Requested in this MMR | Virement actioned. Virement actioned. |
| Gillian Tee | Youth Service | 17 | Manage staff vacancies. £50k one-off virement from Scrutiny carry-forward agreed by Cabinet. Holdback on non-staffing costs. | Overspend projection takes account of senior managers covering vacant posts until end of 05/06. Virement actioned. | Projected overspend contained at current level since July 2005. Projected overspend reduced from £103k in September 05 to £17k currently. |
| Gillian Tee | Student Support | 2 | Manage staff vacancies. | Overspend projection takes account of savings arising from not backfilling maternity leave. Additional staff vacancies. | Reduction in staffing hours enabling projected overspend to be contained and gradually reduced. |
| Richard Munro | Adult Learning | 309 | Complete service restructuring process according to schedule. Review balance of course provision for learners with learning disabilities in 06/07 academic year. Appoint substantive Head of Adult Learning by end of February 2006. | 12 candidates for voluntary redundancy agreed with effect from 1 January 2006. Review of provision has started. Appointment process in hand. |  |
| Richard Munro | Museums & Heritage Service | 9 |  |  |  |
| Richard Munro | Music Service | 21 |  |  |  |
| Rick Harmes | PRC | 490 | Offset part of overspend with £439k unallocated carry-forward underspend. Proposal to meet the cost of Adult Learning redundancies from reserves, subject to other commitments on the reserve. | Requested through August MMR. | Virement actioned. |
| Rick Harmes | Misc Employee Expenses | 143 |  |  |  |
| Rick Harmes | Licences | 10 |  |  |  |