## ANNEX 1

## Children’s Centres in Oxfordshire - Phase 3 draft timeline

| Sept |  |
| --- | --- |
| Aug/Sept | Planning meetings with PCT and Jobcentre plus Mapping and proposals |
| Sept 10 | Briefing paper to John Mitchell |
| Sept 14 | Member’s briefing |
| Sept 24 | Children’s Centre Programme Board for approval of (subject to elected member approval) Proposals for consultation Principles Mapping Funding formula development |
| Oct |  |
| Delegated member approval Oct 2nd or full cabinet 16th October | Proposals for consultation Principles Mapping Funding formula development Timeframes (question re capital approval?) Future of rural project |
| Oct 18 | Children’s Centre Leads Funding formula proposals – consultation on factors for inclusion in formula & constitution of working group |
| Oct - Nov | Funding working group designs and agrees formula model Indicative 3 year allocations published |
| End Sept to Dec |  |
|  | Consultation: Parent/carer questionnaire Expressions of interest in Children’s Centre involvement Parents (via Health Visitors) and children in 30-50% category; Thame, Wallingford, Grove, Wantage Focus groups with Health Visitors |
| Nov / Dec |  |
|  | 11 Consultation evenings |
| Jan / Feb |  |
| Cabinet Feb 19 (report in by Jan 25) | Analysis of consultation Report to cabinet with firmed up proposals Funding formula and sums for each centre Capital outline if appropriate |
| Feb to April |  |
|  | Tendering |
| April |  |
|  | Capital allocation |