The New Scrutiny Work Programme – Work to commence in 2007/08

| Priority | Topic | Type of Scrutiny | Membership | Proposed start/ finish dates: work starting 2007 | No of officer days | Resources (Finance & external support) required |
| --- | --- | --- | --- | --- | --- | --- |
| Community Safety Committee (CS) |
| 1 | Ability to recruit (and retain) retained fire fighters. Incorporating work around workforce diversity, retention of retained firefighters, whole time recruitment. The Task Group would also monitor the implementation of the recommendations and outcomes of the Fire Cover Review as compared to the position the previous year as part of this review. | Scrutiny Review | Cllrs Altaf-Khan, Farrow, Mathew | Sept 07- June 08 | 40 days | Max £1500 – visits and events |
| 2 | Gypsy & Traveller sites. High priority - lessons learned to ensure retention of Chartermark, the first Gypsy & Traveller service to achieve this. | Presentation/Select Committee | Small Task Group (Cllrs Rose, Viney, Legge) to initiate background work | Autumn Autumn 2008 | If it proceeds to review – 40 days | N/A - unless need to commission Directorate support |
|  | Coroner’s Caseload and Interaction with Oxfordshire County Council. | Scrutiny Review | Councillors Legge and Mathew | This is an ongoing review |  |  |
| Social & Community Services (S&CS) |
| 1 | Fundamental Service Review: Cultural Services. | FSR | Cllrs Seale, Hallchurch, Gatehouse | ongoing | 0 days (done by directorate officers) |  |
| 2 | Fundamental Service Review: Day Services for Older People. | FSR | Cllrs Haffenden, Sanders and Godden | recently underway | 0 days (done by directorate officers) |  |
| 3 | Single Front Door for social care/ Advice and Information Service/ common referral and assessment for preventative services and Single Point of Access to Rehabilitation and Care (SPARC)/ Single Assessment Process (SAP). | Scrutiny Review | Cllrs Fitzgerald-O’Connor & Hallchurch | 22 Aug 07 14 May 08 | 40 days | £400 |
| 4 | Cogges Manor Farm Museum. Committee to monitor progress made in relation to the production of a Business Plan in six month’s time | Q & A session during meeting | Whole Committee activity | July 2008 | 0 days (done by C’ttee officers) | None. |
| 5 | Adult Learning To assess the impact of the new emphasis on level 2 qualifications with regard to the impact on provision for people with learning disabilities. | Task Group | Cllrs Haffenden, L. Sanders + Gatehouse | t.b.d. | 40 days |  |
| Children’s Services (Ch S) |
| 1 | Young (Child) Carers (and support for them). | Scrutiny Review | Cllrs Turner, Fitzgerald O’ Connor & Viney + Mr Jackson | Sept 2007 March 08 | 50 days | Similar to above; £5,000 |
| 2 | Educational Attainment among the most “deprived” across all Key Stages. (City Council will be doing a review on BME & Achievement) | Scrutiny Review | Cllrs Haffenden, Turner & V. Smith + Mrs Matthew, Ms Spencer | Feb 09 | 50 days - likely to be a complex review? | Possibly some directorate & external support? £5 – 10,000 |
| Environment & Economy (E&E) |
| 1 | Mitigating Future Flood Risk | Scrutiny Review | Cllrs Greene, Lamont, Mathew & Purse | 31 October 2007/ 16 July 2008 | 50 days | £1,600 (but may increase) |
| 2 | The economy of market towns and Villages How are these being supported and sustained – what strategies are in place and how effective is the Oxfordshire Economic Partnership at addressing this issue? This may be tasked to also address tourism. | Scrutiny Review | t.b.d. | After one year of operation | t.b.d. | t.b.d. |
| 3 | Cycling to work Do current strategies represent value for money? Could look at cycling safety/ casualties as well. | Select Committee Q&A session | Cllrs Lamont, Greene & Dhall | 20 February 2008 @ 2:00 p.m.; 21 May 2008 – draft report | t.b.d. | t.b.d. |
| 4 | Fundamental Service Review of Transport Scrutiny to examine (light touch) the options produced by the FSR. | FSR | Cllrs Dhall, Hayward & Roz Smith | Head of Transport to appraise the Committee regularly following liaison with the Lead Members | t.b.d. | t.b.d. |

| Corporate Governance (CG) |
| --- |
| 1 High | Scrutiny – to consider implications for Oxfordshire CCs scrutiny function as a result of all new government legislation | Scrutiny Review* | Cllrs Bryden, Rose & Wilmshurst | September 2007: *Further action deferred pending guidance by the Lead Member Group on progress of the Bill and clarification of the relevant legislation. | t.b.d. | t.b.d. |
| 2 Medium | Publications | Scrutiny Review | Cllrs Armitage, Carter & Wilmshurst | t.b.d. | t.b.d. | t.b.d. |
| t.b.d. | Consultation & Engagement Arrangements – to consider with the Cabinet Member for Change Management the outcomes of the external review of arrangements and direction of travel of Cabinet report; and to consider the updated strategy & improvement plan | Select Committee Q&A session | Whole Committee activity | 6 March 2008; t.b.d. | t.b.d. | t.b.d. |

t.b.d. = to be determined

ANNEX B

The New Scrutiny Work Programme – Work to commence in 2008/09

| Priority | Topic | Type of Scrutiny | Membership | Proposed start/ finish dates: work starting 2008 | No of officer days | Resources (Finance & external support) required |
| --- | --- | --- | --- | --- | --- | --- |
| Children’s Services (Ch S) |
| 3 | Ongoing review of the CYPP after 1 year Involving a task group reporting back to the committee periodically. | Task Group | Cllrs Fooks, Glass Woodin Haffenden, Handley + Sue Matthew, Bernadine Spencer | t.b.d. | Ongoing | N/A –Support from Scrutiny & directorate officers |
| 4 | Sport in Schools. (select committee) | Select Committee/”Mini Review” | Cllr Carter & others t.b.d. | t.b.d. | 20 days? | < £1,000 |
| 5 | “Why are 95% of EBD pupils boys?” | t.b.d. | t.b.d. | t.b.d. | 20 days | < £1,000 |
| 6 | Workload and Recruitment of Headteachers (the implementation of PPA time has put additional pressures on headteachers. The Committee was concerned that this is one more factor likely to affect existing difficulties with Oxfordshire recruitment and retention of headteachers and wish to bring this to the notice of Cabinet). | Select Committee | t.b.d. | t.b.d. | 40 days | t.b.d. |
| 7 | Monitoring of external agencies | Scrutiny Review | t.b.d. | t.b.d. | t.b.d. | t.b.d. |
| Environment & Economy (E&E) |
| 5 | Effectiveness of the Oxfordshire Waste Partnership What difference does partnership working make? | Review process to be determined | t.b.d. | After one year of operation (21 May 2008?) | t.b.d. | £100 |
| 6 | Highways Safety / Road Accidents To examine the responsibilities of partners | t.b.d. | t.b.d. | t.b.d. | t.b.d. | t.b.d. |
| Social & Community Services (S&CS) |
| 6 | Sustainable Community Strategy. Esp. the Health and Well Being Partnership and the Healthy Communities and Older People block of the LAA. | Scrutiny Review | Cllr J. Godden | t.b.d. (The strategy won’t be finalised until December). | 30 days |  |
| 7 | Cultural Events | Q & A session | t.b.d. |  |  |  |
| 8 | Electronic Social care Record | Q & A session | t.b.d. |  |  |  |
| Corporate Governance (C&G) |
| t.b.d. | Scrutiny of Partnership / Local Area Agreement | Task Group | Cllrs Brighouse, Bryden & Wilmshurst | t.b.d. | t.b.d. | t.b.d. |
| t.b.d. | Council communications | t.b.d. | t.b.d. | t.b.d. | t.b.d. | t.b.d. |
| t.b.d. | Procurement | t.b.d. | t.b.d. | t.b.d. | t.b.d. | t.b.d. |

ANNEX C

Oxfordshire Joint Health Overview and Scrutiny Committee

Work Programme Projects 2007/ 2008

| Topic | Status |
| --- | --- |
| Oxfordshire Joint Health Overview & Scrutiny Committee |
| The impact of demographic change on older people's services (continued from 2005/06 programme) | Ongoing |
| Stroke prevention | Just about to start |
| Partnership working | Delayed for the time being in light of imminent information of the Health & Well-being Partnership by the Director of Public Health |
| Access to psychological therapies (an overview of the effect of the OBMHT changes) | Just started |
| Public Health Group |
| An investigation into the effects on public health, if any, caused indirectly from fortnightly collections of rubbish, especially in the County's larger dwelling areas | Deferred until government’s Communities and Local Government Parliamentary Select Committee has reported then will consider whether to go ahead with it again. |
| Equality of Health and Social Care Consumption - initially in the provision of services relating to type 2 diabetes | Just started |
| Shifting the Emphasis to Prevention – with the emphasis on older people | Part of the impact of demographic change review |