CM8 – page 3

Scrutiny work programme 
ITEM CM8
	
	August
	September
	October
	November
	December
	January
	February
	March

	Task & finish reviews  

	Demographics
	
	
	
	
	Draft (S&CS)


	Final    (OJHOSC)
	
	

	Educational Attainment 
	 
	Scoping- COMPLETE 
	
	
	
	
	Draft 
	FINAL

	Finmere Quarry 
	
	Scoping-  COMPLETE 
	 
	Draft report to committee 
	
	
	 
	

	Debt and Money Advice
	
	
	Scoping 

COMPLETE 
	Work begins
	Interim paper 
	
	Final
	

	Market Towns 
	
	
	
	Scoping 
	
	
	Draft 
	Final 

	Select Committees /Seminars 

	Flu Pandemic(II)
	
	Planning - COMPLETE
	Select Committee

COMPLETE 
	Report to Cmmtee/CCMT

Complete
	
	
	
	

	Climate change
	
	
	
	
	Scoping
	
	Select Committee
	Report to CCMT/Cabinet

	Teenage Conception and Pregnancy
	
	
	Planning 

COMPLETE 
	
	Seminar 
	
	
	

	Working Group

	Self Directed Support 
	
	
	
	
	Planning 
	
	Interim paper 
	

	Partnerships 
	
	
	
	
	Report to Cmmttee
	
	
	

	Legislative changes to scrutiny
	
	
	
	
	Report to Cmmtee
	
	
	

	Directorate Resourced

	Publications (1)
	Planning - 

COMPLETE 
	Report to Committee COMPLETE
	
	
	
	
	
	

	Oxfordshire Waste Ptnrhsip


	
	Planning -COMPLETE 
	Scoping COMPLETE 
	
	
	
	Report to Cmmtee
	

	Barriers to Employment
	
	
	Planning 

COMPLETE 
	
	
	
	Seminar 
	Report to committee 

	Local Transport Plan 3 
	
	
	 
	Scoping 
	
	
	
	


Work programme July 2008 – April 2009 
	Committee 

	Subject area 
	Type of work 
	Resource
	Scoping doc to committee
	Draft to committee

	Community Safety 
	Flu Pandemic – part 2 (ongoing) 
	Select Committee
	PPR
	N/A
	November 08 

	
	Debt and Money Advice 
	Review 
	PPR
	COMPLETE
	December 08

	
	
	
	
	
	

	Children’s Services 
	Educational Attainment 
	Review 
	PPR
	COMPLETE 
	February 09

	
	Teenage conception and pregnancy
	Seminar 
	PPR 
	December 08
	

	
	
	
	
	
	

	Social and Community Services 
	Barriers to Employment (Joint with E & E) 
	Seminar 
	Directorate
	November 08
	February 09 

	
	Self Directed Support 
	Working Group 
	PPR 
	December 08
	February 09 

	
	
	
	
	
	

	Environment and Economy 
	Oxfordshire Waste Partnerships pilot financial arrangements 
	Working Group
	Directorate 
	October 08
	February 09

	
	Barriers to Employment (Joint with SCS) 
	Seminar 
	Directorate 
	November 09 
	February 09 

	
	Adaptation to climate change 
	Select Committee 
	PPR
	December 08
	February 09 

	
	Finmere Quarry  
	Review 
	PPR
	COMPLETE 
	November 08

	
	Market Towns 
	Review 
	PPR & Directorate
	December 08
	March 09 

	
	Local Transport Plan 3 
	Working Group 
	Directorate 
	November 08 
	December 09 

	
	
	
	
	
	

	Corporate Governance 
	Partnerships working group (ongoing) 
	Working Group 
	PPR 
	Ongoing 
	December 08

	
	Legislative changes to scrutiny  
	Working Group 
	PPR
	Ongoing 
	December 08

	
	Publications – Initial scoping 
	Working Group 
	Directorate 
	Ongoing 
	September 08

	
	
	
	
	
	

	OJHOSC
	Demographics (ongoing) 
	Review 
	PPR
	Ongoing 
	November 08


PPR = Policy, performance and review team 













































CM_DEC0108R07.doc
CM_DEC0108R07.doc

