## Summary
Capital Programme Monthly Financial Monitoring 2004/05
April 2004
| Original | April | May | June | July | August | September | October | November | December | January | February | March | Variance | Cumulative
Directorate | Capital | Review | Review | Review | Review | Review | Review | Review | Review | Review | Review | Review | Review |  | Variance
Programme
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Learning & Culture
Education | 30633 | April: 32902 | 2269 | 2269
City Schools | 3654 | April: 3654 | 0 | 0
Cultural Services | 1390 | April: 1390 | 0 | 0
Social & Health Care | 4866 | April: 5088 | 222 | 222
Environment & Economy | 33901 | April: 35505 | 1604 | 1604
Community Safety | 191 | April: 191 | 0 | 0
Resources & CDC | 519 | April: 519 | 0 | 0
Totals | 75154 | 79249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4095 | 4095
This annex sets out the summary position in respect of planned capital spend. The first column (Original Capital Programme) shows the 2004/05 total planned spend for each directorate as reported to the Executive on 18 May 2004. The second column (April Review) shows the latest estimate of the planned spend for the year. For the first report of the year, the Variance column shows the difference between the original capital programme and the April estimate. For subsequent months the variance column will show the difference between the month of review and the previous month’s figures. The sum of all the variations in the year will be shown in the Cumulative Variance column.

## Variations
Variations from the Original Capital Programme
Cap
Prog |  | Details |  | £000 | Comments
Ref
Exempt Schemes
(included in the capital programme financing summary as planned payments awaiting project appraisals, not shown as part of the directorate programme)
Learning & Culture
|  |  | ED500 Benson | 1227 | Total Cost £1,827k funded from capital receipts. Scheme rephased since initial proposals
|  |  | ED588 Botley, Elms Road Nursery | 828 | Total Cost £1,504k funded from capital receipts. Scheme rephased since initial proposals
|  |  | ED592 Orchard Fields | 1589 | Total Cost £5,506k funded from capital receipts / government grant. Scheme rephased since initial proposals
| Sub-total |  |  | 3644
Additional Schemes
Learning & Culture
|  |  | ED610 Leafield | 416 | Total Cost £426k - Modernisation Scheme
|  |  | ED534 St Francis | 254 | Total Cost £343k - Modernisation Scheme
51 |  |  | NDS Modernisation Schemes | -670 | Allocation of Modernisation Scheme to specific schemes above
|  |  | Other variations | 197 | Funded mainly from developer contributions
Social & Health Care
810 |  |  | IT Strategy Grant Funded | 222 | Local Information Plan Grant funded
Environment & Economy
|  |  | A41 from M40 to Buckinghamshire boundary | 1604 | Supplementary Credit Approval issued 31 March 2004 for strengthening and improvement work on a recently detrunked road
| Sub-total |  |  | 2023
Revisions to Scheme Costs
Learning & Culture
|  |  | Other variations | 128
| Sub-total |  |  | 128
Slippage on Existing Schemes
Learning & Culture
37 |  |  | ED494 Nettlebed | -700
40 |  |  | ED498 Springfield | -1000
| Sub-total |  |  | -1700
| Total |  |  | 4095
This annex provides details of the month-on-month variance, itemised over various categories. Larger variances on individual schemes (lines in the capital programme) will be itemised and smaller variances will be reported in total.

## Total scheme variances
Capital Programme Monthly Financial Monitoring 2004/05
Total Scheme Variations
Cap |  | Original | Forecast | Total
Prog | Project | Project | Total | Scheme | Comments
Ref |  | Cost | Cost | Variance
|  | £000 | £000 | £000
None to report
This annex will provide information on significant variations to total scheme costs. It will be prepared on a memorandum basis and it is not intended to reconcile to the variance reported in the summary. This is a nil return for April.

## Capital Receipts
Capital Receipts Monthly Financial Monitoring 2004/05
| Original | April | May | June | July | August | September | October | November | December | January | February | March | Variance | Cumulative
Directorate | Capital | Review | Review | Review | Review | Review | Review | Review | Review | Review | Review | Review | Review |  | Variance
Receipts
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Learning & Culture
Education | 3184 | April: 3184 | 0 | 0
City Schools | 1810 | April: 1810 | 0 | 0
Less DfES | -8144 | April: -8144 | 0 | 0
Cultural Services | 29 | April: 29 | 0 | 0
Social & Health Care | [13 empty] | 0 | 0
General | 3633 | April: 3633 | 0 | 0
HOPS | 1600 | April: 1600 | 0 | 0
Environment & Economy | 506 | April: 506 | 0 | 0
Community Safety | 750 | April: 750 | 0 | 0
Resources & CDC | 45 | April: 45 | 0 | 0
Totals | 3413 | 3413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B19: StephanieSkivington: -1 rounding