## Summary
Provisional Capital Outturn 2003/04
| Capital | Outturn | Variation
Programme
| £000 | £000 | £000
Directorate Gross Expenditure
Learning & Culture
Main* | 42503 | 29841.7 | -12661.3
City Schools | 14429 | 12489 | -1940
Social & Health Care | 3653.244 | 3156.1012 | -497.1428
Environment & Economy | 31120 | 28072 | -3048
Community Safety | 146 | 58 | -88
Resources & CDC* | 4966 | 4321 | -645
Directorate Gross Expenditure | 96817.244 | 77937.8012 | -18879.4428
Professional Fees
Property | 3941 | 4307 | 366
Transport | 1967 | 377 | -1590
Total Gross Expenditure | 102725.244 | 82621.8012 | -20103.4428
Other Expenditure Items
Repayment of City Schools Reserve | 4921 | 2500 | -2421
HOPS Revenue/Capital Switch | 2124 | 2124 | 0
Transfer to HOPS Reserve | 1126 | 0 | -1126
Total Expenditure | 110896.244 | 87245.8012 | -23650.4428
Financed by
Credit Approvals | 40723 | 41142 | 419
Capital Receipts ** | 31638 | 19614 | -12024
Grants, Reimbursements and Contributions | 35157 | 24272 | -10885
Revenue | 1413 | 810 | -603
Capital Reserve | 70 | 70 | 0
Revenue Budget Contribution | 500 | 500 | 0
Other | 1395 | 838 | -557
Total Financing | 110896 | 87246 | -23650
* £200k of resources have been transferred from L&C to Corporate ICT
** Actual capital receipts in 2003/04 were £32.6m. The unused balance of £13.0m
will be carried forward to be used in a later period to fund slippage in capital
payments.
Note on F37: StephanieSkivington: adjusted for vehicles capitalisationand gypsy sites
Note on F38: StephanieSkivington: adjusted for vehicles capitalisation & gypsy sites
Note on F36: StephanieSkivington: adjusted for Crouch Street reduced so that financing matches spend
Note on G24: StephanieSkivington: rounding adjustment

## L&C Main
LEARNING & CULTURE DIRECTORATE |  |  |  |  | ANNEX 8
Provisional Capital Outturn 2003/04
Ref | Scheme | 2003/04 Budget | Expenditure | Variation | Comments
|  | £000 | £000 | £000
1 | 2002/03 and Earlier Starts - Retention's | 1106 | 629 | -477 | Slippage in finalisation of earlier projects
2 | Carterton LEA Liabilities | 626 | 529 | -97
3 | Madley Brook, Witney - New Primary School & relocation of Springfield School | 1333 | 1180 | -153 | Retention and re-phasing of completion works
4 | Hanwell Fields, Banbury - New Primary School | 1225 | 1105 | -120 | Retention and re-phasing of completion works
5 | Watlington, Icknield - Phase 2 | 462 | 448 | -14
6 | Warriner, Bloxham - Phase 2 Extensions | 477 | 477 | 0
7 | St Mary's Banbury - Repl HORSA | 280 | 269 | -11
8 | Sonning Common - Repl HORSA | 237 | 184 | -53
9 | Eynsham, Bartholomew - Repl HORSA | 14 | 7 | -7
10 | Wheatley Park - Repl HORSA | 244 | 233 | -11
11 | Henry Box - HORSA | 587 | 587 | 0
12 | Carswell - Ext & Adaptations | 574 | 530 | -44
13 | Abingdon, Caldecott - Consolidation | 840 | 759 | -81
14 | Sandhills Primary School - Replacement School | 210 | 210 | 0
15 | Cropredy School - Extensions | 339 | 321 | -18
16 | Wantage Schools Unification (Inc NDS (4)) | 279 | 198 | -81
17 | Thameside - Sports & Arts | 50 | 4 | -46
18 | West Oxford | 444 | 444 | 0
19 | Relocation of Music Service | 240 | 244 | 4
20 | Peers P2 - Mabel Prichard | 75 | 0 | -75
21 | Ormerod - Relocation to Marlborough | 77 | 82 | 5
22 | Langtree, Woodcote - Extensions | 479 | 502 | 23
23 | Ladygrove | 317 | 313 | -4
24 | Carterton Community College - Phase 1 | 525 | 493 | -32
25 | St Birinus - 6 class Humanities | 721 | 731 | 10
26 | Marlborough - 5 Classroom Maths Block | 552 | 554 | 2
27 | Wood Green -Extensions 6th Form | 200 | 0 | -200 | Slippage due to delayed start of major project
28 | Shrivenham - Repl HORSA | 564 | 533 | -31
29 | St Michael, Steventon - Repl HORSA | 100 | 75 | -25
30 | Matthew Arnold - New Science | 870 | 871 | 1
31 | Badgemore | 288 | 236 | -52
32 | Bartlemas - Relocate SS Mary & John | 712 | 712 | 0
33 | Grimsbury Early Excellence | 840 | 795 | -45
34 | Neighbourhood Nursery & Family Centre - Ormerod | 255 | 268 | 13
35 | Abingdon Family Centre | 350 | 269 | -81
36 | Neighbourhood Nursery & Family Centre - Wood Farm | 370 | 274 | -96
37 | Nettlebed | 0 | 0 | 0
38 | Brookside - Sports & Arts | 61 | 1 | -60
39 | Queens Dyke - Ext | 395 | 340 | -55
40 | Springfield School (Secondary) | 0 | 0 | 0
41 | Northern House - Repl HORSA | 453 | 413 | -40
42 | The Harlow Centre | 150 | 144 | -6
43 | Heyfords | 0 | 0 | 0
44 | Watchfield | 0 | 0 | 0
45 | Burford | 0 | 0 | 0
46 | Minor Works | 7096 | 4919 | -2177 | Delayed claims against financial commitments
47 | Key Stage 2 * | 20 | 6 | -14
48 | Devolved Formula ** | 10632 | 5780 | -4852 | Delayed spending of finance delegated to schools
49 | Condition * | 3009 | 2301 | -708 | Programme rephasing
50 | Modernisation | 2904 | 9 | -2895 | Programme rephasing
51 | Modernisation | 0 | 0 | 0
52 | Modernisation | 0 | 0 | 0
53 | Staff Work Places | 361 | 120 | -241 | Slippage
54 | Seed Challenge * | 293 | 257 | -36
501 | Computer Scheme (Online Public Access) | 0 | 0 | 0
502 | Oxfordshire Museum-Extension Phase I & II | 16 | 16 | 0
504 | Bicester Library Extension | 0 | 0 | 0
505 | Central Library | 1 | 1 | 0
506 | Kidlington Library, Day Centre & Highways Offices | 314 | 314 | 0
507 | Museum & Heritage - Education Centre | 11 | 10.7 | -0.3
508 | Libraries & Museums Minor Works | 121 | 139.3 | 18.3
509 | Wychwood Library Minor Works | 4 | 4.7 | 0.7
| Transfer of resources to Corporate ICT programme | -200 |  | 200
| TOTAL | 42503 | 29841.7 | -12661.3
Note on D53: GraCl: includes £12k orchard fields
Note on D69: PercivalE: excludes £18.9K developer Contribution (M42100)

## L&C City
LEARNING & CULTURE DIRECTORATE |  |  |  |  | ANNEX 8
Provisional Capital Outturn 2003/04 - Oxford City Schools Reorganisation
Ref | Scheme | 2003/04 Budget | Expenditure | Variation | Comments
|  | £000 | £000 | £000
1 | Barton Village First / Bayswater Middle | 164 | 164 | 0
2 | Church Cowley St James First School | 11 | 1 | -10
3 | Cutteslowe First School | 11 | 9 | -2
4 | East Oxford First School | 26 | 25 | -1
5 | Larkrise First School | 55 | 33 | -22
6 | Lawn Upton Middle / Speedwell First | 1320 | 1245 | -75
7 | Orchard Meadow First School | 102 | 25 | -77
8 | Pegasus First School | 6 | 0 | -6
9 | SS Mary and John First School / Isis Middle School | 512 | 475 | -37
10 | St Barnabus First School | 40 | 0 | -40
11 | St Christopher's CE First School | 22 | 10 | -12
12 | St Ebbe's CE Aided First School | 0 | 0 | 0
13 | St Francis First School | 9 | 0 | -9
14 | St Michael's First School | 15 | 10 | -5
15 | St Nicholas First School - Phase 1 | 65 | 65 | 0
16 | Windale First School | 43 | 1 | -42
17 | Windmill First School - Phase 1 | 5 | 0 | -5
18 | Windmill First School - Phase 2 | 810 | 712 | -98 | Slippage due to programme phasing
19 | Wolvercote First School | 134 | 68 | -66
20 | SS Philip and James CE First | 238 | 5 | -233 | Retention and slippage due to rephasing of completion works
21 | St Aloysius RC First School | 68 | 68 | 0
22 | St Joseph's RC First School | 41 | 40 | -1
23 | Our Lady's RC First School | 18 | 17 | -1
24 | Hinksey | 323 | 228 | -95 | Slippage due to programme phasing
25 | St Andrews | 42 | 30 | -12
26 | Orchard Meadow First School | 0 | 0 | 0
27 | Cherwell School | 1940 | 1802 | -138 | Retention and slippage due to rephasing of completion works
28 | Cheney School | 2359 | 2181 | -178 | Retention and slippage due to rephasing of completion works
29 | Cheney School - Sports Hall | 79 | 79 | 0
30 | Oxford School | 2643 | 2643 | 0
31 | Peers School | 362 | 362 | 0
32 | Transition Costs | 993 | 736 | -257
33 | Cycle Storage | 275 | 148 | -127 | Financial slippage due to rephasing of works
34 | Highway Costs | 0 | 0 | 0
35 | Schemes under £200,000 | 1326 | 1036 | -290 | Financial slippage due to rephasing of works
36 | Language Resource Base - Secondary | 250 | 189 | -61
37 | Language Resource Base - Primary | 0 | 0 | 0
38 | Land | 25 | 30 | 5
39 | Risk | 0 | 0 | 0
40 | Planning Appl's / Disbursements etc | 52 | 52 | 0
41 | Abortive Time / Travel Studies etc. | 45 | 0 | -45
| TOTAL | 14429 | 12489 | -1940

## S&HC
SOCIAL & HEALTHCARE DIRECTORATE |  |  |  |  | ANNEX 8
Provisional Capital Outturn 2003/04
Ref | Scheme | 2003/04 | Expenditure | Variation | Comments
Budget
|  | £000 | £000 | £000
804/813 | HOPS STAGE 1&2 | 1561 | 1557.788 | -3.212
805 | Community Mental Health | 201 | 10.371 | -190.629 | Complete
808 | IT - Mental Health SCA | 329 | 329.111 | 0.111 | Complete
812 | Wallingford Day Centre | 387 | 387.099 | 0.099 | Complete
809 | IT Strategy - Supporting People | 102.334 | 13 | -89.334 | Underspend to be carried forward to 2004/5
810 | IT Strategy - Grant Funding | 325.209 | 294 | -31.209 | Underspend to be carried forward to 2004/5
803 | IT Strategy | 106 | 44.4602 | -61.5398 | Underspend to be carried forward to 2004/5
814 | Children's homes Holme Leigh | 0 | 0 | 0
818 | Minor Works (CF) | 248 | 281.007 | 33.007
806 | New Directions | 248.701 | 168.701 | -80 | Underspend to be carried forward to 2004/5
802 | Office Accom Strategy (CF) | 0 | 0 | 0 | Complete
816 | Health & Safety | 100 | 0 | -100 | Underspend to be carried forward to 2004/5
817 | Child Disability Svsc Re-des | 45 | 70.564 | 25.564
| TOTAL | 3653.244 | 3156.1012 | -497.1428

## E&E
ENVIRONMENT & ECONOMY DIRECTORATE |  |  |  |  | ANNEX 8
Provisional Capital Outturn 2003/04
Ref | Scheme | 2003/04 | Expenditure | Variation | Comments
Budget
| Transport | £000 | £000 | £000
Major Schemes
301 | Total Pre 2001/02 retentions | 638 | 11 | -627
302 | Oxford Integrated Transport Strategy | 3185 | 858 | -2327 | Schemes slipped to 04/05 due to changes in planned strategies
303 | Thornhill P & R | 225 | 156 | -69 | Retention payments due in 2004/05
304 | GTE for Oxfordshire | 500 | 375 | -125 | Delayed progress with consultancy work
305 | B4031 Improvements -Finmere | 180 | 166 | -14
306 | Didcot Milton Heights 2 | 468 | 584 | 116 | Additional costs to secure programmed completion
307 | Bicester Skimmingdish Lane | 711 | 650 | -61 | Completion in 2004/05
309 | Highway Depot Strategy | 0 | 55 | 55 | Awaiting sale of associated sites
310 | Banbury Hennef Way | 3889 | 3425 | -464 | Minor delays to programme - completion still on programme
311 | Faringdon Depot | 17 | 0 | -17 | Awaiting sale of associated sites
312 | Witney Cogges Link | 455 | 105 | -350 | Waiting for new planning applications
313 | Witney West End Link Rd | 77 | 45 | -32 | Programme delay by Land purchase
314 | North Oxford P & R | 360 | 507 | 147 | Payments for additional work required
315 | Cornmarket | 2508 | 2282 | -226 | 2003/04 budget reflects updated cost position. Scheme completion in 04/05
316 | Thornhill Interchange | 40 | 36 | -4
| Total Major Schemes | 13253 | 9255 | -3998
ANNUAL PROGRAMMES
317 | Structural Maintenance | 10006 | 10211 | 205
318 | Sustainable Transport
a | Better ways to School |  | 599
b | Cycling & Walking
| Culham to Berinsfield |  | 39
Benson to Wallingford
Thame to Shabbington
| Hanborough/Bladon |  | 124
| Horspath to Oxford |  | 436
| Abingdon to Drayton |  | 188
| NCN Top up funding |  | 195
| North Leigh to Witney |  | 165
| Cycling Schemes under £100K |  | 144
c | Public Transport
1 | Rail Station Development |  | 10
2 | Premium Routes |  | 52
3 | Real Time Information |  | 34
4 | Taxibuses |  | 200
5 | Public Transport Schemes under £100K |  | 203
| Sustainable Transport 03'04 allocation | 2329 | 2389 | 60
319 | Community Safety
| Traffic Management & Calming |  | 776
| Rural Traffic Management |  | 302
Footways
| Home Zones |  | 6
| Pedestrian Crossings |  | 403
| Pedestrian & Cycle Imps |  | 54
| Allocation 2003/04 | 1650 | 1541 | -109 | Some schemes slipped to 04/05
320 | Casualty Reduction
| Assessed Schemes |  | 607
| Mass Action Plans |  | 9
Speed Cameras
Speed Indicator Devices
| DFT Cowley Rd Demonstration Project | 100 | 84 | -16
| Allocation 2003/04 | 800 | 700 | -100 | Some schemes slipped to 04/05
321 | Integrated Transport Studies
| Banbury |  | 1008 |  | Developer funded schemes
| Abingdon |  | 836
| Bicester |  | 443
| Witney |  | 291
| Henley |  | 676 |  | Inclusion of Henley TC Improvements funded from Contribtions from Henley TC & SODC
| Allocation 2003/04 | 2728 | 3254 | 526 | Retentions from 02/03 and changes to planned strategy
323 | Works associated with private development | 1 | 0 | -1
324 | Miscellaneous land Acquisitions & Surveys | 85 | 3 | -82 | Provision for blight
| Developer Funding | 0 | 602 | 602 | Funded from Developer Contributions
Waste Disposal
326 | Waste Disposal-Dix Pit Redesign | 126 | 0 | -126 | Scheme sipped to 04/05
Trading Standards
328 | Mass Comparators | 20 | 17 | -3
329 | Road Traffic Act Enforcement | 22 | 16 | -6
| Sub Total Annual Schemes | 17867 | 18817 | 950
| Total Schemes | 31120 | 28072 | -3048

## CS
COMMUNITY SAFETY |  |  |  |  | ANNEX 8
Provisional Capital Outturn 2003/04
Ref | Scheme | 2003/04 | Expenditure | Variation | Comments
Budget
|  | £000 | £000 | £000
Fire & Rescue Service
703 | Radio Scheme | 45 | 0 | -45 | Slippage
706 | Minor Works | 101 | 58 | -43 | Slippage
| TOTAL | 146 | 58 | -88

## R&CDC
RESOURCES & CDC |  |  |  |  | ANNEX 8
Provisional Capital Outturn 2003/04
Ref | Scheme | 2003/04 | Expenditure | Variation | Comments
Budget
|  | £000 | £000 | £000
ICT
603 | Countywide Broadband Network | 2038 | 1627 | -411 | capital work to be competed in 2004/05
616 | Corporate ICT | 1200 | 1151 | -49
|  | 3238 | 2778 | -460
Property
601 | Headquarters Offices | 214 | 57 | -157
602 | County hall Improvements | 0 | 237 | 237
604 | Artistic Decorations | 16 | 30 | 14 | Contributions due from other directorates & contractors
606 | Raising our Performance | 168 | 136 | -32 | Work slipped to 04/05
605 | Staff Housing | 45 | 1 | -44 | Work slipped to 04/05
607 | Energy Conservation Programmes | 66 | 36 | -30 | Work slipped to 04/05
608 | Minor Works | 129 | 99 | -30 | Work slipped to 04/05
609 | Restoration of Listed Buildings | 6 | 0 | -6
610 | Restoration of Venison House | 17 | 16 | -1
611 | Asbestos Monitoring | 67 | 70 | 3
612 | Asset Management Plans | 50 | 50 | 0
613 | Oxford Castle Archeological Work | 300 | 300 | 0
614 | Oxford Castle Education Centre | 150 | 0 | -150 | Contingency
615 | Structural Maintenace (inc. fees) | 500 | 475 | -25
| Rationalisation Of Central Offices |  | 36 | 36
|  | 1728 | 1543 | -185
| Total | 4966 | 4321 | -645