OXFORDSHIRE WASTE PARTNERSHIP JOINT COMMITTEE

OXFORDSHIRE WASTE PARTNERSHIP JOINT COMMITTEE
27th March 2009
AGENDA ITEM 10
Performance Monitoring Report – march 2009 

	1
	Purpose of Report

	1.1
	To provide a quarterly update on the performance of the Oxfordshire Waste Partnership (OWP).

	2
	Background

	2.1
	This report provides an update on the OWP’s progress over the previous quarter against its agreed Joint Municipal Waste Management Strategy (JMWMS) Action Plan. A budget statement is included, together with a summary of performance against National Indicator (NI) and Local Area Agreement (LAA) targets.



	2.2
	JMWMS Action Plan

The 2008/09 Action Plan is attached at appendix 1. Each action has been assigned a “traffic light” score to indicate whether the project is:

· Completed or on track (green)

· Progressing, but with some outstanding issues or concerns (amber)

· Not progressing as planned (red)

Some of the main areas of success and concern are set out below.

Successes

· The contract for food waste treatment has been signed, which will see the construction of new In-Vessel Composting and Anaerobic Digestion plants within Oxfordshire;
· The joint collection contract between South Oxfordshire and Vale of White Horse has been signed, which will introduce new weekly food waste collections and alternating recycling and refuse wheeled bin collections;
· A countywide communications campaign encouraging people to reduce food waste (Love Food Hate Waste) is currently being delivered. This includes newspaper advertising, website information, a series of countywide road shows and a “left overs” recipe competition.
· Commercial waste recycling services have been extended within Oxford City with the support of OWP New Initiatives Funding.

Concerns
· As previously reported, the trial food waste collection schemes planned within Cherwell and Oxford City will not be delivered this year, due to the absence of suitable local outlets. These schemes will be launched once facilities become available through the County Council Food Waste Treatment Contract.
· The planned review of partner councils purchasing polices, with a view to developing a “buy recycled” policy has not been completed by the target date of Mar 09. Work will continue in 2009/10 on this project.

· Whilst all partner councils have signed up to the LGA reputations campaign, none have yet fully reached the silver status within the programme by the target date of Mar 09. Work will continue in 2009/10 on this project.




	2.3
	Risks

A risk register that identifies risks associated with the delivery of the 2008/09 JMWMS Action Plan is maintained. Risks are scored according to their likelihood and the impact that they would have should they occur. Mitigation measures are set out to reduce the effects of these risks. The highest scoring risks (i.e. those that are either most likely or might have the most dramatic impact) are set out in table 1 below. 
The likelihood of two risks (nos. 5.1 and 8.2) has been increased, making them high level risks. The likelihood of two previously high level risks (nos. 8.4 and 13.2) has been reduced, so these are now classed as moderate risks. These are not routinely reported to the joint committee, but are reviewed twice per year by the Officer strategy group. 
Table 1 – high level risks

No. (from JMWMS Action Plan)
Action 

(from JMWMS Action Plan)

Risk

Possible Consequence

Mitigation

Status at Jan 09
1.3
Show case best practice on in-house waste reduction to Oxfordshire residents & businesses.

Dependency - reliant on successful completion of earlier project phases.

Unable to showcase best practice.

Effective project management of earlier stages.

Regular updates on project progress provided at WRPG meetings. To date, preceding phases completed as planned. Currently developing a summary report of council buildings waste audits. 
5.1
Implement an enforcement plan and joint policies on controlling waste, and trade waste abuse.

Failure to reach agreement on joint plan, differing priorities at Partner Councils

Disjointed practices, potential increased costs. Failure to meet LAA2 targets.

Appropriate prioritisation through EQ&C group, plus clear recommendations to elected members.

Joint plan not yet developed. EQ&CG is still at information gathering and exchange of best practice level, rather than developing joint policies. Work is underway, but original deadline missed. Risk likelihood has, therefore, been increased. 

6.1
Implement trial collection schemes for food waste.

Location of facility.
Operational difficulties might preclude development of collection schemes.

Ensure logistics and transportation are factored into County Council tender evaluation.

The absence of a local facility has prevented the development of trial schemes this year. 

The County Council preferred bidder's solution is based on three Oxfordshire based sites for food waste. Two sites have now been granted planning permission. Construction of the facilities remains subject to contract award by OCC.

6.4
Procure a facility for the acceptance and reprocessing of food waste.

Deliverability - short timescales, planning & construction risks.

Project delay, leading to cost increases and potential implications for Waste Collection Authority procurements. Reputation damage.

Good project management, setting realistic timescales and goals. Contingency planning.

Regular discussions at Officer Strategy Group and OWP on the delivery of new facilities and collection schemes. 
Planning permission granted for two facilities. Contract has been awarded.
6.4
(as above)
Failure to introduce new collection systems by WCAs.
Cost increases and reputation damage.

Good project management and ongoing commitment to partnership objectives.

Scheme design options are being finalised by each Waste Collection Authority (schemes largely finalised in Cherwell, South and Vale).

Joint working group commissioned to improve consistency and coordination. Bid for Local Area Agreement reward funding submitted.

8.2
Provide recycling collection services to commercial waste customers.

Changes to legislation and market trends.

Service costs increase.

Environmental scanning, monitor developing trends.

DEFRA issued clarification on definition of wastes within the Controlled Waste Regulations 1992 (CWR). Many councils including Oxfordshire had interpreted the legislation differently.

Following LGA lobbying 
DEFRA have agreed to review the CWR, but the detailed timetable for this is not yet known.
Legal view suggests changes may be needed to comply with current legislation. Risk likelihood increased, so that this is now considered a high level risk.

8.4
Reduce the amount of residual waste collected per customer for commercial waste collection services.

Dependent upon provision of alternatives services (reduction and recycling).
Increased LATS costs.

Good services and effective promotion.

NIF funding awarded to Oxford City and Cherwell for commercial waste recycling services. Risk likelihood reduced, meaning that for the time being, this will no longer be treated as a high level risk.

10.1
Secure sufficient landfill capacity for Oxfordshire's municipal waste.

Sufficient competition.
Higher contract prices.

Ensure contracts are packaged in a way that encourages wider competition.

OJEU contract notice to be published in March 09.

13.2
Encourage the local reprocessing of collected waste streams through partner council procurement and contracts.

Ability of market to deliver.
Potential increased cost to process materials locally. Quality of service compromised. 

Ensure full exploration of potential markets.

OCC food waste contract secured in county processing. South /Vale has local bulking but wider reprocessing. Risk likelihood reduced, meaning that this will no longer be treated as a high level risk.

15.3
Finalise and agree targets for LAA2.
Failure to reach stretch targets.
Potential LAA reward payments cannot be accessed. Reputation damage.

Regular performance monitoring. Good project planning.

There is regular reporting to OSG & OWP on National Indicator performance.

LAA2 activity plans developed and submitted to Partnership Unit.

NI 195 peer review monitoring sessions are ongoing.
15.6
Develop enforcement measures to support recycling & composting collection services and the roll out of alternate weekly refuse collections.

Public/media opinion.
Bad press coverage. Enforcement action not supported at Magistrates courts. Residents do not cooperate with schemes.

Good education and communication. Support provided to residents to explain scheme requirements. Enforcement used as a last resort, when other options have been exhausted.

A range of measures identified and considered by Environmental Quality & Cleansing Group. These will be included in a draft joint enforcement plan.
15.6
(as above)
Support and buy in of operational staff

Material quality suffers. Potential increase in fly-tipping. Residents do not support new schemes.
Involve operational staff early and ensure that they are adequately trained.

Contract mobilisation plan for SODC includes staff training.




	2.4


	Budget statement

The current budget position is shown in table 2 below. This shows an under spend of £106,180. The majority of this sum is a current under spend of £53,572 against the communications plan. Some of the main reasons for this are that new collection calendars budgeted for South Oxfordshire and Vale of White Horse are now not needed until next year and also road shows have been delivered in-house, whereas an amount for outsourcing had been budgeted.   Salary savings of approximately £36,500 have arisen because the Communications Officer and Clean & Green Officer posts were filled mid-year, and also due to a buy-out of a performance related pay scheme at Cherwell D.C in 2007/08. 
Proposals for the treatment of any under spend will be put forward to the next meeting (as part of the annual report). It was agreed on 16th January 2009 that the reserve of £40,232 carried forward this year, will be used to off-set 2009/10 partner contributions.
Table 2  - budget statement at Mar 09

	
	 

Budget £

Actual £

Commitment £

Variance £

Expenditure

 

 

 

 

Core Budget 

 

 

 

 

Partnership Officer 

70,000

52,517

4,997

-12,487 
Training and support costs

4,000

2,306

300

-1,394 
Admin Support

5,000

0

2,000

-3,000 
OWP Host Authority admin costs

2,000

0

2,000

0 

OWP Accounting Authority costs

2,000

0

2,000

0 

OWP Auditing Authority costs

1,000

0

3,530

2,530 

Waste Enforcement Officer

34,200

13,725

2,487

-17,988 
Communications Officer (WRAP)

34,200

24,827

3,164

-6,209 
Sub-total Core 

118,200

68,548

17,314

-32,339 
Development Budget 

 

 

 

 

Wild Waste Show

120,000

90,000

30,000

0 

Waste Reduction Packs

20,000

3,200

0

-16,800 
Home composting

18,500

13,954

1,500

-3,046 
Communications Plan

164,900

94,071

17,258

-53,572 
LAA Project Municipal Waste

43,747

37,324

5,500

-923 
LAA Project Clean Green

59,383

42,834

16,549

0 

Contingency/Opportunities

17,500

18,000

0

500 

Sub-total Development

444,030

299,383

70,807

-73,841 
Total Expenditure

562,230

367,931

88,120

-106,180 
Income

 

 

 

 

WPEG

 

 

 

 

Cherwell District Council

45,423 

45,423 

0 

0 

Oxford City Council

45,423 

 

45,423 

0 

Oxfordshire County Council

226,998 

226,998 

 

0 

South Oxfordshire District Council

45,423 

45,423 

0 

0 

Vale of White Horse District Council

45,423 

45,423 

0 

0 

West Oxfordshire District Council

44,379 

44,379 

 

0 

WPEG Total

453,068

407,646

45,423

1 

LAA pump priming

103,130

103,130

 

0 

Carried forward from previous year

40,232

40,232

 

0 

Total Income

596,430

551,008

45,423

1 



	2.5

	New Initiatives fund
Table 3 provides a summary of the New Initiatives Fund (NIF) budget position. From this it can be seen that £542,687 of revenue and £554,645 of capital funding currently remains available for projects.  The value of the fund includes the Local Area Agreement Performance Reward Grant (PRG) for our recycling target, which is known to have been achieved. It excludes PRG for our Clean & Green Targets, which is not yet certain. The twelve projects funded to date are listed in table 4. 

Table 3 – NIF summary budget statement

 

Revenue

Capital

Total

Total fund value

 £   793,230 

 £   793,230 

 £1,586,460 

 

 

 

 

Total commitments

 £   230,453 

 £   236,200 

 £   466,653 

 

 

 

 

Total expenditure

 £     20,090 

 £      2,385 

 £     22,475 

 

 

 

 

Remaining funds

 £   542,687 

 £   554,645 

 £1,097,332 

Table 4 NIF funded projects
Bidding authority

Bid partners

Project

Funding awarded

Vale of White Horse D.C

-

Hessian sack recycling containers for flat dwellers

 £    2,475 

Oxford City

-

Food waste collection trial

 £         -   

Cherwell D.C

Kidlington Versus Climate Change, Kidlington P.C 

Recycling containers at bus stops

 £    9,878 

Oxfordshire County Council

Cherwell D.C

Study and compositional anlaysis of Waste Recycling Centre residual waste

 £  35,000 

Cherwell D.C

Bicester Town Council, Oxfordshire Highways

Lay-by recycling containers

 £  10,000 

Oxford City

-

Door knocking survey to flats and houses of multiple occupancy

 £  40,000 

Cherwell D.C

Oxford City, South Oxfordshire & West Oxfordshire

Christmas sacks for kerbside recycling collections.

 £    7,550 

Cherwell D.C

Oxfordshire C.C, EiE, Kidlington Parish Council, Bicester Town Council & Banbury T.C

Trade waste recycling

 £    7,250 

Oxford City

-

Trade waste recycling

 £157,000 

West Oxfordshire

Oxfordshire C.C and Oxford City

Trade waste recycling

 £    9,975 

West Oxfordshire

Oxfordshire C.C

Interim green waste service

 £  90,000 

Cherwell D.C

Kidlington Parish Council, Bicester Town Council & Banbury T.C

Food waste collections.

 £120,000 

Totals

 

 

 £489,128 




	2.6
	NI Target performance

Performance against national Indicators is summarised in table 5 below. From this is can be seen that recycling and composting performance is currently 43.89%, this is a slight drop from the previous quarter. This is matched with a slight increase to the percentage landfilled.
Performance standards on litter remain very strong, but there has been a slight deterioration of 0.6% from the previous quarter. Standards on detritus remain lower and a score of 36% within the Vale of White Horse is currently skewing overall results. This is twice as much as is being recorded in other districts. Levels of graffiti and fly-posting remain low.
The latest figures on fly-tipping incidents suggest that 08/09 performance will show a reduction in the number of fly-tips reported compared to the previous year. The figures reported in January for South, Vale and West appear to have been overstated. Amended figures have now been included in table 5.
Table 5 National Indicator performance
NI number

NI description

07/08 performance

Previous quarter performance

08/09 performance to date

NI 191

Residual waste per household

New indicator for 08/09.

399.85 kg (to end of Oct)
543 kg
NI 192

Percentage of household waste sent for reuse, recycling and composting

40.25%

45.27% (to end of Oct)
43.89%
NI 193

Percentage of municipal waste landfilled

61.31%

54.73%.
57%
NI 195

Improved street and environmental cleanliness (levels of litter, detritus, graffiti and fly posting)

New indicator - a revision of the previous BVPI 199.

Litter – 6%

Detritus – 10%

Graffiti – 2%
Fly posting – 1.4%
Litter – 4.2%
Detritus – 16.6%
Graffiti – 2.6%
Fly posting – 1.4%
Litter – 4.8%
Detritus – 18.6%
Graffiti – 2.8%
Fly posting – 1.4%
NI 196

Improved street and environmental cleanliness – fly tipping

Total incidents 6,277:

Cherwell -  616

Oxford City -  3,570

South - 836

Vale - 604

West - 651
Total incidents 2879 (April to Nov 08):
Cherwell -  437
Oxford City -  1263
South - 470
Vale - 313
West - 396
Total incidents (April 08 to Jan 09): 
3499
Cherwell -  550
Oxford City - 1446
South - 600
Vale - 412
West - 491


	2.7
	LAA1 target performance

Table 6 summarises performance against Local Area Agreement 1 targets. Performance against LAA1 recycling targets remains on track, but we are now in danger of missing our street cleanliness target. Here no more than 11% of land can fall below acceptable standards for litter & detritus levels. Our latest monitoring has returned a score of 11.2%. This is being affected by the current detritus score within Vale of White Horse.

The results of the Place Survey are still awaited. These will determine whether the target on the % of people satisfied with cleanliness standards has been met.
Table 6 LAA1 targets
Indicator

Description

07/08 performance

Previous quarter performance

08/09 performance to date

LAA1 target 6

To increase recycling and composting county wide to 38% in 2008/9 and to recycle 4,875 extra tonnes of non biodegradable waste accumulatively from 2006/7 to 2008/9 inclusive. 

40.25%

45.27% (to end of Oct)
43.89%
LAA1 target 7

1. Reduce the proportion of relevant land and highways assessed as having combined deposits of litter and detritus falling below an acceptable standard by 9%, so that no more than 11% falls below standard (BVPI 199a)

8.60%

10%
11.2%
 

2. % of people satisfied with cleanliness standards increased to 69.58% (BVPI 89)

The BVPI 89 Survey is carried out every 3 years. The results from the 2006/07 survey was 71.4% countywide

-
Awaiting Place Survey results.


	2.8
	LAA2 target performance

Table 7 sets out current performance against LAA2 targets. Annual improvement targets have been set, but it is only the outturn performance in 2010/11 that determines reward grant payments. Current performance against NI 191, 192 and 195 (litter component) is strong. Improvement is needed if targets on reducing levels of detritus and fly-tipping are to be met.

Table 7 LAA 2 targets
Target

Description

08/09 target

09/10 target

10/11 target

Current performance

Notes

NI 191: Residual household waste per household Defra
To reduce the amount of residual waste collected to 715 kg per household or less by 2010/11.

730 kg

723 kg

715 kg

543 kg
Current performance equates to 651 kg per annum (using a linear profile).

NI 192: Household waste recycled and composted
To achieve a 45% recycling & composting rate by March 2011. 

40%

42%

45%

43.89%
Currently meeting the 09/10 target and exceeding 08/09 target.

NI 195: Improved street and environmental cleanliness (levels of graffiti, litter, detritus and fly posting
To ensure that the percentage of relevant land and highways that is assessed as having deposits of litter and detritus that falls below an acceptable standard (below grade B) by March 2011are 4% and 7% respectively, or less.

Litter 6%

Detritus 10%

Litter 5%

Detritus 9%

Litter 4%

Detritus 8%

Litter 4.8%
Detritus 18.6%
Only the litter component attracts reward grant. Currently meeting litter target for 09/10, further improvement needed for 10/11 target.
Considerable Improvement needed to meet detritus target.

NI 196: Improved street and environmental cleanliness – fly tipping
To reduce the number of incidents of fly-tipping by 10% by March 2011.

(from baseline no. of 6370)

6179

5994

5754

3499

Current performance equates to approx 4,198 incidents for the year. Target is currently being met.


	3
	Financial, Risk and Staff Implications

	3.1
	A budget under spend of approximately £106,180 is estimated. 

	4
	Areas Affected

	4.1
	All Partner Authorities are affected by the matters within this report.

	5
	Effect on Strategic Policies

	5.1
	The Action Plan has been developed to progress each of the strategic policies within the JMWMS and to support delivery of NI and LAA targets.

	6
	Options or Alternatives

	6.1
	Not applicable.

	7
	Recommendations

	7.1
	That the report is noted and that Vale of White Horse District Council be asked to investigate its current score for levels of detritus.

	8
	Reasons for Recommendations

	8.1
	To provide a performance monitoring system to support the delivery of the OWP’s objectives.

	9
	Contact Officer

	9.1
	Author:
	Wayne Lewis
	Tel:
	01295 221903

	
	Email:
	Wayne.lewis@cherwell-dc.gov.uk

	
	Background Papers:











- 1 -

