CLICK ON THE GREY FIELDS AND BEGIN TYPING


Report No:
RMB/13/05


Meeting Date:
13 July 2005


Agenda Item No:
5     



Progress Update- “Highlight Report”

13 July 2005 
KEY ISSUE/DECISION

To advise Members of the Regional Management Board (RMB) of the progress made during the period 14 April 2005 until 13 July 2005 in the development of the modernisation programme of the Fire and Rescue Services within the South East.

EXECUTIVE SUMMARY

This report presents an update on progress of the Programme using information available from the six Key Collaborative Areas: KCA1.Regional Control Rooms, KCA2.Resilience, KCA3.Procurement, KCA4.Training, KCA5.Human Resources, and KCA6.Common and Specialist Services.

CONSULTATION

Constituent members of the South East Fire and Rescue Services Regional Management Board

RECOMMENDATIONS

That the Board accept the report. 

REASONS FOR RECOMMENDATIONS

In line with the requirements outlined in Report RMB/04/04, 14 July 2004, Agenda Item 5, “Programme Management”. 

LEAD/CONTACT OFFICER: Mike McCarthy – Programme Manager     
TELEPHONE NUMBER: 01737 224035/mobile: 07968 834456     
EMAIL: mike.mccarthy @ surreycc.gov.uk

BACKGROUND PAPERS: Appendices 1-5 inclusive

INTRODUCTION

At the last RMB meeting on 13 April 2005, the end of year report was presented on the progress of the six Key Collaborative Areas (KCAs), which form the basis of the Programme for the Region.

BACKGROUND

Previous quarterly reports were produced in a “prose” format using information from individual project directors.

The total number of projects within the programme has grown significantly over the past twelve months, from seventeen to thirty nine, such that it has become increasing more difficult to report both objectively, and with clarity on the progress and direction of individual projects.

In addition, individual project directors have decided, bearing in mind the large number of projects within their portfolios, to priorities activities over the next year.

This has meant reviewing the status of their projects, and managing resources accordingly.

This report makes use of a different format, that of “Project Status Reports” with a contemporary “Traffic light “ approach to progress indication (see appendix 1) 

ANALYSIS AND COMMENTARY

Key activities within the reporting period

1. Establishing the current position with regard to progress

2. Re- assessment of “baseline” position

3. Introduction of additional programme documentation 

4. Communication established with new Business Change Manager (BCM)

5. Liaison with “Firepro” representatives and lead authority on media and communications (Surrey) with a view to establishing a Regional Web Site

6. Expansion and rationalisation of KCA (work stream) portfolios

7. Completion of projects in Procurement, Training, Human Resources and Common and specialist Services.

8. Further alignment to common terminology and process framework

9. Establishment of professional rapport between Programme Manager and Chairing Authority

10. Emergence of dependencies between projects 

Exceptions/Problems during the reporting period.

1. Lack of adherence to timeframes regarding project reporting (In particular “checkpoint reporting”)

Outlook

Within the next reporting period, the following key tasks will continue to be addressed and completed:

· Cross-reference between KCAs to establish synergies and address any areas of duplication.

· Ensure “check point” reporting on a monthly basis (or whenever deemed appropriate by individual project heads)

· Establish a “brokerage centre”

· Develop the training, education and communications process
. This will include the production of a project manager’s information pack, and ultimately the provision of training dependent upon resources.

· Development of Communications via “Firepro”

· Revision of Regional “Who’s Who?”

· Further engagement Board members, Chief Fire Officers and their Management Teams.
· Development and implementation of regional financial processes.
Issues Update

A number of issues remain outstanding across the work streams:

· Questions regarding funding (All work streams)

· Linkage between National and Regional Strategies (Regional Controls, Resilience, Training)

· Clarity of roles and effective communications (Regional Controls)

· Conflict in priorities between Regional and National expectations (Resilience)

· Commitment, Capacity and Resourcing (All work streams)

· Business continuity preserved whilst collaborative development processes are underway (Training, HR)

· Retention and redundancy issues regarding the Regional Control Centre Project.

Risks

See attached Risk Log (appendix 2)

Benefits arising during this period

See attached “Overview of Regional Best Practice”(appendix 3)

IMPLICATIONS

As of the date of submission, the number of candidate projects peaked at thirty-nine.

Several projects have now been completed; and the current portfolio stands at thirty-five (see appendices 4 and 5) 

Work stream Directors are now prioritising their projects, and the make-up of the working groups is gradually being modified with the inclusion of such members as finance and human resource specialists.

CONCLUSION

The report recommending the appointment of a programme manager (RMB/04/04; 14 July 2004), indicated that the main reason for this recommendation was that:

“There would currently appear to be a lack of cohesion in terms of the overall concept of Programme Management, and a consequential lack of control, monitoring, standardisation, validation and review, such that there exists a lack of opportunity to determine synergies, or to detect and avoid clashes between separate work streams”

It is considered that through the development of standardised processes, embedded within the programme, and increased collaboration between respective Fire and Rescue Authorities, that all the areas of concern above are being addressed.

Several projects have reached completion, and the corresponding benefits derived from collaborative working. 

The project sponsors all continue to develop the activities within their respective areas of influence, and both Officers and Members of the RMB remain helpful and supportive in their approach to the continuing development of the programme. 

SUPPORTING BIBLIOGRAPHY

The Fire and Rescue Service National Framework 2004/05

Our Fire and Rescue Service White Paper (June 2003)

RMB Business Plan 2005/2006

Managing Successful Projects with Prince2 – OGC

Managing Successful Programmes – OGC

APPENDIX 1.

Project Status July 2005

Sub Project Title
Ref.

KCA.1
Objective
Lead
Milestone/Date
Status

(R/A/G)
Comments

South East Regional Control Centre
1.1
The formal FiReControl Project business objectives are:

1.To enhance resilience in the national fire control capability

2.To support enhance efficiency and effectiveness in fire and rescue service delivery

3.To work effectively with local fire authorities to deliver sustainable business change

4.To support the wider change agenda within the fire and rescue service

5.It must be demonstrated that this investment is both affordable and value for money.

The additional business objectives for the SE Regional Project are:

6.At all times to maintain the existing fire cover for the region during the transition

7.To support the management of the transition and transfer arrangements for Control Staff to far as is reasonably practicable

8.To ensure that the RCC provides an improved service to people in the SE.


Anne Downing

(W.Sussex)
1.  Location of RCC selected

Spring 2005

(All subsequent dates are unconfirmed due to slippage of the national project)

2. Establish corporate body/Lead Authority to run RCC

Q2 2005

3. Contracts with existing suppliers revised.

10/2005

4. Individual FRA plans for modifications to existing IT systems developed.

5. Full Business Case available for review by RMB

Q1 2006

6. Governing Entity (e.g. Company Limited by Guarantee) established 


7. Building lease signed

Q3 2006

8. Regional Control Centre Director and senior managers recruited.

9. Staff transferred to Governing Entity under TUPE

10. Staff selected through Assessment process

No realistic estimates of dates are available for the following:

11. Building passed practical completion ready for hand-over to Infrastructure Services supplier.

12. Data extracted from FRA systems into RCC

13. Staff fully trained

14. RCC accepted

Q4 2007

15. Operational RCC – 1st Brigade (these dates are contingent upon agreement by ODPM and must be scheduled with neighbouring RCCs for resilience)

16. Fully operational RCC
A

A

A

A

A

A

A

A

A

A

A

A

A

A

A

A


All regions except SE have had final “moderation” meeting with Chair of RMB.  Still no date given for this in SE. 

Date for location announcements has been put back from “spring” to “before the summer recess” (July 21st).

There will be an inaugural meeting of legal representatives (1/region) on 30rd June to discuss.  Timetable for development and agreement of issues should be available after this.  Work will need to be done regionally on determining how decisions binding on FRAs can be achieved.

FRA technical staff are completing an initial assessment of ICT equipment for business continuity risk assessment, which will highlight contracts that need to be revised.

Possibly by end 2005 if all requirements for data for the proposed RCC systems are known.

Estimate only – no date has been given for this by National Project Team.  Work is starting on establishing what costs will fall on SE FRAs.

Subject to further information from ODPM on tax status and advice from FRA legal representatives.  

At this stage it is not clear who will sign the lease.  N.B.  Facilities Management contracts will need to be set up regionally.

} This will take place for Tranche

} 1 regions first.  No realistic dates 
} available.

}

}

}

}



APPENDIX 1.

Project Status July 2005

RMB Project  (Work stream) Regional Resilience

Senior Responsible Owner: Cllr David Rowlands (Buckinghamshire & Milton Keynes)

Project Director: Damian Smith                                                      Liaison Officer: David Norris

Sub Project Title
Ref.

KCA.2
Objective
Lead
Milestone/

Date
Status

(R/A/G)

Site Specific Risk Assessment
2.1
2.1.1 Compile data on Site Specific information regarding USAR/ Mass Decontamination Identified risks. Add to New Dimensions database.

2.1.2 Review USAR/ Mass Decontamination Site Specific Plans at year-end, update New Dimension database.

2.1.3 Link assessments to Civil Contingencies Act contingency planning


To be determined
To be determined
Green








Amber








Amber










Urban Search and Rescue
2.2
2.2.1 For all brigades in the South East region, who will be receiving a USAR unit, to facilitate and deliver USAR capability

2.2.2 Complete USAR capability for the region
To be determined
To be determined
Amber





2.2.2 


Amber








Mass Decontamination
2.3
2.3.1 To provide initial Mass Decontamination training for personnel in brigades in the region receiving a MD unit.

2.3.2 To provide MD continuation training within each brigade in receipt of USAR unit, in accordance with IPDS
To be determined
To be determined
Green








Amber








Detection, Identification and Monitoring Equipment
2.4
2.4.1 To provide initial DIM training for personnel in brigades in the region receiving DIM equipment.

2.4.2 To provide DIM continuation training within each brigade in receipt of a DIM unit, in accordance with IPDS
To be determined
To be determined
Amber








Amber








Water and Water Rescue
2.5
2.5.1 To provide initial High Volume Pumping (HVP) and Water Rescue training for personnel in brigades in the region receiving a HVP unit. Water rescue training to be initiated in accordance with IPDS for all brigades in South east

2.5.2 To provide HVP and Water rescue continuation training within each brigade in receipt of HVP unit, in accordance with IPDS. Water rescue training to be maintained in accordance with IPDS for all brigades in South east
To be determined
To be determined
Amber








Amber








Command and Control
2.6

To be determined
To be determined
Red








New Dimension Training
2.7
2.7.1 To provide initial New Dimension training for personnel in brigades in the region.

2.7.2 To provide New Dimension continuation training within each brigade in receipt of USAR unit, in accordance with IPDS
To be determined
To be determined
Green








Amber








Multi-Agency Response to Resilience
2.8
To be determined following discussions with SE Resilience Working Group
To be determined
To be determined
Red

APPENDIX 1.

Project Status July 2005

RMB Project  (Work stream) Procurement

Senior Responsible Owner: Cllr. Ray Jelf (Oxfordshire)

Project Director: John Parry                    Project Manager: Mike Smyth

Sub Project Title
Ref.

KCA.3
Objective
Lead
Milestone/Date
Status*

(R/A/G)

Regional Procurement Strategy
3.1
1.To produce a 3 year plan by Sept 2004, setting out a time table for the review and letting of contracts

2.To determine organisational arrangements for the delivery of the procurement function by June 2004

3.Prepare an annual procurement plan with targets and savings by January each year for implementation during the following financial year (commencing 2004)

4.Review progress against the national Procurement Strategy for Local Government to be reviewed by April 2006

Regions to review stores/distribution arrangements on a regional basis once PPE/non PPE contract awarded


John Parry

Steve Dutton

(OF&RS)
03/2005

03/2006

05/2007
Amber

Draft regional strategy gives organisational structure.

2005/06 plan being reviewed

National strategy not released yet. Time lag will require milestones to be revisited








Print and Graphic Design Contract
3.2
To put into place a contract providing a Printing and Graphic design service as described in the tender documentation that meet customer requirements
Bob Dicken

(KBC)

Graham Smith

(SE CFOA)
Q4 2005
Amber








Operational Equipment Procurement
3.3
The formal Operational Equipment Procurement Project business objectives are:

1.To deliver best value by sharing information and technical expertise

2.To support and enhance efficiency and effectiveness in the fire and rescue services operational service delivery objectives

3.To work efficiently and effectively with local fire authorities service personnel to deliver cost effective solutions in the development of all operational equipment

4.To support the wider change agenda nationally within the fire and rescue service and work closely with Fire Buy and related agencies

5.To maximise the economies of scale in the procurement process to reduce purchase costs of the equipment

6.To demonstrate that this project produces value for money, and reduces whole life costs for the end user’s.

The additional business objectives for the SE Regional Project are:

7.To reduce the costly administration process in producing equipment manuals and training aids

8.To ensure that the outcomes provides an improved service to the stakeholders in the SE Region

9.To reduce tendering and contractual costs in the procurement of operational equipment.

Des Tidbury

(RBF&RS)
02/2005
Amber

Andy Haste (RBF&RS) making good progress.








Volvo Parts Contract
3.4
1.To initially scope the actual potential spend and parts usage of Volvo vehicles throughout the SE Region.

2.To collaborate by aggregating the spend of Volvo vehicle parts. 

3.To competitively tender/negotiate (captive parts) for Volvo vehicles 

4.To seek Volvo parts at the right price, quality, quantity and delivery. 

5.To place a “call off” Contracts by end of March 2005 for Volvo Parts

6.To allow participating groups to call off from the agreements
Mike Smyth

OF&RS

Green

In Place, all Brigades will receive some financial benefit from this arrangement








South East Website Implementation
3.5
1.To provide a central electronic document library within the South East Region.

2.To improve and develop Best Practice.

3.To develop templates for procurement related documents e.g. Invitation to Tender; Risk Assessment

4.To provide mechanism for the regional work streams to cooperate with each other.
Amanda Lilley

(Surrey)
Completion 05/2005
Amber








Electrical Accessories Contracts
3.6
1.To price a representative basket of electrical accessories for each FRA’s provider, including the OGC providers.

2.Compile a service level profile for each FRA’s provider.

3.To provide an objective set of information to support the development of a contract strategy for electrical accessories.
Amanda Lilley

(Surrey)
Completion

12/2004
Amber








Cleaning Materials Contract
3.7
1.To price a representative basket of cleaning materials for each FRA’s provider, including the OGC provider (Buck and Hickman).

2.Compile a service level profile for each FRA’s provider.

3.To provide an objective set of information to support the development of a contract strategy for cleaning materials.
Amanda Lilley

(Surrey)
Completion

12/2004
Amber








Hazardous Materials Database
3.8
1.Determine a common specification for provision of hazardous material/chemical information for use by the brigades in the SE region.

2.Secure the most competitive contract for provision of these services.
Wendy Lambert

(HF&RS)

Amber








Procurement Training
3.9
1.To identify all procurement staff, other staff with procurement duties and elected Members within individual FRAs and to establish the regional position.  

2.To define their level of involvement and responsibility of individuals and groups of staff. 

3. To establish the skills gaps that exist and to present the options to support the provision of a range of professional procurement training and awareness training at appropriate levels.  

4.To present the options for a regional approach to professional procurement training.
Mike Smyth

(OF&RS)
11/2004
Amber

Funding for training matrix required.

Member training to be paid by RMB

APPENDIX 1.

Project Status July 2005

RMB Project  (Work stream) Training 

Senior Responsible Owner: Cllr. Terry Mills (Royal Berkshire)

Project Director: Iain Cox        Project manager: Cliff Sear (W.Sussex)

Sub Project Title
Ref.

KCA.
Objective
Lead
Milestone/Date
Status

(R/A/G)

Assessment and Development Centres
4.1
1.To develop and implement a best practice approach to administration and management of ADCs making best use of regional resources.

2.To undertake ADCs on a regional basis making best use of regional resources.

3.To develop best practice guidance for appointment procedures for fire authorities using ADC’s.
Alex Dunnett

(Kent)
11/2004

12/2004

04/2005
Amber

Amber

Amber








Development Programmes
4.2
1.To produce regional schemes of work for development activities associated with the roles of fire fighter, supervisory manager, middle manager and strategic manager.

2.To identify, using regional procurement procedures, the most cost-effective methods of delivering development programmes to staff across the region

3.To establish arrangements for delivery of programmes that make the best use of regional and national resources
Alex Dunnett

(Kent)
04/2005

10/2005-

04/2006
Green








Amber

Amber








HRDG Awards


4.3
1.To develop and implement a best practice approach to administration and procedures.

2.To develop best practice approaches to training assessors and verifiers.

3.To identify, using regional procurement procedures, the most cost-effective method of training assessors and verifiers across the region.

4.To establish arrangements for delivery of training of assessors and verifiers, which make best use of regional resources.

5.To establish a regional process for managing issues of accredited prior learning (APL) and accredited prior experiential learning (APEL).

6.To identify and agree a common framework for Awards within the Region.


Alex Dunnett

(Kent)
04/2005

04/2005 

10/2005

10/2005

10/2005

10/2005
Green








Amber

Amber

Amber

Amber








Green















Training Strategies
4.4
To develop a cost effective model for the design, delivery and evaluation of Training for staff within the South East Region, facilitating optimum use of existing resources.
Alex Dunnett

(Kent)
01/2005

03/2005
Amber










APPENDIX 1.

Project Status July 2005

RMB Project  (Work stream) Human Resources 

Senior Responsible Owner: Cllr. Michael Cartwright (Hampshire)

Project Director:  John Bonney                  Project Manager: Cliff Sear (W.Sussex)

Sub Project Title
Ref.

KCA.5
Objective
Lead
Milestone/Date
Status

(R/A/G)

Personnel Resourcing
5.1
1.To ensure that all Services within the Region have access to a range of standards and practices that fully-support best practice in terms of recruitment and retention of staff. 

2.To optimise the process of recruiting uniformed staff ensuring best use of facilities and most efficient process.
Kay Banfield

(Kent)
11/2004

03/2005
Amber








Working Patterns
5.2
Develop range of approved Working Patterns for uniformed personnel that reflect needs identified by IRMPs for use by Constituent Authorities.
Kay Banfield

(Kent)
04/2005
Green








Structure and Job Sizing
5.3
Agree methodology for developing organisational structures and Job sizing as a part of the transition from rank to role, ensuring a consistent approach across the Region.


Kay Banfield

(Kent)
09/2004

10/2004

12/2004
Amber








Occupational Health
5.4
Harmonise standards of Occupational Health provision within the Region and identify opportunities for improved efficiency through shared resources.
Kay Banfield

(Kent)
12/2004

03/2005
Red








Policies and Record Keeping
5.5
Harmonise policy development process, structure and content relevant to HR issues within the Region. Prioritised on a risk-assessed basis.


Jeremy Morrison

(Bucks)
11/2004

12/2004

01/2005
Amber








Work/Life balance
5.6
Develop best practice policies and procedures supporting healthy work/life balance.


Jeremy Morrison

(Bucks)
11/2004

01/2005

06/2005
Amber








Terms and Conditions of Service
5.7
Harmonise policies and procedures relating to terms and conditions of employment for staff.
Jeremy Morrison

(Bucks)
12/2004

01/2005
Amber








RMB Project  (Work stream) Human Resources 

Senior Responsible Owner: Cllr. Michael Cartwright (Hampshire)

Project Director:  John Bonney                  Project Manager: Cliff Sear (W.Sussex)

Sub Project Title
Ref.

KCA.5
Objective
Lead
Milestone/Date
Status

(R/A/G)

Equality & Diversity
5.8
Develop robust policies, strategies and employment practices that recognize the differing needs of our employees and communities, and equip our managers to proactively and positively promote fairness and diversity in the workplace and in service delivery.
Andy Kettle

(Hants)
01/05
Amber








APPENDIX 1.

Project Status July 2005

RMB Project  (Work stream) Common and Specialist Services

Senior Responsible Owner: Cllr Bryan Cope.                        Kent and Medway Towns 

Project Director: Peter Coombs                                     Project Manager: Charlie Hendry

Sub Project Title
Ref.

KCA.6
Objective
Lead
Milestone/Date
Status

(R/A/G)

Co-responding for Medical Emergencies
6.1
1.Review current schemes for co-responding in constituent authorities and other regions

2. Evaluate effectiveness and impact on other services

3. Assess risk and need with other relevant agencies across region and report with recommendations

4.Develop common procedures across region for co-responding and protocols/mou with other agencies

5. Establish potential for collaborative models of service delivery

6. Review and report on effectiveness in meeting locally agreed targets
Paul Southern

(RBF&RS)
Final Report

Q3-2005
Amber








Domestic Safety Campaigns
6.2
1.To provide best guidance across region for establishing and running domestic FS Campaigns aimed at reducing death and injury in the home

2. To develop cost effective approaches to Domestic Fire Safety Campaigns
Bill Welsh

(Kent)
Final Report 25/01/05

 
Green*

Dependent upon ratification at Steering group meeting and Board approval










Life-long Learning Education Initiatives
6.3
1. To provide best practice guidance across the region for establishing and running educational initiatives for community fire safety aimed at reducing death and injury from fire

2. To develop cost effective approaches to educational initiatives
Bill Welsh

(Kent)
Final Report

25/01/05
Green*

Dependent upon ratification at Steering group meeting and Board approval










Anti Fire- Setting
6.4
1.To provide best practice guidance across region for establishing and running youth diversion schemes aimed at arson reduction

2. To develop cost effective approaches to youth diversion schemes aimed at reducing arson.
Bill Welsh

(Kent)
Final Report

25/01/05
Green*

Dependent upon ratification at Steering group meeting and Board approval










Fire Investigation Partnership
6.5
1.To develop agreed standard of service to be applied across region

2. To review provision of current resources against that standard

3. Establish potential for collaborative delivery of fire investigation activity

4. Establish potential to extend role of fire investigators into other areas
Gary Walsh

(ESF&RS)
Final Report

Q3- 2005
Amber








Partnership Working
6.6
1. To review current practices and arrangements across region

2. To identify potential partners and likely benefits

3. Develop a best practice strategy for partnership working
Martin Crapper

(OF&RS)

Amber








Unwanted and Hoax Calls
6.7
1. To review current practices and initiatives

2. To review good practice guidance

3. To develop intervention strategies that can be applied consistently across the region
Bob Stead

(Surrey)
Final Report

Q4-2005
Amber








Regulatory Reform Order
6.8
  1.Review of progress to date

  2. Common risk assessment methodology

 3. Common policies and procedures to implement order

4. Common specification for skills and training required

5. Flexible staffing and resources model for management, enforcement and advice


Bob Stead

(Surrey)
Final Report 

Q4-2005
Amber








Specialist Operations and Major Incident Management
6.9
1.Review current arrangements for:

a) Animal Rescue

b) USAR

c) Incident Command

2. Develop best practice and common procedures across region for response including protocols/MOU with other agencies.

3. Establish potential for collaborative models of service delivery
Kevin Butcher

(HF&RS)
Final Report

Q4-2005


Amber








Management of Health and Safety at Work
6.10
1. Identify good and best practice with regard to guidance from HSE, HMFSI, ODPM, CFOA and other relevant agencies.

2. Review the currency and consistency of generic risk assessments across the region and identify common policies, procedures and training to ensure effective management of health and safety

3. Maintain and develop arrangements for inter-Service H&S audits using ROSPA QA methodology

4. Develop a regional action plan for dealing with introduction of new noise and vibration regulations

5. Use comparative data to identify regional health and safety priorities and produce regional action plans to address areas of concern.

6. Establish and implement a process for the production and maintenance of common regional health and safety policies. 

7. Undertake an efficiency review of the provision of competent health and safety advice against the requirements of the Management of Health and Safety Regulations 1999 and report with recommendations. 
David Wallace

(RBF&RS)
Final Report 

Q2-2006
Amber

APPENDIX 2    




Risk Log – July 2005

Issue Category
Definition

A
Requires immediate attention



B
Important



C
Moderate



D
Closed since last report



No
Risk No.
Cat.
Title
Narrative
Impact
Mitigation
Update
Owner
Status



1

B
KCA 3

Procurement
LOSS OF PROJECT MANAGER
DELAY IN PROJECT ADMINISTRATION AND EFFECT UPON PRACTITIONER ENGAGEMENT
PROJECT DIRECTOR TO FACILITATE NEW APPOINTMENT
AWAITING OUTCOME OF APPOINTMENT PROCESS WITHIN OF&RS
JOHN PARRY/MIKE SMYTH


2

C
KCA 1,3,6
NEW SENIOR RESPONSIBLE OWNERS
NEW MEMBERS COMING UP TO SPEED ON RMB ISSUES
INDIVIDUAL PROJECT DIRECTORS IN COLLABORATION WITH CLERK AND PROGRAMME MANAGER TO ASSIST AS NECESSARY
TO BE ADDRESSED FOLLOWING JULY RMB
RMB


3

B
ALL PROJECTS
CAPACITY OF SOME PRACTITIONERS TO ADDRESS COMPETING PRIORITIES
DELAY IN REPORTING AND ACHIEVING DEADLINES
PRIORITISATION BY PROJECT DIRECTORS WITHIN THEIR INDIVIDUAL PORTFOLIOS
ALL PROJECTS ARE BEING PRIORITISED, AND A “R/A/G” ASSESSMENT UNDERTAKEN
Project directors


4

A
KCA1/KCA2
DELAYS AND CHANGES IN NATIONAL STRATEGY RELATED TO CENTRALLY DRIVEN PROJECTS
DELAY IN REGIONAL CONSIDERATIONS; IMPACT UPON BOTH HR AND OPERATIONAL CONSIDERATIONS
PROJECT LEADERS TO MONITOR PROGRESS AND UPDATE RMB
AWAITING:

1. SITE ANNOUNCEMEMT

(RCC)

2.AWARD OF FIRELINK CONTRACT

3. FINALISATION OF NEW DIMENSION EQUIPMENT LOCATIONS
SROs/

Project

directors


5

C
ALL PROJECTS
COMPOSITION OF WORKSTREAM GROUPS
UNDER-REPRESENTATION OF FINANCE AND HR SPECIALISTS.
COMPOSITON BEING 

REVIEWED, FINANCE SPECIALIST ALLOCATED TO EACH PROJECT AREA.
REVIEW TO BE COMPLETED BY OCTOBER RMB
Project 

directors


6










7










8










9










10










APPENDIX 3   

BEST PRACTICE OVERVIEW

1. BEST PRACTICE RESULTING FROM COLLABORATIVE WORKING


KEY COLLABORATIVE AREA (KCA)
KCA

REFERENCE


DESCRIPTION
COMMENTS

1
PROCUREMENT
3.4
VOLVO PARTS CONTRACT
1.The actual potential spends and parts usage of Volvo vehicles throughout the SE Region fully scoped.

2.The total spend on Volvo vehicle parts fully aggregated. 

3.Captive parts for Volvo vehicles competitively tendered/negotiated 

4. Volvo parts at the right price, quality, quantity and delivery secured. 

5. “Call off” Contracts placed end of March 2005 for Volvo Parts

6.Participating groups to     call off from the agreements







2
TRAINING
4.2 (1)
DEVELOPMENT PROGRAMMES
1.Regional schemes of work for development activities associated with the roles of fire fighter, supervisory manager, middle manager and strategic manager produced.

3

4.3 (1) (6)
HRDG AWARDS
1. A best practice approach to administration and procedures developed and implemented

6. A common framework for Awards within the Region identified and agreed. 







4
HUMAN RESOURCES
5.2 
WORKING PATTERNS
A range of approved working patterns for uniformed personnel that reflect the needs identified by IRMPs developed for use by constituent authorities







5
COMMON AND SPECIALIST SERVICES
6.2
DOMESTIC SAFETY CAMPAIGNS
1.Best guidance provided across region for establishing and running domestic FS Campaigns aimed at reducing death and injury in the home

2. Cost effective approaches to Domestic Fire Safety Campaigns developed

6

6.3
LIFE-LONG LEARNING EDUCATION INITIATIVES
1. Best practice guidance developed across the region for establishing and running educational initiatives for community fire safety aimed at reducing death and injury from fire

2. Cost effective approaches to educational initiatives developed across Region

2. BEST PRACTICE RELATED TO RMB MANAGEMENT PROCESSES


PROCESS
REFERENCE 
DESCRIPTION
COMMENTS

1
PROGRAMME MANAGEMENT
RMB/Clerk
Further 12 month secondment of Programme Manager
Building upon the benefits of a programme- based approach using principles of OGC
 methodology

2
DOCUMENTATION
Programme Manager
Standardisation of templates, documentation and processes.
Greater efficiency and ease of reporting.

Capacity to facilitate “sign-off” and approvals from stakeholders

3
REVIEW OF PROJECT TEAMS
Project Directors
Project teams reviewed to include financial and HR specialists
In order to strengthen the definition of projects and ascertain a true reflection of costs

4
COMMUNICATIONS
Surrey F&RS/Firepro.
1.Formulation of Regional communications Strategy

2.development of RMB Website.
1.Strategy to be presented for approval at July RMB

2.Prototype site now constructed

5
HUMAN RESOURCES
Hampshire F&RS
Advertising for Regional HR Specialist to work on all aspects of strategic HR issues
To be initially funded by Hampshire, with future consideration of proportional funding through RMB FRAs. 

6
FINANCE
Kent F&RS
/RMB Finance Network
1.Development of Business Planning and tentative budgetary considerations for 2006/07

2.Realignment of working groups to include finance specialist.
1.Consideration of RMB impact upon planning cycles of constituent FRAs.

2.Support and advice on budgetary implications of project development

APPENDIX 4           

PROGRAMME SYNOPSIS JULY 2005

Key Collaborative Area
Completed
Ongoing
Stopped
Projects added
Total

KCA 1.Regional Control Centre

1


1








KCA 2.Resilience

8


8








KCA 3. Procurement
1
8


9








KCA 4. Training

4


4








KCA 5.Human Resources
1
5
1
1
8








KCA 6. Common and Specialist Services
3
7


10








Total
6
32
1
1
40

1.Programme Status up to 13 July 2005

Key Collaborative Area
Completed
Ongoing
Stopped
Projects added
Total

KCA 1.Regional Control Centre

1


1








KCA 2.Resilience

8


8








KCA 3. Procurement

8


8








KCA 4. Training

3


3








KCA 5.Human Resources

5
1
1
7








KCA 6. Common and Specialist Services

7


7








Total
0
32
1
1
34

2.Programme Status from 13 July 2005

APPENDIX 5 

PROJECT LIST JULY 2005 

REFERENCE
PROJECT TITLE

KCA. 1
REGIONAL CONTROL CENTRE

1.1
CONTROL CENTRE PROJECT


SUB TOTAL 1

KCA. 2
RESILIENCE

2.1
SITE SPECIFIC RISK ASSESSMENT

2.2
URBAN SEARCH AND RESCUE

2.3
MASS DECONTAMINATION

2.4
DETECTION, ID. AND MONITORING EQUIPMENT

2.5
WATER AND WATER RESCUE

2.6
COMMAND AND CONTROL

2.7
NEW DIMENSION TRAINING

2.8
MULTI-AGENCY RESPONSE TO RESILIENCE


SUB TOTAL 8

KCA. 3
PROCUREMENT

3.1
REGIONAL PROCUREMENT STRATEGY

3.2
PRINT & GRAPHIC DESIGN

3.3
OPERATIONAL EQUIPMENT PROCUREMENT

3.5
SOUTH EAST WEBSITE IMPLEMENTATION

3.6
ELECTRICAL ACCESSORIES CONTRACTS

3.7
CLEANING MATERIALS CONTRACT

3.8
HAZARDOUS MATERIALS DATABASE

3.9
PROCUREMENT TRAINING


SUB TOTAL 8

KCA. 4
TRAINING

4.1
ASSESSMENT AND DEVELOPMENT CENTRES

4.2
DEVELOPMENT PROGRAMMES

4.3
HRDG AWARDS

4.4
TRAINING STRATEGY


SUB TOTAL 4

KCA. 5
HUMAN RESOURCES

5.1
PERSONNEL RESOURCING

5.3
STRUCTURE AND JOB SIZING

5.4
OCCUPATIONAL HEALTH

5.5
POLICIES AND RECORD KEEPING

5.6
WORK/LIFE BALANCE

5.7
TERMS & CONDITIONS OF SERVICE

5.8
EQUALITY AND DIVERSITY


SUB TOTAL 7

KCA 6.
COMMON & SPECIALIST SERVICES

6.1
CO-RESPONDING FOR MEDICAL EMERGENCIES

6.5
FIRE INVESTIGATION PARTNERSHIP

6.6
PARTNERSHIP WORKING

6.7
UNWANTED AND HOAX CALLS

6.8
REGULATORY REFORM ORDER

6.9
SPECIALIST OPS. & MAJOR INCIDENT MANAGEMENT

6.10
MANAGEMENT OF HEALTH & SAFETY


SUB TOTAL 7


PROGRAMME TOTAL: 35 SUB-PROJECTS

� Brokerage Centre-The establishment of a central resource for resource/funding requests and for engineering appropriate synergies between “Independent” projects. 


� To be developed and co-ordinated through the Programme Manager and in liaison with SF&RS Media Department-details to follow.


� CFOA Working Partnership consisting of all FRS Media Specialists within SE Region.


� OGC- Office of Government Commerce (Prince 2 and Managing Successful Programmes)


� Kent F&RS –Abbreviation for Kent and Medway Towns Fire Authority


� NOTE: The updates illustrated above will be reflected in subsequent documentation for the period July –October 2005.











RMB_JUL1305R03.doc

