ITEM TD6   - ANNEX1

OXFORDSHIRE COUNTY COUNCIL

E&E TRANSPORT

TRANSPORT DECISIONS COMMITTEE

PROGRESS OF APPROVED SCHEMES – APRIL 2007 UPDATE

| TIC/CMDT Date | Ref | Scheme | Contact Officer | Status | Implementation Planned (P)/Actual (A) Dates with Comments |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Red | Amber | Green |  |
| 6 December 2002 | 11/02 | Stopping Up of Highway – off Newlands Avenue, Didcot | John Boyd (01865 815082) |  |  |  | With SODC to progress and unable to advise on dates (appears SODC have been reluctant to act but Legal Services are applying pressure). |
| 17 April 2003 | 19/03 | Goring Waiting Restrictions | Peter Ronald (01235 466139) |  |  |  | Superseded by a new scheme. |
| 25 September 2003 | 41/03 | Thornhill Park and Ride Interchange Improvements | Mike Collins (01865 815877) |  |  |  | Programme for construction over 2006/07 and 08 (P). |
| 23 October 2003 | 43/03 | 50mph Speed Limit Proposals: Formal Consultation | Geoff Barrell (01865 810450) |  |  |  | See 20 January 2005 TIC. |
| 8 January 2004 | 01/04 | Kidlington Premium Bus Route | David Taylor (01865 816519) |  |  |  | Oxford Rd/Yarnton Rd Signals & Linking: Imp’d Oct 2005 (A) see 28 Oct 2004 TIC. Kidlington Rbt Bus Lane: January 07 (A). |
|  | 10/04 | A40 Oxford, Headington – Green Road Roundabout Short and Medium Term Measures | Colin Baird (01865 815536) |  |  |  | Medium term measures overtaken by main roundabout scheme implemented December 2006 (A). |
| 17 June 2004 | 40/04 | Oxford, Headington North East, Quarry and Girdlestone Road Parking Controls | Craig Rossington (01865 810443) |  |  |  | Introduced and enforceable. Over 2005/06 and 2006/07. |
| 29 July 2004 | 48/04 | Oxford, London Road, Headington – Provision of an ‘Off Road’ Cycle Route | David Clough (01865 815743) |  |  |  | New brief now expected following implementation of A40 Headington scheme. |
| 28 October 2004 | 58/04 | Premium Bus Routes – Progress of Strategy | David Taylor (01865 816519) |  |  |  | Kidlington to Cutteslowe: Implemented 2005/06 (A). |
|  | 64/04 | Enstone, Bicester Road – Proposed Traffic Calming | Paul Wilson (01865 812612) |  |  |  | April 2007 (P). |
| 20 January 2005 | 01/05 | 50 mph Speed Limit Proposals | Geoff Barrell (01865 810450) |  |  |  | Implemented April 2006 (A). |
|  | 09/05 | Eynsham Traffic Proposals; Consultation Results | David Taylor (01865 816519) |  |  |  | See 16 March 2006 TIC. |
|  | 14/05 | Cholsey Church Railway Bridge; Transfer of Ownership from Wallingford Town Council to Oxfordshire County Council | Peter Brown (01865 815641) |  |  |  | Property Services processing transfer through MouchelParkman. Unable to advise on transfer date. |
| 24 March 2005 | 16/05 | Oxfordshire CC (Dark Lane2 and Moor Avenue1, Witney) (Prohibition of Motor Vehicles) Order 200* | Colin Baird (01865 815536) |  |  |  | Moor Avenue consultation now under way. Dark Lane implemented December 2005 (A). |
| 14 April 2005 | 19/05 | Oxford, Additional Short Term Parking | Andrew Vidovic (01865 810437) |  |  |  | 1st part implemented July 2005 (A). 2nd part implemented March 2006 (A). |
| 7 July 2005 | 30/05 | Deddington, High Street/Horsefair Traffic Signal Junction – Pedestrian Crossing Facility in Horse Fair | Andrew Johnson (01865 815737) |  |  |  | Implemented April 2006 (A). |
|  | 36/05 | Abingdon Integrated Transport Strategy Town Centre Improvements – Traffic Regulation Order | Andy Warren (01865 815835) |  |  |  | Implemented October 2006 (A). |
| 1 September 2005 | 41/05 | Stopping Up of Highway – Milton Park Estate, Sutton Courtenay | Caren O’Sullivan (01865 815916) |  |  |  | Legal Services to process through Magistrates and currently unable to advise on dates because contractual indemnity issues require resolution. |
| 6 October 2005 | 42/05 | Oxford City Centre On-Street Parking Charges – Pilot Scheme | Craig Rossington (01865 810443) |  |  |  | Parking Review undertaken in May 2006 and presented to 8 June 2006 TIC. |
|  | 45/05 | Thame Review of Parking and Waiting Restrictions (Phase 1) | Peter Egawhary (01865 815857) |  |  |  | Implemented May 2006 (A). |
| 17 November 2005 | 49/05 | Banbury: Merton Street/Middleton Road Traffic Signals & OCC (Prohibition of Restriction of Waiting & Loading) Amendment Order 200* | David Clough (01865 815737) |  |  |  | See 27 April 2006 TIC. |
|  | 53/05 | Witney – Woodford Mill Cycle Track | Alex Coley (01865 810443) |  |  |  | Public inquiry in February 2007 now awaiting decision. |
| 22 December 2005 | 59/05 | Oxford, Merrivale Square – Proposed One-way System | John Cramer (01865 815963) |  |  |  | Implemented January 2007 (A). |
|  | 60/05 | Lechlade Road, Faringdon – Proposed Traffic Calming | Lee Turner (01235 466120) |  |  |  | Implemented April 2006 (A). |
|  | 61/05 | Provision of Bus Stop Clearways – Witney Road, Eynsham1 and George Street, Oxford2 | David Taylor (01865 816519) |  |  |  | Witney Road, Eynsham: March (P) & . George Street, Oxford: April 2006 (A). |
| 2 February 2006 | 01/06 | Provision of Bus Stop Clearways – Castle Street, Oxford | David Taylor (01865 816519) |  |  |  | Implemented May 2006 (A). |
|  | 02/06 | Oxford, Quarry Controlled Parking Zone | Richard Kingshott (01865 815716) |  |  |  | Implemented August 2006 (A). |
|  | 03/06 | Oxford, Girdlestone Road Controlled Parking Zone | Richard Kingshott (01865 815716) |  |  |  | Implemented July 2006 (A). |
|  | 04/06 | Banbury, Orchard Way Zebra Crossing | David Clough (01865 815743) |  |  |  | April 2007 (P). |
|  | 05/06 | Stopping up of Highway - Turnagain Lane, Abingdon | Caren O’Sullivan (01865 815916) |  |  |  | Implemented June 2006 (A). |
|  | 06/06 | Bus Services from Wantage/Grove to Abingdon, Oxford, Milton Park and Harwell | David Taylor (01865 816519) |  |  |  | Awaiting conclusions of Didcot (Wantage) Transport Study. |
| 16 March 2006 | 07/06 | Oxford, Headington North East Controlled Parking Zone | Richard Kingshott (01865 815716) |  |  |  | Implemented September 2006 (A). |
|  | 09/06 | Abingdon Town Centre Various Roads 20 mph Speed Restriction Proposals | Ralph Green (01865 815816) |  |  |  | March 2009 (P) to end of Phase 2 works. |
|  | 10/06 | Eynsham Premium Bus Route – Land Acquisition | James Wright (01865 815551) |  |  |  | Significant issues: EA object to flood relief aspect, land CPO requirements may involve PI and funding availability. Project Sponsor to consider options. |
| 27 April 2006 | 11/06 | Banbury. Merton Street/Middleton Road Signalisation and Associated Traffic Regulation Orders | David Clough (01865 815743) |  |  |  | May 2007 (P). |
|  | 12/06 | Oxfordshire County Council (Various Roads, Banbury) (Prohibition and Restriction of Waiting)(Amendment) Order 2006 | Louise Harrison (01865 812632) |  |  |  | Implemented June 2006 (A). |
|  | 13/06 | Oxford, Old Marston Village – Traffic Calming | Andrew Vidovic (01865 810437) |  |  |  | Implemented December 2006 (A). |
|  | 14/06 | Oxfordshire County Council (Footpath No 4 and Footpath No7 Little Wittenham) Footpath Closure Order 2006 | Peter Ronald (01235 466139) |  |  |  | Implemented June 2006 (A). |
|  | 15/06 | Harcourt Road/Charlton Village Road, Wantage – Proposed Traffic Calming | Peter Ronald (01235 466139) |  |  |  | Implemented July 2006 (A). |
| 8 June 2006 | 16/06 | Bicester, Residents Parking Agency Agreement | Ralph Grant (01865 812622) |  |  |  | Agency agreement is agreed between with CDC. Intend to advertise order in April 07 and take any objections to Cabinet Member on 19 July 07. |
|  | 18/06 | Parking Charges Oxford City Centre On-Street Parking | Craig Rossington (01865 810443) |  |  |  | Deferred for consideration at 20 July 2006 TIC. |
|  | 20/06 | Oxford, City Centre Cycle Parking Measures | Andrew Vidovic (01865 810437) |  |  |  | Implemented July 2006 (A). |
|  | 21/06 | Wheatley Traffic Calming Phase 2B: London Road (Between the Two Old London Road Junctions | David Deriaz (01865 815666) |  |  |  | Implemented December 2006 (A). |
| 20 July 2006 | 22/06 | Public Transport Development Programme | David Taylor (01865 816519) |  |  |  | Large number of smaller schemes underway in East Oxford in line with draft Bus Quality Partnership agreements. |
|  | 23/06 | Kidlington Premium Bus Route - Bus Lane Order | James Wright (01865 815551) |  |  |  | Implemented January 2007 (A). |
|  | 24/06 | Oxfordshire County Council (Bicester) (Traffic Regulation) (Amendment) Order 200* | Louise Harrison (01865 812632) |  |  |  | Implemented August 2006 (A). |
|  | 25/06 | Bicester A4095 : Proposed Speed Limits | David Deriaz (01865 815666) |  |  |  | Implemented November 2006 (A). |
|  | 26/06 | Parking Charges Oxford City Centre On-Street Parking | Craig Rossington (01865 810443) |  |  |  | Implemented January 2007 (A). |
|  | 27/06 | Oxford, The Lakes Parking Zone | Richard Kingshott (01865 815716) |  |  |  | Implemented (enforceable) January 2007 (A). |
|  | 28/06 | Oxford, Northway Parking Zone | Richard Kingshott (01865 815716) |  |  |  | Implemented (enforceable) January 2007 (A). |
|  | 29/06 | Oxford Cowley Place Zebra Crossing | Pete Evans (01865 815836) |  |  |  | Implemented September 2006 (A). |
|  | 30/06 | Stopping Up at Roman Way and Garsington Road, Oxford | John Boyd (01865 815082) |  |  |  | On 20 February 2007 Cabinet approved Stopping Up application to go to Magistrates (being arranged by Legal Services). |
|  | 31/06 | Henley Integrated Transport Strategy - Town Centre Scheme Traffic Regulation Orders | Mike Collins (01865 815877) |  |  |  | Implemented October 2006 (A). |
|  | 32/06 | Disabled Persons' Parking Places - Vale of White Horse District | Mike Ruse (01865 815978) |  |  |  | Implemented October 2006 (A). |
| 14 September 2006 | 33/06 | Disabled Persons’ Parking Places – South Oxfordshire District | Mike Ruse (01865 815978) |  |  |  | Implemented November 2006 (A). |
|  | 34/06 | Shillingford Bridge Signalisation | Gary Critchlow-Smith (01865 815817) |  |  |  | Ph 1 April 2007 (P). Ph 2 Autumn 2007 (P) subject to funding. |
| 6 October 2006 | 38/06 | Camera Enforcement – Oxford City Centre Bus Gates | Alex Coley (01865 810409) |  |  |  | Implemented February 2007 (A). |
|  | 39/06 | Oxford, Marston South Controlled Parking Zone | Richard Kingshott (01865 815716) |  |  |  | April 2007 (P). |
|  | 40/06 | A361 Banbury Road, Bloxham, Ells Lane Proposed Controlled Crossing | James Wright (01865 815551) |  |  |  | Developer is awaiting S273 agreement from OCC Development Control. |
|  | 42/06 | Gorwell, Watlington – Amendments to One Way and No Waiting Traffic Order | Malcolm Bowler (01235 466119) |  |  |  | Implemented February 2007 (A). |
|  | 43/06 | Henley-on-Thames, Market Place – Proposed Traffic Regulation (Amendment) Order | Malcolm Bowler (01235 466119) |  |  |  | Implemented March 2007 (A). |
|  | 44/06 | Disabled Persons’ Parking Places – Cherwell District | Mike Ruse (01865 815978) |  |  |  | Implemented February 2007 (A). |
|  | 45/06 | Disabled Persons’ Parking Places – West Oxfordshire District | Mike Ruse (01865 815978) |  |  |  | Implemented March 2007 (A). |
| 24 November 2006 | 46/06 | Oxfordshire County Council (Banbury, Ruscote Avenue)(Prohibition of Right Turns) Order 200* | David Clough (01865 815743) |  |  |  | March 2007 (P). |
|  | 47/06 | Special Parking Areas Outside Oxford - Enforcement Arrangements | Steve Smith (01865 810435) |  |  |  | April 2008 (P). Work being undertaken to develop agency agreements with District Authorities to administer the proposed scheme. |
|  | 48/06 | Oxford: Headley Way Cycle/Pedestrian Crossing | Craig Rossington (01865 815575) |  |  |  | March 2007 (P). |
| 4 January 2007 | 01/07 | Implementation of Bus Stop Clearways – Various | Daniel Metcalfe (01865 815683) |  |  |  | Implemented January 2007 (A). |
|  | 02/07 | Cowley Road, Oxford – Traffic Regulation Order Amendments to Waiting and Parking | John Cramer (01865 815963) |  |  |  | April 2007 (P). |
|  | 03/07 | Oxford, A40 Elsfield Way to Jackson Road Experimental Left Turn Ban | Jeremy Dufour (01865 815625) |  |  |  | March 2007 (P). |
| 15 February 2007 | 04/07 | 50mph Speed Limit Proposals | James Wright (01865 815551) |  |  |  | June 2007 (P). |
|  | 05/07 | Oxford, George Street/Cornmarket Street, Oxford – Review of Traffic Signals | John Cramer (01865 815963) |  |  |  | Further report to be considered in March 2008. |
|  | 06/07 | Oxfordshire County Council (High Street, Didcot) (Bus Lane, One Way and Prohibition of Waiting) Order 2007 | Malcolm Bowler (01235 466119) |  |  |  | Implemented March 2007 (A). |
|  | 07/07 | Coopers Lane, Abingdon – Amendment to Restriction of waiting Traffic Order | Lee Turner (01235) 466120 |  |  |  | April 2007 (P). |

# Text boxes

G

G

G

G

G

G

G

G

G

G

R

G

G

G

G

A

A

G

G

G

A

A

A

A

G